## PERT Input Audit
Activity ID | Activity / Stage | Predecessor | Successor | O | ML | P | Status | Message
e12 | Identification | Start VO Trigger | Evaluation / Proposal | 5 | 7 | 10 | PASS | Matches authoritative six-activity route
e23 | Evaluation / Proposal | Identification | Approval / Instruction | 5 | 7 | 10 | PASS | Matches authoritative six-activity route
e34 | Approval / Instruction | Evaluation / Proposal | Implementation | 10 | 14 | 20 | PASS | Matches authoritative six-activity route
e45 | Implementation (Control Point) | Approval / Instruction | Inspection / Verification | 50 | 60 | 80 | PASS | Matches authoritative six-activity route
e56 | Inspection / Verification | Implementation | Valuation & Adjustment | 10 | 12 | 14 | PASS | Matches authoritative six-activity route
e67 | Valuation & Adjustment (Consolidation) | Inspection / Verification | Final Closeout | 7 | 10 | 12 | PASS | Matches authoritative six-activity route

## Validation
Check | Status
Correct PERT file selected | PASS
Input hashes recorded | PASS
PERT rows = 6 | PASS
PERT route exact | PASS
PERT sums O/ML/P | PASS
PERT duration ordering | PASS
PERT 50,000 valid results | PASS
PERT analytical verification passed | PASS

## Metadata
Field | Value
Input file | C:\Users\moham\OneDrive\Desktop\PERT Input.docx
SHA-256 | 7984b5b2e29928345772f0110ea1fa1c9ceb4121dc2e3aed4737112a98bc1f58
Rows | 6
Generated status | PRELIMINARY EXPERIMENTAL SIMULATION RESULTS