## Input Audit
Word table row | Source node name | Node ID | Input logic | Output logic | Arc expression | Arc Tag | Probability | Loop Cap | O | ML | P | Probability-group total | Missing fields | PERT use | GERT use | Validation status | Validation message
5 | Identification | S1 | XOR | XOR | S1 -> S1 | e12 | 0.6 |  | 5 | 7 | 10 | 1 |  | Yes - fixed PERT activity input | Yes | PASS | Numerical and explicit GERT structural fields valid.
6 | Identification | S1 | XOR | XOR | S1 -> ST | e1T | 0.4 |  | 2 | 3 | 4 | 1 |  | No | Yes | PASS | Numerical and explicit GERT structural fields valid.
7 | Evaluation / Proposal | S2 | XOR | XOR | S2 -> S3 | e23 | 0.01 |  | 5 | 7 | 10 | 1 |  | Yes - fixed PERT activity input | Yes | PASS | Numerical and explicit GERT structural fields valid.
8 | Evaluation / Proposal | S2 | XOR | XOR | S2 -> S4 | e24 | 0.9 |  | 12 | 15 | 17 | 1 |  | No | Yes | PASS | Numerical and explicit GERT structural fields valid.
9 | Evaluation / Proposal | S2 | XOR | XOR | S2 -> S2 | e22 | 0.04 | 2 | 7 | 9 | 12 | 1 |  | No | Yes | PASS | Numerical and explicit GERT structural fields valid.
10 | Evaluation / Proposal | S2 | XOR | XOR | S2 -> S1 | e21 | 0.04 | 2 | 3 | 5 | 7 | 1 |  | No | Yes | PASS | Numerical and explicit GERT structural fields valid.
11 | Evaluation / Proposal | S2 | XOR | XOR | S2 -> ST | e2T | 0.01 |  | 7 | 10 | 12 | 1 |  | No | Yes | PASS | Numerical and explicit GERT structural fields valid.
12 | Approval / Instruction | S3 | XOR | XOR | S3 -> S4 | e34 | 0.9 |  | 10 | 14 | 20 | 1 |  | Yes - fixed PERT activity input | Yes | PASS | Numerical and explicit GERT structural fields valid.
13 | Approval / Instruction | S3 | XOR | XOR | S3 -> S3 | e33 | 0.04 | 2 | 4 | 7 | 10 | 1 |  | No | Yes | PASS | Numerical and explicit GERT structural fields valid.
14 | Approval / Instruction | S3 | XOR | XOR | S3 -> S2 | e32 | 0.04 | 2 | 10 | 14 | 20 | 1 |  | Yes - fixed PERT activity input | Yes | PASS | Numerical and explicit GERT structural fields valid.
15 | Approval / Instruction | S3 | XOR | XOR | S3 -> ST | e3T | 0.01 |  | 10 | 14 | 20 | 1 |  | Yes - fixed PERT activity input | Yes | PASS | Numerical and explicit GERT structural fields valid.
16 | Approval / Instruction | S3 | XOR | XOR | S3 -> SD | e3D | 0.01 |  | 10 | 14 | 20 | 1 |  | Yes - fixed PERT activity input | Yes | PASS | Numerical and explicit GERT structural fields valid.
17 | Implementation (Control Point) | S4 | XOR | XOR | S4 -> S5 | e45 | 0.9 |  | 50 | 60 | 80 | 1 |  | Yes - fixed PERT activity input | Yes | PASS | Numerical and explicit GERT structural fields valid.
18 | Implementation (Control Point) | S4 | XOR | XOR | S4 -> S6 | e46 | 0.05 |  | 40 | 45 | 50 | 1 |  | No | Yes | PASS | Numerical and explicit GERT structural fields valid.
19 | Implementation (Control Point) | S4 | XOR | XOR | S4 -> S3 | e43 | 0.02 | 2 | 5 | 7 | 10 | 1 |  | No | Yes | PASS | Numerical and explicit GERT structural fields valid.
20 | Implementation (Control Point) | S4 | XOR | XOR | S4 -> S2 | e42 | 0.01 | 2 | 7 | 10 | 12 | 1 |  | No | Yes | PASS | Numerical and explicit GERT structural fields valid.
21 | Implementation (Control Point) | S4 | XOR | XOR | S4 -> SD | e4D | 0.02 |  | 7 | 10 | 12 | 1 |  | No | Yes | PASS | Numerical and explicit GERT structural fields valid.
22 | Inspection / Verification | S5 | XOR | XOR | S5 -> S6 | e56 | 0.9 |  | 10 | 12 | 14 | 1 |  | Yes - fixed PERT activity input | Yes | PASS | Numerical and explicit GERT structural fields valid.
23 | Inspection / Verification | S5 | XOR | XOR | S5 -> S7 | e57 | 0.05 |  | 7 | 10 | 12 | 1 |  | No | Yes | PASS | Numerical and explicit GERT structural fields valid.
24 | Inspection / Verification | S5 | XOR | XOR | S5 -> S5 | e55 | 0.01 | 2 | 2 | 5 | 7 | 1 |  | No | Yes | PASS | Numerical and explicit GERT structural fields valid.
25 | Inspection / Verification | S5 | XOR | XOR | S5 -> S4 | e54 | 0.02 | 2 | 7 | 10 | 12 | 1 |  | No | Yes | PASS | Numerical and explicit GERT structural fields valid.
26 | Inspection / Verification | S5 | XOR | XOR | S5 -> S2 | e52 | 0.01 | 2 | 7 | 10 | 12 | 1 |  | No | Yes | PASS | Numerical and explicit GERT structural fields valid.
27 | Inspection / Verification | S5 | XOR | XOR | S5 -> SD | e5D | 0.01 |  | 7 | 10 | 12 | 1 |  | No | Yes | PASS | Numerical and explicit GERT structural fields valid.
28 | Valuation & Adjustment (Consolidation) | S6 | XOR | XOR | S6 -> S7 | e67 | 0.95 |  | 7 | 10 | 12 | 1 |  | Yes - fixed PERT activity input | Yes | PASS | Numerical and explicit GERT structural fields valid.
29 | Valuation & Adjustment (Consolidation) | S6 | XOR | XOR | S6 -> S6 | e66 | 0.04 | 2 | 5 | 7 | 10 | 1 |  | No | Yes | PASS | Numerical and explicit GERT structural fields valid.
30 | Valuation & Adjustment (Consolidation) | S6 | XOR | XOR | S6 -> SD | e6D | 0.01 |  | 7 | 10 | 12 | 1 |  | Yes - fixed PERT activity input | Yes | PASS | Numerical and explicit GERT structural fields valid.
31 | Dispute Resolution | SD | XOR | XOR | SD -> S3 | eD3 | 0.9 |  | 5 | 7 | 10 | 1 |  | No | Yes | PASS | Numerical and explicit GERT structural fields valid.
32 | Dispute Resolution | SD | XOR | XOR | SD -> S7 | eD7 | 0.05 |  | 5 | 7 | 10 | 1 |  | No | Yes | PASS | Numerical and explicit GERT structural fields valid.
33 | Dispute Resolution | SD | XOR | XOR | SD -> ST | eDT | 0.05 |  | 5 | 7 | 10 | 1 |  | No | Yes | PASS | Numerical and explicit GERT structural fields valid.

## Validation
Check | Result
Parsed node groups | 11
Probabilistic records | 29
Probability groups | 7
Probability group sums | PASS
Loop Cap = 2 records | 10
GERT structural gate | PASS
GERT status | GERT SIMULATION RUN - PASS

## Metadata
Field | Value
Input file | C:\Users\moham\OneDrive\Desktop\Authoritative_GERT_PERT_Input.docx.docx
SHA-256 | ae6cd0c5088ac5965a1b098c3428384ba5b71f67ccbe2a7c595b0f3fbe69bd0b
Generated title | PRELIMINARY EXPERIMENTAL SIMULATION RESULTS