| Activity ID | Activity / Stage | Predecessor — السابق | Successor — اللاحق | Optimistic O | Most Likely ML | Pessimistic P |
| --- | --- | --- | --- | --- | --- | --- |
| e12 | Identification | Start VO Trigger | Evaluation / Proposal | 5 | 7 | 10 |
| e23 | Evaluation / Proposal | Identification | Approval / Instruction | 5 | 7 | 10 |
| e34 | Approval / Instruction | Evaluation / Proposal | Implementation | 10 | 14 | 20 |
| e45 | Implementation (Control Point) | Approval / Instruction | Inspection / Verification | 50 | 60 | 80 |
| e56 | Inspection / Verification | Implementation | Valuation & Adjustment | 10 | 12 | 14 |
| e67 | Valuation & Adjustment (Consolidation) | Inspection / Verification | Final Closeout | 7 | 10 | 12 |