## Run Metadata
Field | Value
Result_Status | PRELIMINARY EXPERIMENTAL SIMULATION RESULTS
Program_Version | raw-data-export-1.0.0
Iterations | 50000
Root_Seed | 42
Time_Unit | days
Beta_PERT_Lambda | 4.0
PERT_Run_ID | PERT-42-50000-01
GERT_Run_ID | GERT-42-50000-01
Start_Time_UTC | 2026-07-29T21:27:24+00:00
Simulation_Completion_UTC | 2026-07-29T21:54:03+00:00
PERT_Input_File | PERT Input.docx
PERT_SHA256 | 7984b5b2e29928345772f0110ea1fa1c9ceb4121dc2e3aed4737112a98bc1f58
GERT_Input_File | GERT nput.docx
GERT_SHA256 | dc34b00fcd3988146da0760ac18499eeca9d8596601c09445ca5d956c4ae6387
PERT_Reproducibility | PASS
GERT_Reproducibility | PASS
Exact_Verification | PASS
Monte_Carlo_Acceptance | PASS

## PERT Input
Sequence | Activity_ID | Activity_Name | Predecessor | Successor | O | ML | P | Alpha | Beta
1 | e12 | Identification | Start VO Trigger | Evaluation / Proposal | 5 | 7 | 10 | 2.6 | 3.4
2 | e23 | Evaluation / Proposal | Identification | Approval / Instruction | 5 | 7 | 10 | 2.6 | 3.4
3 | e34 | Approval / Instruction | Evaluation / Proposal | Implementation | 10 | 14 | 20 | 2.6 | 3.4
4 | e45 | Implementation (Control Point) | Approval / Instruction | Inspection / Verification | 50 | 60 | 80 | 2.3333 | 3.6667
5 | e56 | Inspection / Verification | Implementation | Valuation & Adjustment | 10 | 12 | 14 | 3 | 3
6 | e67 | Valuation & Adjustment (Consolidation) | Inspection / Verification | Final Closeout | 7 | 10 | 12 | 3.4 | 2.6

## GERT Nodes
Node_ID | Node_Name | Input_Logic | Output_Logic | Role | Word_Row
S0 | Start VO Trigger |  | XOR | Start | 4
S1 | Identification | XOR | XOR | Transient | 6
S2 | Evaluation / Proposal | XOR | XOR | Transient | 11
S3 | Approval / Instruction | XOR | XOR | Transient | 16
S4 | Implementation (Control Point) | XOR | XOR | Transient | 21
S5 | Inspection / Verification | XOR | XOR | Transient | 27
S6 | Valuation & Adjustment (Consolidation) | XOR | XOR | Transient | 30
SD | Dispute Resolution | XOR | XOR | Dispute Transient | 33
S7 | Final Closeout | XOR |  | Successful Terminal | 34
ST | Withdrawn / Rejected | XOR |  | Terminated Terminal | 35

## GERT Arcs
Arc_Tag | From_Node | To_Node | Original_Probability | Loop_Cap | O | ML | P | Alpha | Beta | Structural
e01 | S0 | S1 | 1 |  | 0 | 0 | 0 |  |  | TRUE
e12 | S1 | S2 | 0.6 |  | 5 | 7 | 10 | 2.6 | 3.4 | FALSE
e1T | S1 | ST | 0.4 |  | 2 | 3 | 4 | 3 | 3 | FALSE
e23 | S2 | S3 | 0.01 |  | 5 | 7 | 10 | 2.6 | 3.4 | FALSE
e24 | S2 | S4 | 0.9 |  | 12 | 15 | 17 | 3.4 | 2.6 | FALSE
e22 | S2 | S2 | 0.04 | 2 | 7 | 9 | 12 | 2.6 | 3.4 | FALSE
e21 | S2 | S1 | 0.04 | 2 | 3 | 5 | 7 | 3 | 3 | FALSE
e2T | S2 | ST | 0.01 |  | 7 | 10 | 12 | 3.4 | 2.6 | FALSE
e34 | S3 | S4 | 0.9 |  | 10 | 14 | 20 | 2.6 | 3.4 | FALSE
e33 | S3 | S3 | 0.04 | 2 | 4 | 7 | 10 | 3 | 3 | FALSE
e32 | S3 | S2 | 0.04 | 2 | 10 | 14 | 20 | 2.6 | 3.4 | FALSE
e3T | S3 | ST | 0.01 |  | 10 | 14 | 20 | 2.6 | 3.4 | FALSE
e3D | S3 | SD | 0.01 |  | 10 | 14 | 20 | 2.6 | 3.4 | FALSE
e45 | S4 | S5 | 0.9 |  | 50 | 60 | 80 | 2.3333 | 3.6667 | FALSE
e46 | S4 | S6 | 0.05 |  | 40 | 45 | 50 | 3 | 3 | FALSE
e43 | S4 | S3 | 0.02 | 2 | 5 | 7 | 10 | 2.6 | 3.4 | FALSE
e42 | S4 | S2 | 0.01 | 2 | 7 | 10 | 12 | 3.4 | 2.6 | FALSE
e4D | S4 | SD | 0.02 |  | 7 | 10 | 12 | 3.4 | 2.6 | FALSE
e56 | S5 | S6 | 0.9 |  | 10 | 12 | 14 | 3 | 3 | FALSE
e57 | S5 | S7 | 0.05 |  | 7 | 10 | 12 | 3.4 | 2.6 | FALSE
e55 | S5 | S5 | 0.01 | 2 | 2 | 5 | 7 | 3.4 | 2.6 | FALSE
e54 | S5 | S4 | 0.02 | 2 | 7 | 10 | 12 | 3.4 | 2.6 | FALSE
e52 | S5 | S2 | 0.01 | 2 | 7 | 10 | 12 | 3.4 | 2.6 | FALSE
e5D | S5 | SD | 0.01 |  | 7 | 10 | 12 | 3.4 | 2.6 | FALSE
e67 | S6 | S7 | 0.95 |  | 7 | 10 | 12 | 3.4 | 2.6 | FALSE
e66 | S6 | S6 | 0.04 | 2 | 5 | 7 | 10 | 2.6 | 3.4 | FALSE
e6D | S6 | SD | 0.01 |  | 7 | 10 | 12 | 3.4 | 2.6 | FALSE
eD3 | SD | S3 | 0.9 |  | 5 | 7 | 10 | 2.6 | 3.4 | FALSE
eD7 | SD | S7 | 0.05 |  | 5 | 7 | 10 | 2.6 | 3.4 | FALSE
eDT | SD | ST | 0.05 |  | 5 | 7 | 10 | 2.6 | 3.4 | FALSE

## Probability Groups
From_Node | Arc_Count | Original_Probability_Sum | Required_Sum | Difference | Valid | Arc_Tags
S1 | 2 | 1 | 1 | 0 | TRUE | e12;e1T
S2 | 5 | 1 | 1 | 0 | TRUE | e23;e24;e22;e21;e2T
S3 | 5 | 1 | 1 | 0 | TRUE | e34;e33;e32;e3T;e3D
S4 | 5 | 1 | 1 | 0 | TRUE | e45;e46;e43;e42;e4D
S5 | 6 | 1 | 1 | 0 | TRUE | e56;e57;e55;e54;e52;e5D
S6 | 3 | 1 | 1 | 0 | TRUE | e67;e66;e6D
SD | 3 | 1 | 1 | 0 | TRUE | eD3;eD7;eDT

## Loop Register
Loop_ID | Arc_Tag | From_Node | To_Node | Loop_Cap | Rule | Valid
e22 | e22 | S2 | S2 | 2 | Independent capped return arc | TRUE
e21 | e21 | S2 | S1 | 2 | Independent capped return arc | TRUE
e33 | e33 | S3 | S3 | 2 | Independent capped return arc | TRUE
e32 | e32 | S3 | S2 | 2 | Independent capped return arc | TRUE
e43 | e43 | S4 | S3 | 2 | Independent capped return arc | TRUE
e42 | e42 | S4 | S2 | 2 | Independent capped return arc | TRUE
e55 | e55 | S5 | S5 | 2 | Independent capped return arc | TRUE
e54 | e54 | S5 | S4 | 2 | Independent capped return arc | TRUE
e52 | e52 | S5 | S2 | 2 | Independent capped return arc | TRUE
e66 | e66 | S6 | S6 | 2 | Independent capped return arc | TRUE

## Parameter Register
Parameter_ID | Model | Entity_Type | Entity_ID | Parameter_Name | Baseline_Value | Data_Type | Unit | Allowed_Minimum | Allowed_Maximum | Constraint_Group | Constraint_Rule | Sensitivity_Eligible | Sensitivity_Method | Notes
PERT.e12.O | PERT | Activity | e12 | O | 5 | double | days |  |  | e12 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
PERT.e12.ML | PERT | Activity | e12 | ML | 7 | double | days |  |  | e12 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
PERT.e12.P | PERT | Activity | e12 | P | 10 | double | days |  |  | e12 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
PERT.e23.O | PERT | Activity | e23 | O | 5 | double | days |  |  | e23 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
PERT.e23.ML | PERT | Activity | e23 | ML | 7 | double | days |  |  | e23 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
PERT.e23.P | PERT | Activity | e23 | P | 10 | double | days |  |  | e23 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
PERT.e34.O | PERT | Activity | e34 | O | 10 | double | days |  |  | e34 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
PERT.e34.ML | PERT | Activity | e34 | ML | 14 | double | days |  |  | e34 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
PERT.e34.P | PERT | Activity | e34 | P | 20 | double | days |  |  | e34 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
PERT.e45.O | PERT | Activity | e45 | O | 50 | double | days |  |  | e45 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
PERT.e45.ML | PERT | Activity | e45 | ML | 60 | double | days |  |  | e45 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
PERT.e45.P | PERT | Activity | e45 | P | 80 | double | days |  |  | e45 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
PERT.e56.O | PERT | Activity | e56 | O | 10 | double | days |  |  | e56 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
PERT.e56.ML | PERT | Activity | e56 | ML | 12 | double | days |  |  | e56 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
PERT.e56.P | PERT | Activity | e56 | P | 14 | double | days |  |  | e56 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
PERT.e67.O | PERT | Activity | e67 | O | 7 | double | days |  |  | e67 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
PERT.e67.ML | PERT | Activity | e67 | ML | 10 | double | days |  |  | e67 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
PERT.e67.P | PERT | Activity | e67 | P | 12 | double | days |  |  | e67 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e12.O | GERT | Arc | e12 | O | 5 | double | days |  |  | e12 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e12.ML | GERT | Arc | e12 | ML | 7 | double | days |  |  | e12 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e12.P | GERT | Arc | e12 | P | 10 | double | days |  |  | e12 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e12.Probability | GERT | Arc | e12 | Probability | 0.6 | double | dimensionless | 0 | 1 | S1 | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
GERT.e1T.O | GERT | Arc | e1T | O | 2 | double | days |  |  | e1T | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e1T.ML | GERT | Arc | e1T | ML | 3 | double | days |  |  | e1T | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e1T.P | GERT | Arc | e1T | P | 4 | double | days |  |  | e1T | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e1T.Probability | GERT | Arc | e1T | Probability | 0.4 | double | dimensionless | 0 | 1 | S1 | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
GERT.e23.O | GERT | Arc | e23 | O | 5 | double | days |  |  | e23 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e23.ML | GERT | Arc | e23 | ML | 7 | double | days |  |  | e23 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e23.P | GERT | Arc | e23 | P | 10 | double | days |  |  | e23 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e23.Probability | GERT | Arc | e23 | Probability | 0.01 | double | dimensionless | 0 | 1 | S2 | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
GERT.e24.O | GERT | Arc | e24 | O | 12 | double | days |  |  | e24 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e24.ML | GERT | Arc | e24 | ML | 15 | double | days |  |  | e24 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e24.P | GERT | Arc | e24 | P | 17 | double | days |  |  | e24 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e24.Probability | GERT | Arc | e24 | Probability | 0.9 | double | dimensionless | 0 | 1 | S2 | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
GERT.e22.O | GERT | Arc | e22 | O | 7 | double | days |  |  | e22 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e22.ML | GERT | Arc | e22 | ML | 9 | double | days |  |  | e22 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e22.P | GERT | Arc | e22 | P | 12 | double | days |  |  | e22 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e22.Probability | GERT | Arc | e22 | Probability | 0.04 | double | dimensionless | 0 | 1 | S2 | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
GERT.e22.LoopCap | GERT | Loop | e22 | Loop Cap | 2 | integer | traversals | 0 |  | e22 | Non-negative integer; baseline 2 | TRUE | Discrete scenario analysis | Alternative caps require model-owner approval
GERT.e21.O | GERT | Arc | e21 | O | 3 | double | days |  |  | e21 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e21.ML | GERT | Arc | e21 | ML | 5 | double | days |  |  | e21 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e21.P | GERT | Arc | e21 | P | 7 | double | days |  |  | e21 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e21.Probability | GERT | Arc | e21 | Probability | 0.04 | double | dimensionless | 0 | 1 | S2 | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
GERT.e21.LoopCap | GERT | Loop | e21 | Loop Cap | 2 | integer | traversals | 0 |  | e21 | Non-negative integer; baseline 2 | TRUE | Discrete scenario analysis | Alternative caps require model-owner approval
GERT.e2T.O | GERT | Arc | e2T | O | 7 | double | days |  |  | e2T | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e2T.ML | GERT | Arc | e2T | ML | 10 | double | days |  |  | e2T | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e2T.P | GERT | Arc | e2T | P | 12 | double | days |  |  | e2T | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e2T.Probability | GERT | Arc | e2T | Probability | 0.01 | double | dimensionless | 0 | 1 | S2 | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
GERT.e34.O | GERT | Arc | e34 | O | 10 | double | days |  |  | e34 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e34.ML | GERT | Arc | e34 | ML | 14 | double | days |  |  | e34 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e34.P | GERT | Arc | e34 | P | 20 | double | days |  |  | e34 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e34.Probability | GERT | Arc | e34 | Probability | 0.9 | double | dimensionless | 0 | 1 | S3 | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
GERT.e33.O | GERT | Arc | e33 | O | 4 | double | days |  |  | e33 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e33.ML | GERT | Arc | e33 | ML | 7 | double | days |  |  | e33 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e33.P | GERT | Arc | e33 | P | 10 | double | days |  |  | e33 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e33.Probability | GERT | Arc | e33 | Probability | 0.04 | double | dimensionless | 0 | 1 | S3 | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
GERT.e33.LoopCap | GERT | Loop | e33 | Loop Cap | 2 | integer | traversals | 0 |  | e33 | Non-negative integer; baseline 2 | TRUE | Discrete scenario analysis | Alternative caps require model-owner approval
GERT.e32.O | GERT | Arc | e32 | O | 10 | double | days |  |  | e32 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e32.ML | GERT | Arc | e32 | ML | 14 | double | days |  |  | e32 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e32.P | GERT | Arc | e32 | P | 20 | double | days |  |  | e32 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e32.Probability | GERT | Arc | e32 | Probability | 0.04 | double | dimensionless | 0 | 1 | S3 | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
GERT.e32.LoopCap | GERT | Loop | e32 | Loop Cap | 2 | integer | traversals | 0 |  | e32 | Non-negative integer; baseline 2 | TRUE | Discrete scenario analysis | Alternative caps require model-owner approval
GERT.e3T.O | GERT | Arc | e3T | O | 10 | double | days |  |  | e3T | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e3T.ML | GERT | Arc | e3T | ML | 14 | double | days |  |  | e3T | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e3T.P | GERT | Arc | e3T | P | 20 | double | days |  |  | e3T | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e3T.Probability | GERT | Arc | e3T | Probability | 0.01 | double | dimensionless | 0 | 1 | S3 | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
GERT.e3D.O | GERT | Arc | e3D | O | 10 | double | days |  |  | e3D | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e3D.ML | GERT | Arc | e3D | ML | 14 | double | days |  |  | e3D | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e3D.P | GERT | Arc | e3D | P | 20 | double | days |  |  | e3D | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e3D.Probability | GERT | Arc | e3D | Probability | 0.01 | double | dimensionless | 0 | 1 | S3 | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
GERT.e45.O | GERT | Arc | e45 | O | 50 | double | days |  |  | e45 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e45.ML | GERT | Arc | e45 | ML | 60 | double | days |  |  | e45 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e45.P | GERT | Arc | e45 | P | 80 | double | days |  |  | e45 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e45.Probability | GERT | Arc | e45 | Probability | 0.9 | double | dimensionless | 0 | 1 | S4 | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
GERT.e46.O | GERT | Arc | e46 | O | 40 | double | days |  |  | e46 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e46.ML | GERT | Arc | e46 | ML | 45 | double | days |  |  | e46 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e46.P | GERT | Arc | e46 | P | 50 | double | days |  |  | e46 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e46.Probability | GERT | Arc | e46 | Probability | 0.05 | double | dimensionless | 0 | 1 | S4 | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
GERT.e43.O | GERT | Arc | e43 | O | 5 | double | days |  |  | e43 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e43.ML | GERT | Arc | e43 | ML | 7 | double | days |  |  | e43 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e43.P | GERT | Arc | e43 | P | 10 | double | days |  |  | e43 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e43.Probability | GERT | Arc | e43 | Probability | 0.02 | double | dimensionless | 0 | 1 | S4 | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
GERT.e43.LoopCap | GERT | Loop | e43 | Loop Cap | 2 | integer | traversals | 0 |  | e43 | Non-negative integer; baseline 2 | TRUE | Discrete scenario analysis | Alternative caps require model-owner approval
GERT.e42.O | GERT | Arc | e42 | O | 7 | double | days |  |  | e42 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e42.ML | GERT | Arc | e42 | ML | 10 | double | days |  |  | e42 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e42.P | GERT | Arc | e42 | P | 12 | double | days |  |  | e42 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e42.Probability | GERT | Arc | e42 | Probability | 0.01 | double | dimensionless | 0 | 1 | S4 | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
GERT.e42.LoopCap | GERT | Loop | e42 | Loop Cap | 2 | integer | traversals | 0 |  | e42 | Non-negative integer; baseline 2 | TRUE | Discrete scenario analysis | Alternative caps require model-owner approval
GERT.e4D.O | GERT | Arc | e4D | O | 7 | double | days |  |  | e4D | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e4D.ML | GERT | Arc | e4D | ML | 10 | double | days |  |  | e4D | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e4D.P | GERT | Arc | e4D | P | 12 | double | days |  |  | e4D | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e4D.Probability | GERT | Arc | e4D | Probability | 0.02 | double | dimensionless | 0 | 1 | S4 | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
GERT.e56.O | GERT | Arc | e56 | O | 10 | double | days |  |  | e56 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e56.ML | GERT | Arc | e56 | ML | 12 | double | days |  |  | e56 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e56.P | GERT | Arc | e56 | P | 14 | double | days |  |  | e56 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e56.Probability | GERT | Arc | e56 | Probability | 0.9 | double | dimensionless | 0 | 1 | S5 | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
GERT.e57.O | GERT | Arc | e57 | O | 7 | double | days |  |  | e57 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e57.ML | GERT | Arc | e57 | ML | 10 | double | days |  |  | e57 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e57.P | GERT | Arc | e57 | P | 12 | double | days |  |  | e57 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e57.Probability | GERT | Arc | e57 | Probability | 0.05 | double | dimensionless | 0 | 1 | S5 | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
GERT.e55.O | GERT | Arc | e55 | O | 2 | double | days |  |  | e55 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e55.ML | GERT | Arc | e55 | ML | 5 | double | days |  |  | e55 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e55.P | GERT | Arc | e55 | P | 7 | double | days |  |  | e55 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e55.Probability | GERT | Arc | e55 | Probability | 0.01 | double | dimensionless | 0 | 1 | S5 | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
GERT.e55.LoopCap | GERT | Loop | e55 | Loop Cap | 2 | integer | traversals | 0 |  | e55 | Non-negative integer; baseline 2 | TRUE | Discrete scenario analysis | Alternative caps require model-owner approval
GERT.e54.O | GERT | Arc | e54 | O | 7 | double | days |  |  | e54 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e54.ML | GERT | Arc | e54 | ML | 10 | double | days |  |  | e54 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e54.P | GERT | Arc | e54 | P | 12 | double | days |  |  | e54 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e54.Probability | GERT | Arc | e54 | Probability | 0.02 | double | dimensionless | 0 | 1 | S5 | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
GERT.e54.LoopCap | GERT | Loop | e54 | Loop Cap | 2 | integer | traversals | 0 |  | e54 | Non-negative integer; baseline 2 | TRUE | Discrete scenario analysis | Alternative caps require model-owner approval
GERT.e52.O | GERT | Arc | e52 | O | 7 | double | days |  |  | e52 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e52.ML | GERT | Arc | e52 | ML | 10 | double | days |  |  | e52 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e52.P | GERT | Arc | e52 | P | 12 | double | days |  |  | e52 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e52.Probability | GERT | Arc | e52 | Probability | 0.01 | double | dimensionless | 0 | 1 | S5 | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
GERT.e52.LoopCap | GERT | Loop | e52 | Loop Cap | 2 | integer | traversals | 0 |  | e52 | Non-negative integer; baseline 2 | TRUE | Discrete scenario analysis | Alternative caps require model-owner approval
GERT.e5D.O | GERT | Arc | e5D | O | 7 | double | days |  |  | e5D | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e5D.ML | GERT | Arc | e5D | ML | 10 | double | days |  |  | e5D | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e5D.P | GERT | Arc | e5D | P | 12 | double | days |  |  | e5D | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e5D.Probability | GERT | Arc | e5D | Probability | 0.01 | double | dimensionless | 0 | 1 | S5 | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
GERT.e67.O | GERT | Arc | e67 | O | 7 | double | days |  |  | e67 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e67.ML | GERT | Arc | e67 | ML | 10 | double | days |  |  | e67 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e67.P | GERT | Arc | e67 | P | 12 | double | days |  |  | e67 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e67.Probability | GERT | Arc | e67 | Probability | 0.95 | double | dimensionless | 0 | 1 | S6 | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
GERT.e66.O | GERT | Arc | e66 | O | 5 | double | days |  |  | e66 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e66.ML | GERT | Arc | e66 | ML | 7 | double | days |  |  | e66 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e66.P | GERT | Arc | e66 | P | 10 | double | days |  |  | e66 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e66.Probability | GERT | Arc | e66 | Probability | 0.04 | double | dimensionless | 0 | 1 | S6 | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
GERT.e66.LoopCap | GERT | Loop | e66 | Loop Cap | 2 | integer | traversals | 0 |  | e66 | Non-negative integer; baseline 2 | TRUE | Discrete scenario analysis | Alternative caps require model-owner approval
GERT.e6D.O | GERT | Arc | e6D | O | 7 | double | days |  |  | e6D | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e6D.ML | GERT | Arc | e6D | ML | 10 | double | days |  |  | e6D | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e6D.P | GERT | Arc | e6D | P | 12 | double | days |  |  | e6D | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.e6D.Probability | GERT | Arc | e6D | Probability | 0.01 | double | dimensionless | 0 | 1 | S6 | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
GERT.eD3.O | GERT | Arc | eD3 | O | 5 | double | days |  |  | eD3 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.eD3.ML | GERT | Arc | eD3 | ML | 7 | double | days |  |  | eD3 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.eD3.P | GERT | Arc | eD3 | P | 10 | double | days |  |  | eD3 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.eD3.Probability | GERT | Arc | eD3 | Probability | 0.9 | double | dimensionless | 0 | 1 | SD | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
GERT.eD7.O | GERT | Arc | eD7 | O | 5 | double | days |  |  | eD7 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.eD7.ML | GERT | Arc | eD7 | ML | 7 | double | days |  |  | eD7 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.eD7.P | GERT | Arc | eD7 | P | 10 | double | days |  |  | eD7 | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.eD7.Probability | GERT | Arc | eD7 | Probability | 0.05 | double | dimensionless | 0 | 1 | SD | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
GERT.eDT.O | GERT | Arc | eDT | O | 5 | double | days |  |  | eDT | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.eDT.ML | GERT | Arc | eDT | ML | 7 | double | days |  |  | eDT | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.eDT.P | GERT | Arc | eDT | P | 10 | double | days |  |  | eDT | 0 <= O <= ML <= P and O < P | TRUE | Scenario analysis; PRCC after parameter variation | Requires model-owner approval for sensitivity bounds
GERT.eDT.Probability | GERT | Arc | eDT | Probability | 0.05 | double | dimensionless | 0 | 1 | SD | Outgoing group must sum to 1 | TRUE | Constrained probability scenario analysis | Requires model-owner approval for perturbation range
SIM.Iterations | Both | Simulation | Run | Iterations | 50000 | integer | iterations | 1 |  | Simulation | Positive integer | FALSE | Precision planning | Fixed for this export
SIM.RootSeed | Both | Simulation | Run | Root Seed | 42 | integer | seed | 0 |  | Simulation | Non-negative integer | FALSE | Common random numbers | Fixed for this export

## Input Audit
Test | Status | Detail
Correct PERT file selected | PASS
Correct GERT file selected | PASS
Input hashes recorded | PASS
PERT rows = 6 | PASS
PERT route exact | PASS
PERT sums O/ML/P | PASS
PERT duration ordering | PASS
GERT nodes = 10 | PASS
No header parsed as a node | PASS
GERT probabilistic arcs = 29 | PASS
Structural arcs = 1 | PASS
e12 = S1 -> S2 | PASS
Every Arc Tag unique | PASS
Every Arc Tag agrees with From/To | PASS
No blank From or To | PASS
GERT duration ordering | PASS
Seven probability groups | PASS
Probability groups sum to 1 | PASS
Ten independently capped arcs | PASS
Every capped arc has cap 2 | PASS

## Software Versions
Component | Version
Python | 3.12.13
NumPy | 2.3.5
SciPy | Not installed; custom sparse iterative solver used
XlsxWriter | 3.2.9
openpyxl | 3.1.5
Program | raw-data-export-1.0.0

## Random Streams
Stream_Name | Entropy | Spawn_Key | Pool_Size | Generator
PERT_Duration | 42 | [0] | 4 | NumPy SeedSequence child stream
GERT_Routing | 42 | [1] | 4 | NumPy SeedSequence child stream
GERT_Duration | 42 | [2] | 4 | NumPy SeedSequence child stream

## Data Dictionary
Dataset | Workbook | Worksheet | Column_Name | Data_Type | Unit | Definition | Calculation | Source | Allowed_Values | Missing_Value_Rule | Sensitivity_Use | Notes
01_Input_and_Metadata::Run Metadata | 01_Input_and_Metadata.xlsx | Run Metadata | Field | string |  | Field | Directly exported value. | Fresh seeded simulation from authoritative Word inputs. |  | Blank only when the field is not applicable to the record. | Supporting identifier, audit, or reconciliation field.
01_Input_and_Metadata::Run Metadata | 01_Input_and_Metadata.xlsx | Run Metadata | Value | string |  | Value | Directly exported value. | Fresh seeded simulation from authoritative Word inputs. |  | Blank only when the field is not applicable to the record. | Supporting identifier, audit, or reconciliation field.
01_Input_and_Metadata::PERT Input | 01_Input_and_Metadata.xlsx | PERT Input | Sequence | int64 |  | Sequence | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Supporting identifier, audit, or reconciliation field.
01_Input_and_Metadata::PERT Input | 01_Input_and_Metadata.xlsx | PERT Input | Activity_ID | string | identifier | Activity ID | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Supporting identifier, audit, or reconciliation field.
01_Input_and_Metadata::PERT Input | 01_Input_and_Metadata.xlsx | PERT Input | Activity_Name | string |  | Activity Name | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Supporting identifier, audit, or reconciliation field.
01_Input_and_Metadata::PERT Input | 01_Input_and_Metadata.xlsx | PERT Input | Predecessor | string |  | Predecessor | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::PERT Input | 01_Input_and_Metadata.xlsx | PERT Input | Successor | string |  | Successor | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::PERT Input | 01_Input_and_Metadata.xlsx | PERT Input | O | double |  | O | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::PERT Input | 01_Input_and_Metadata.xlsx | PERT Input | ML | double |  | ML | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::PERT Input | 01_Input_and_Metadata.xlsx | PERT Input | P | double |  | P | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::PERT Input | 01_Input_and_Metadata.xlsx | PERT Input | Alpha | double |  | Alpha | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::PERT Input | 01_Input_and_Metadata.xlsx | PERT Input | Beta | double |  | Beta | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Supporting identifier, audit, or reconciliation field.
01_Input_and_Metadata::GERT Nodes | 01_Input_and_Metadata.xlsx | GERT Nodes | Node_ID | string | identifier | Node ID | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::GERT Nodes | 01_Input_and_Metadata.xlsx | GERT Nodes | Node_Name | string |  | Node Name | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::GERT Nodes | 01_Input_and_Metadata.xlsx | GERT Nodes | Input_Logic | string |  | Input Logic | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::GERT Nodes | 01_Input_and_Metadata.xlsx | GERT Nodes | Output_Logic | string |  | Output Logic | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::GERT Nodes | 01_Input_and_Metadata.xlsx | GERT Nodes | Role | string |  | Role | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::GERT Nodes | 01_Input_and_Metadata.xlsx | GERT Nodes | Word_Row | int64 |  | Word Row | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::GERT Arcs | 01_Input_and_Metadata.xlsx | GERT Arcs | Arc_Tag | string |  | Arc Tag | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Supporting identifier, audit, or reconciliation field.
01_Input_and_Metadata::GERT Arcs | 01_Input_and_Metadata.xlsx | GERT Arcs | From_Node | string |  | From Node | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::GERT Arcs | 01_Input_and_Metadata.xlsx | GERT Arcs | To_Node | string |  | To Node | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::GERT Arcs | 01_Input_and_Metadata.xlsx | GERT Arcs | Original_Probability | double | dimensionless | Original Probability | Derived from the complete unsampled exported simulation records. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::GERT Arcs | 01_Input_and_Metadata.xlsx | GERT Arcs | Loop_Cap | int64 |  | Loop Cap | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::GERT Arcs | 01_Input_and_Metadata.xlsx | GERT Arcs | O | double |  | O | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::GERT Arcs | 01_Input_and_Metadata.xlsx | GERT Arcs | ML | double |  | ML | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::GERT Arcs | 01_Input_and_Metadata.xlsx | GERT Arcs | P | double |  | P | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::GERT Arcs | 01_Input_and_Metadata.xlsx | GERT Arcs | Alpha | double |  | Alpha | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::GERT Arcs | 01_Input_and_Metadata.xlsx | GERT Arcs | Beta | double |  | Beta | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Supporting identifier, audit, or reconciliation field.
01_Input_and_Metadata::GERT Arcs | 01_Input_and_Metadata.xlsx | GERT Arcs | Structural | bool |  | Structural | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. | 0; 1 | Blank only when the field is not applicable to the record. | Supporting identifier, audit, or reconciliation field.
01_Input_and_Metadata::Probability Groups | 01_Input_and_Metadata.xlsx | Probability Groups | From_Node | string |  | From Node | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Probability Groups | 01_Input_and_Metadata.xlsx | Probability Groups | Arc_Count | string | count | Arc Count | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Probability Groups | 01_Input_and_Metadata.xlsx | Probability Groups | Original_Probability_Sum | double | dimensionless | Original Probability Sum | Derived from the complete unsampled exported simulation records. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Probability Groups | 01_Input_and_Metadata.xlsx | Probability Groups | Required_Sum | double |  | Required Sum | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Supporting identifier, audit, or reconciliation field.
01_Input_and_Metadata::Probability Groups | 01_Input_and_Metadata.xlsx | Probability Groups | Difference | double |  | Difference | Derived from the complete unsampled exported simulation records. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Supporting identifier, audit, or reconciliation field.
01_Input_and_Metadata::Probability Groups | 01_Input_and_Metadata.xlsx | Probability Groups | Valid | bool |  | Valid | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. | 0; 1 | Blank only when the field is not applicable to the record. | Supporting identifier, audit, or reconciliation field.
01_Input_and_Metadata::Probability Groups | 01_Input_and_Metadata.xlsx | Probability Groups | Arc_Tags | string |  | Arc Tags | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Supporting identifier, audit, or reconciliation field.
01_Input_and_Metadata::Loop Register | 01_Input_and_Metadata.xlsx | Loop Register | Loop_ID | string | identifier | Loop ID | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Loop Register | 01_Input_and_Metadata.xlsx | Loop Register | Arc_Tag | string |  | Arc Tag | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Supporting identifier, audit, or reconciliation field.
01_Input_and_Metadata::Loop Register | 01_Input_and_Metadata.xlsx | Loop Register | From_Node | string |  | From Node | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Loop Register | 01_Input_and_Metadata.xlsx | Loop Register | To_Node | string |  | To Node | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Loop Register | 01_Input_and_Metadata.xlsx | Loop Register | Loop_Cap | int64 |  | Loop Cap | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Loop Register | 01_Input_and_Metadata.xlsx | Loop Register | Rule | string |  | Rule | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Supporting identifier, audit, or reconciliation field.
01_Input_and_Metadata::Loop Register | 01_Input_and_Metadata.xlsx | Loop Register | Valid | bool |  | Valid | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. | 0; 1 | Blank only when the field is not applicable to the record. | Supporting identifier, audit, or reconciliation field.
01_Input_and_Metadata::Parameter Register | 01_Input_and_Metadata.xlsx | Parameter Register | Parameter_ID | string | identifier | Parameter ID | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Parameter Register | 01_Input_and_Metadata.xlsx | Parameter Register | Model | string |  | Model | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Parameter Register | 01_Input_and_Metadata.xlsx | Parameter Register | Entity_Type | string |  | Entity Type | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Parameter Register | 01_Input_and_Metadata.xlsx | Parameter Register | Entity_ID | string | identifier | Entity ID | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Supporting identifier, audit, or reconciliation field.
01_Input_and_Metadata::Parameter Register | 01_Input_and_Metadata.xlsx | Parameter Register | Parameter_Name | string |  | Parameter Name | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Parameter Register | 01_Input_and_Metadata.xlsx | Parameter Register | Baseline_Value | double |  | Baseline Value | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Supporting identifier, audit, or reconciliation field.
01_Input_and_Metadata::Parameter Register | 01_Input_and_Metadata.xlsx | Parameter Register | Data_Type | string |  | Data Type | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Parameter Register | 01_Input_and_Metadata.xlsx | Parameter Register | Unit | string |  | Unit | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Supporting identifier, audit, or reconciliation field.
01_Input_and_Metadata::Parameter Register | 01_Input_and_Metadata.xlsx | Parameter Register | Allowed_Minimum | double |  | Allowed Minimum | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Parameter Register | 01_Input_and_Metadata.xlsx | Parameter Register | Allowed_Maximum | double |  | Allowed Maximum | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Parameter Register | 01_Input_and_Metadata.xlsx | Parameter Register | Constraint_Group | string |  | Constraint Group | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Parameter Register | 01_Input_and_Metadata.xlsx | Parameter Register | Constraint_Rule | string |  | Constraint Rule | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Parameter Register | 01_Input_and_Metadata.xlsx | Parameter Register | Sensitivity_Eligible | bool |  | Sensitivity Eligible | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. | 0; 1 | Blank only when the field is not applicable to the record. | Supporting identifier, audit, or reconciliation field.
01_Input_and_Metadata::Parameter Register | 01_Input_and_Metadata.xlsx | Parameter Register | Sensitivity_Method | string |  | Sensitivity Method | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Parameter Register | 01_Input_and_Metadata.xlsx | Parameter Register | Notes | string |  | Notes | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Input Audit | 01_Input_and_Metadata.xlsx | Input Audit | Test | string |  | Test | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Supporting identifier, audit, or reconciliation field.
01_Input_and_Metadata::Input Audit | 01_Input_and_Metadata.xlsx | Input Audit | Status | string |  | Status | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Supporting identifier, audit, or reconciliation field.
01_Input_and_Metadata::Input Audit | 01_Input_and_Metadata.xlsx | Input Audit | Detail | string |  | Detail | Directly exported value. | Authoritative PERT Input.docx or GERT nput.docx. |  | Blank only when the field is not applicable to the record. | Supporting identifier, audit, or reconciliation field.
01_Input_and_Metadata::Software Versions | 01_Input_and_Metadata.xlsx | Software Versions | Component | string |  | Component | Directly exported value. | Fresh seeded simulation from authoritative Word inputs. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Software Versions | 01_Input_and_Metadata.xlsx | Software Versions | Version | string |  | Version | Directly exported value. | Fresh seeded simulation from authoritative Word inputs. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Random Streams | 01_Input_and_Metadata.xlsx | Random Streams | Stream_Name | string |  | Stream Name | Directly exported value. | Fresh seeded simulation from authoritative Word inputs. |  | Blank only when the field is not applicable to the record. | Supporting identifier, audit, or reconciliation field.
01_Input_and_Metadata::Random Streams | 01_Input_and_Metadata.xlsx | Random Streams | Entropy | int64 |  | Entropy | Directly exported value. | Fresh seeded simulation from authoritative Word inputs. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Random Streams | 01_Input_and_Metadata.xlsx | Random Streams | Spawn_Key | string |  | Spawn Key | Directly exported value. | Fresh seeded simulation from authoritative Word inputs. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Random Streams | 01_Input_and_Metadata.xlsx | Random Streams | Pool_Size | int64 |  | Pool Size | Directly exported value. | Fresh seeded simulation from authoritative Word inputs. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Random Streams | 01_Input_and_Metadata.xlsx | Random Streams | Generator | string |  | Generator | Directly exported value. | Fresh seeded simulation from authoritative Word inputs. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Data Dictionary | 01_Input_and_Metadata.xlsx | Data Dictionary | Dataset | string |  | Dataset | Directly exported value. | Fresh seeded simulation from authoritative Word inputs. |  | Blank only when the field is not applicable to the record. | Supporting identifier, audit, or reconciliation field.
01_Input_and_Metadata::Data Dictionary | 01_Input_and_Metadata.xlsx | Data Dictionary | Workbook | string |  | Workbook | Directly exported value. | Fresh seeded simulation from authoritative Word inputs. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Data Dictionary | 01_Input_and_Metadata.xlsx | Data Dictionary | Worksheet | string |  | Worksheet | Directly exported value. | Fresh seeded simulation from authoritative Word inputs. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Data Dictionary | 01_Input_and_Metadata.xlsx | Data Dictionary | Column_Name | string |  | Column Name | Directly exported value. | Fresh seeded simulation from authoritative Word inputs. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Data Dictionary | 01_Input_and_Metadata.xlsx | Data Dictionary | Data_Type | string |  | Data Type | Directly exported value. | Fresh seeded simulation from authoritative Word inputs. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Data Dictionary | 01_Input_and_Metadata.xlsx | Data Dictionary | Unit | string |  | Unit | Directly exported value. | Fresh seeded simulation from authoritative Word inputs. |  | Blank only when the field is not applicable to the record. | Supporting identifier, audit, or reconciliation field.
01_Input_and_Metadata::Data Dictionary | 01_Input_and_Metadata.xlsx | Data Dictionary | Definition | string |  | Definition | Directly exported value. | Fresh seeded simulation from authoritative Word inputs. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Data Dictionary | 01_Input_and_Metadata.xlsx | Data Dictionary | Calculation | string |  | Calculation | Directly exported value. | Fresh seeded simulation from authoritative Word inputs. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Data Dictionary | 01_Input_and_Metadata.xlsx | Data Dictionary | Source | string |  | Source | Directly exported value. | Fresh seeded simulation from authoritative Word inputs. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Data Dictionary | 01_Input_and_Metadata.xlsx | Data Dictionary | Allowed_Values | string |  | Allowed Values | Directly exported value. | Fresh seeded simulation from authoritative Word inputs. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.
01_Input_and_Metadata::Data Dictionary | 01_Input_and_Metadata.xlsx | Data Dictionary | Missing_Value_Rule | string |  | Missing Value Rule | Directly exported value. | Fresh seeded simulation from authoritative Word inputs. |  | Blank only when the field is not applicable to the record. | Supporting identifier, audit, or reconciliation field.
01_Input_and_Metadata::Data Dictionary | 01_Input_and_Metadata.xlsx | Data Dictionary | Sensitivity_Use | string |  | Sensitivity Use | Directly exported value. | Fresh seeded simulation from authoritative Word inputs. |  | Blank only when the field is not applicable to the record. | Supporting identifier, audit, or reconciliation field.
01_Input_and_Metadata::Data Dictionary | 01_Input_and_Metadata.xlsx | Data Dictionary | Notes | string |  | Notes | Directly exported value. | Fresh seeded simulation from authoritative Word inputs. |  | Blank only when the field is not applicable to the record. | Candidate predictor or response for later analysis.