## PERT Input Snapshot
id | name | o | ml | p | enabled | structural_zero
P01 | Submission review | 2 | 4 | 7 | TRUE | FALSE
P02 | Technical assessment | 3 | 5 | 9 | TRUE | FALSE
P03 | Commercial assessment | 2 | 6 | 12 | TRUE | FALSE
P04 | Approval and close | 1 | 3 | 5 | TRUE | FALSE

## PERT Summary
Metric | Value
Count | 1000
Mean | 20.75
Ceiling of Mean | 21
Standard deviation | 2.5671
Variance | 6.5901
Median | 21
Minimum | 14
Maximum | 28
Range | 14
IQR | 3
Coefficient of variation | 0.12372

## P1-P99
Percentile | Rank | Duration
1 | 10 | 15
2 | 20 | 16
3 | 30 | 16
4 | 40 | 16
5 | 50 | 16
6 | 60 | 17
7 | 70 | 17
8 | 80 | 17
9 | 90 | 17
10 | 100 | 17
11 | 110 | 18
12 | 120 | 18
13 | 130 | 18
14 | 140 | 18
15 | 150 | 18
16 | 160 | 18
17 | 170 | 18
18 | 180 | 18
19 | 190 | 19
20 | 200 | 19
21 | 210 | 19
22 | 220 | 19
23 | 230 | 19
24 | 240 | 19
25 | 250 | 19
26 | 260 | 19
27 | 270 | 19
28 | 280 | 19
29 | 290 | 19
30 | 300 | 19
31 | 310 | 19
32 | 320 | 20
33 | 330 | 20
34 | 340 | 20
35 | 350 | 20
36 | 360 | 20
37 | 370 | 20
38 | 380 | 20
39 | 390 | 20
40 | 400 | 20
41 | 410 | 20
42 | 420 | 20
43 | 430 | 20
44 | 440 | 20
45 | 450 | 20
46 | 460 | 20
47 | 470 | 20
48 | 480 | 21
49 | 490 | 21
50 | 500 | 21
51 | 510 | 21
52 | 520 | 21
53 | 530 | 21
54 | 540 | 21
55 | 550 | 21
56 | 560 | 21
57 | 570 | 21
58 | 580 | 21
59 | 590 | 21
60 | 600 | 21
61 | 610 | 21
62 | 620 | 22
63 | 630 | 22
64 | 640 | 22
65 | 650 | 22
66 | 660 | 22
67 | 670 | 22
68 | 680 | 22
69 | 690 | 22
70 | 700 | 22
71 | 710 | 22
72 | 720 | 22
73 | 730 | 22
74 | 740 | 22
75 | 750 | 22
76 | 760 | 23
77 | 770 | 23
78 | 780 | 23
79 | 790 | 23
80 | 800 | 23
81 | 810 | 23
82 | 820 | 23
83 | 830 | 23
84 | 840 | 23
85 | 850 | 23
86 | 860 | 24
87 | 870 | 24
88 | 880 | 24
89 | 890 | 24
90 | 900 | 24
91 | 910 | 24
92 | 920 | 24
93 | 930 | 25
94 | 940 | 25
95 | 950 | 25
96 | 960 | 25
97 | 970 | 26
98 | 980 | 26
99 | 990 | 27

## Activity Results
Activity ID | Activity Name | Count | Mean | Ceiling of Mean | Standard deviation | Variance | Median | Minimum | Maximum | Range | IQR | Coefficient of variation
P01 | Submission review | 1000 | 4.624 | 5 | 0.98264 | 0.96559 | 5 | 3 | 7 | 4 | 1 | 0.21251
P02 | Technical assessment | 1000 | 5.813 | 6 | 1.1762 | 1.3834 | 6 | 4 | 9 | 5 | 2 | 0.20234
P03 | Commercial assessment | 1000 | 6.83 | 7 | 1.85 | 3.4225 | 7 | 3 | 12 | 9 | 3 | 0.27086
P04 | Approval and close | 1000 | 3.483 | 4 | 0.80147 | 0.64235 | 3 | 2 | 5 | 3 | 1 | 0.23011

## Raw Iteration Totals
Iteration | Duration
1 | 15
2 | 22
3 | 20
4 | 23
5 | 25
6 | 24
7 | 28
8 | 24
9 | 22
10 | 21
11 | 23
12 | 18
13 | 19
14 | 21
15 | 18
16 | 22
17 | 20
18 | 22
19 | 22
20 | 23
21 | 23
22 | 20
23 | 23
24 | 20
25 | 18
26 | 23
27 | 18
28 | 22
29 | 21
30 | 22
31 | 21
32 | 20
33 | 20
34 | 20
35 | 19
36 | 22
37 | 18
38 | 20
39 | 22
40 | 18
41 | 19
42 | 22
43 | 18
44 | 24
45 | 18
46 | 24
47 | 19
48 | 19
49 | 22
50 | 23
51 | 19
52 | 20
53 | 24
54 | 17
55 | 21
56 | 17
57 | 24
58 | 23
59 | 19
60 | 24
61 | 24
62 | 25
63 | 23
64 | 20
65 | 19
66 | 19
67 | 25
68 | 20
69 | 21
70 | 18
71 | 20
72 | 25
73 | 21
74 | 20
75 | 24
76 | 19
77 | 19
78 | 22
79 | 20
80 | 17
81 | 21
82 | 25
83 | 18
84 | 23
85 | 21
86 | 21
87 | 23
88 | 19
89 | 18
90 | 23
91 | 20
92 | 22
93 | 24
94 | 18
95 | 21
96 | 23
97 | 21
98 | 22
99 | 20
100 | 22
101 | 22
102 | 19
103 | 22
104 | 22
105 | 22
106 | 23
107 | 18
108 | 23
109 | 20
110 | 20
111 | 24
112 | 19
113 | 21
114 | 23
115 | 22
116 | 20
117 | 23
118 | 19
119 | 18
120 | 17
121 | 24
122 | 22
123 | 20
124 | 22
125 | 20
126 | 22
127 | 16
128 | 21
129 | 22
130 | 20
131 | 24
132 | 21
133 | 25
134 | 23
135 | 20
136 | 23
137 | 19
138 | 18
139 | 21
140 | 20
141 | 21
142 | 21
143 | 23
144 | 22
145 | 16
146 | 22
147 | 17
148 | 20
149 | 22
150 | 22
151 | 25
152 | 27
153 | 20
154 | 19
155 | 20
156 | 19
157 | 22
158 | 21
159 | 22
160 | 18
161 | 23
162 | 19
163 | 25
164 | 23
165 | 19
166 | 19
167 | 19
168 | 19
169 | 24
170 | 21
171 | 22
172 | 21
173 | 26
174 | 21
175 | 20
176 | 21
177 | 19
178 | 20
179 | 18
180 | 19
181 | 22
182 | 20
183 | 19
184 | 21
185 | 22
186 | 20
187 | 21
188 | 23
189 | 21
190 | 21
191 | 21
192 | 19
193 | 20
194 | 23
195 | 17
196 | 22
197 | 18
198 | 17
199 | 18
200 | 21
201 | 18
202 | 20
203 | 20
204 | 21
205 | 22
206 | 24
207 | 25
208 | 19
209 | 21
210 | 15
211 | 20
212 | 21
213 | 20
214 | 14
215 | 19
216 | 24
217 | 23
218 | 20
219 | 21
220 | 20
221 | 19
222 | 22
223 | 22
224 | 23
225 | 20
226 | 21
227 | 23
228 | 19
229 | 20
230 | 21
231 | 20
232 | 21
233 | 16
234 | 19
235 | 21
236 | 21
237 | 17
238 | 19
239 | 20
240 | 19
241 | 23
242 | 28
243 | 22
244 | 19
245 | 23
246 | 27
247 | 18
248 | 22
249 | 21
250 | 25
251 | 15
252 | 23
253 | 20
254 | 18
255 | 20
256 | 19
257 | 20
258 | 22
259 | 22
260 | 18
261 | 21
262 | 15
263 | 19
264 | 24
265 | 25
266 | 20
267 | 25
268 | 20
269 | 21
270 | 18
271 | 23
272 | 16
273 | 18
274 | 22
275 | 17
276 | 17
277 | 21
278 | 24
279 | 23
280 | 16
281 | 23
282 | 20
283 | 22
284 | 23
285 | 19
286 | 25
287 | 19
288 | 24
289 | 25
290 | 23
291 | 24
292 | 20
293 | 24
294 | 17
295 | 25
296 | 27
297 | 22
298 | 21
299 | 22
300 | 21
301 | 22
302 | 21
303 | 15
304 | 23
305 | 20
306 | 23
307 | 18
308 | 20
309 | 24
310 | 20
311 | 15
312 | 20
313 | 19
314 | 19
315 | 23
316 | 21
317 | 24
318 | 26
319 | 22
320 | 22
321 | 22
322 | 16
323 | 18
324 | 22
325 | 17
326 | 20
327 | 20
328 | 20
329 | 19
330 | 17
331 | 22
332 | 23
333 | 18
334 | 21
335 | 20
336 | 21
337 | 23
338 | 16
339 | 20
340 | 20
341 | 19
342 | 17
343 | 24
344 | 18
345 | 17
346 | 22
347 | 22
348 | 18
349 | 20
350 | 23
351 | 19
352 | 20
353 | 20
354 | 24
355 | 17
356 | 23
357 | 18
358 | 26
359 | 18
360 | 22
361 | 22
362 | 28
363 | 19
364 | 23
365 | 16
366 | 23
367 | 19
368 | 22
369 | 22
370 | 22
371 | 23
372 | 21
373 | 21
374 | 21
375 | 17
376 | 24
377 | 20
378 | 22
379 | 15
380 | 20
381 | 17
382 | 23
383 | 20
384 | 21
385 | 21
386 | 20
387 | 23
388 | 21
389 | 18
390 | 15
391 | 21
392 | 24
393 | 22
394 | 22
395 | 22
396 | 24
397 | 19
398 | 26
399 | 19
400 | 19
401 | 20
402 | 21
403 | 20
404 | 23
405 | 23
406 | 22
407 | 19
408 | 24
409 | 24
410 | 22
411 | 23
412 | 22
413 | 20
414 | 25
415 | 18
416 | 22
417 | 19
418 | 22
419 | 18
420 | 19
421 | 20
422 | 24
423 | 22
424 | 19
425 | 21
426 | 21
427 | 20
428 | 23
429 | 22
430 | 20
431 | 27
432 | 22
433 | 19
434 | 21
435 | 22
436 | 20
437 | 18
438 | 19
439 | 24
440 | 22
441 | 22
442 | 21
443 | 20
444 | 19
445 | 16
446 | 19
447 | 21
448 | 22
449 | 22
450 | 22
451 | 20
452 | 23
453 | 21
454 | 16
455 | 24
456 | 25
457 | 23
458 | 19
459 | 18
460 | 15
461 | 20
462 | 21
463 | 28
464 | 19
465 | 27
466 | 25
467 | 22
468 | 14
469 | 24
470 | 24
471 | 25
472 | 27
473 | 20
474 | 20
475 | 20
476 | 19
477 | 21
478 | 18
479 | 21
480 | 16
481 | 19
482 | 17
483 | 24
484 | 18
485 | 23
486 | 23
487 | 23
488 | 21
489 | 24
490 | 19
491 | 18
492 | 24
493 | 19
494 | 26
495 | 19
496 | 20
497 | 21
498 | 21
499 | 21
500 | 21
501 | 24
502 | 17
503 | 25
504 | 19
505 | 21
506 | 22
507 | 20
508 | 23
509 | 22
510 | 24
511 | 15
512 | 23
513 | 20
514 | 20
515 | 22
516 | 22
517 | 16
518 | 19
519 | 22
520 | 21
521 | 22
522 | 19
523 | 25
524 | 19
525 | 21
526 | 22
527 | 24
528 | 21
529 | 25
530 | 18
531 | 18
532 | 18
533 | 17
534 | 16
535 | 21
536 | 19
537 | 24
538 | 22
539 | 18
540 | 23
541 | 22
542 | 18
543 | 17
544 | 22
545 | 20
546 | 21
547 | 18
548 | 18
549 | 20
550 | 18
551 | 24
552 | 23
553 | 18
554 | 18
555 | 25
556 | 24
557 | 21
558 | 20
559 | 18
560 | 24
561 | 26
562 | 21
563 | 19
564 | 22
565 | 20
566 | 22
567 | 19
568 | 19
569 | 20
570 | 22
571 | 26
572 | 18
573 | 23
574 | 22
575 | 25
576 | 20
577 | 16
578 | 19
579 | 22
580 | 24
581 | 22
582 | 20
583 | 22
584 | 19
585 | 24
586 | 23
587 | 19
588 | 20
589 | 16
590 | 18
591 | 14
592 | 20
593 | 22
594 | 27
595 | 19
596 | 20
597 | 21
598 | 22
599 | 20
600 | 25
601 | 21
602 | 17
603 | 21
604 | 20
605 | 23
606 | 19
607 | 23
608 | 24
609 | 20
610 | 21
611 | 22
612 | 17
613 | 21
614 | 17
615 | 23
616 | 21
617 | 19
618 | 24
619 | 18
620 | 22
621 | 18
622 | 21
623 | 26
624 | 20
625 | 19
626 | 23
627 | 21
628 | 21
629 | 24
630 | 19
631 | 23
632 | 21
633 | 20
634 | 22
635 | 21
636 | 23
637 | 23
638 | 20
639 | 18
640 | 22
641 | 20
642 | 21
643 | 14
644 | 20
645 | 21
646 | 19
647 | 20
648 | 20
649 | 19
650 | 26
651 | 20
652 | 20
653 | 21
654 | 19
655 | 26
656 | 22
657 | 18
658 | 18
659 | 18
660 | 22
661 | 24
662 | 23
663 | 16
664 | 20
665 | 18
666 | 20
667 | 20
668 | 21
669 | 21
670 | 21
671 | 25
672 | 20
673 | 20
674 | 22
675 | 16
676 | 22
677 | 22
678 | 16
679 | 18
680 | 22
681 | 19
682 | 25
683 | 25
684 | 23
685 | 23
686 | 19
687 | 20
688 | 16
689 | 20
690 | 18
691 | 24
692 | 23
693 | 24
694 | 19
695 | 25
696 | 21
697 | 19
698 | 20
699 | 18
700 | 21
701 | 21
702 | 26
703 | 22
704 | 15
705 | 18
706 | 20
707 | 23
708 | 17
709 | 19
710 | 23
711 | 16
712 | 21
713 | 22
714 | 21
715 | 17
716 | 20
717 | 16
718 | 22
719 | 20
720 | 17
721 | 20
722 | 22
723 | 20
724 | 17
725 | 20
726 | 21
727 | 23
728 | 19
729 | 19
730 | 23
731 | 16
732 | 26
733 | 16
734 | 22
735 | 23
736 | 17
737 | 22
738 | 18
739 | 21
740 | 21
741 | 21
742 | 21
743 | 19
744 | 21
745 | 23
746 | 16
747 | 24
748 | 18
749 | 18
750 | 17
751 | 18
752 | 19
753 | 21
754 | 19
755 | 23
756 | 15
757 | 15
758 | 17
759 | 24
760 | 16
761 | 18
762 | 23
763 | 21
764 | 19
765 | 22
766 | 22
767 | 21
768 | 24
769 | 18
770 | 19
771 | 18
772 | 20
773 | 18
774 | 19
775 | 26
776 | 21
777 | 22
778 | 23
779 | 20
780 | 19
781 | 19
782 | 22
783 | 17
784 | 25
785 | 22
786 | 22
787 | 20
788 | 15
789 | 17
790 | 23
791 | 22
792 | 20
793 | 20
794 | 19
795 | 16
796 | 19
797 | 20
798 | 21
799 | 14
800 | 19
801 | 23
802 | 21
803 | 20
804 | 20
805 | 17
806 | 24
807 | 25
808 | 19
809 | 19
810 | 22
811 | 22
812 | 19
813 | 25
814 | 21
815 | 21
816 | 22
817 | 23
818 | 20
819 | 23
820 | 20
821 | 20
822 | 18
823 | 25
824 | 23
825 | 18
826 | 24
827 | 18
828 | 20
829 | 17
830 | 20
831 | 19
832 | 21
833 | 24
834 | 24
835 | 19
836 | 22
837 | 21
838 | 17
839 | 21
840 | 22
841 | 21
842 | 21
843 | 22
844 | 19
845 | 17
846 | 20
847 | 22
848 | 19
849 | 18
850 | 16
851 | 23
852 | 23
853 | 19
854 | 19
855 | 17
856 | 26
857 | 21
858 | 21
859 | 22
860 | 17
861 | 22
862 | 16
863 | 21
864 | 23
865 | 22
866 | 25
867 | 21
868 | 16
869 | 18
870 | 19
871 | 21
872 | 17
873 | 20
874 | 26
875 | 20
876 | 26
877 | 19
878 | 21
879 | 21
880 | 21
881 | 20
882 | 18
883 | 22
884 | 22
885 | 25
886 | 17
887 | 20
888 | 16
889 | 20
890 | 23
891 | 22
892 | 18
893 | 23
894 | 19
895 | 21
896 | 18
897 | 23
898 | 20
899 | 17
900 | 22
901 | 22
902 | 23
903 | 21
904 | 20
905 | 19
906 | 27
907 | 23
908 | 18
909 | 21
910 | 21
911 | 24
912 | 17
913 | 21
914 | 17
915 | 19
916 | 20
917 | 24
918 | 17
919 | 20
920 | 17
921 | 20
922 | 21
923 | 20
924 | 21
925 | 19
926 | 23
927 | 21
928 | 21
929 | 22
930 | 23
931 | 22
932 | 19
933 | 20
934 | 20
935 | 25
936 | 23
937 | 16
938 | 25
939 | 26
940 | 26
941 | 18
942 | 20
943 | 18
944 | 23
945 | 22
946 | 23
947 | 21
948 | 19
949 | 17
950 | 18
951 | 25
952 | 17
953 | 20
954 | 25
955 | 19
956 | 19
957 | 24
958 | 19
959 | 21
960 | 25
961 | 23
962 | 26
963 | 21
964 | 24
965 | 17
966 | 27
967 | 19
968 | 21
969 | 17
970 | 20
971 | 20
972 | 19
973 | 23
974 | 20
975 | 22
976 | 23
977 | 23
978 | 20
979 | 19
980 | 19
981 | 26
982 | 21
983 | 20
984 | 21
985 | 24
986 | 22
987 | 22
988 | 20
989 | 18
990 | 25
991 | 18
992 | 25
993 | 21
994 | 17
995 | 23
996 | 19
997 | 19
998 | 23
999 | 19
1000 | 24

## Raw Activity Durations
Iteration | Activity ID | Activity Name | Duration
1 | P01 | Submission review | 4
1 | P02 | Technical assessment | 6
1 | P03 | Commercial assessment | 3
1 | P04 | Approval and close | 2
2 | P01 | Submission review | 5
2 | P02 | Technical assessment | 6
2 | P03 | Commercial assessment | 8
2 | P04 | Approval and close | 3
3 | P01 | Submission review | 5
3 | P02 | Technical assessment | 4
3 | P03 | Commercial assessment | 7
3 | P04 | Approval and close | 4
4 | P01 | Submission review | 4
4 | P02 | Technical assessment | 8
4 | P03 | Commercial assessment | 7
4 | P04 | Approval and close | 4
5 | P01 | Submission review | 5
5 | P02 | Technical assessment | 7
5 | P03 | Commercial assessment | 11
5 | P04 | Approval and close | 2
6 | P01 | Submission review | 5
6 | P02 | Technical assessment | 6
6 | P03 | Commercial assessment | 10
6 | P04 | Approval and close | 3
7 | P01 | Submission review | 7
7 | P02 | Technical assessment | 8
7 | P03 | Commercial assessment | 11
7 | P04 | Approval and close | 2
8 | P01 | Submission review | 4
8 | P02 | Technical assessment | 7
8 | P03 | Commercial assessment | 9
8 | P04 | Approval and close | 4
9 | P01 | Submission review | 4
9 | P02 | Technical assessment | 6
9 | P03 | Commercial assessment | 9
9 | P04 | Approval and close | 3
10 | P01 | Submission review | 5
10 | P02 | Technical assessment | 6
10 | P03 | Commercial assessment | 6
10 | P04 | Approval and close | 4
11 | P01 | Submission review | 5
11 | P02 | Technical assessment | 4
11 | P03 | Commercial assessment | 9
11 | P04 | Approval and close | 5
12 | P01 | Submission review | 6
12 | P02 | Technical assessment | 4
12 | P03 | Commercial assessment | 5
12 | P04 | Approval and close | 3
13 | P01 | Submission review | 4
13 | P02 | Technical assessment | 7
13 | P03 | Commercial assessment | 6
13 | P04 | Approval and close | 2
14 | P01 | Submission review | 4
14 | P02 | Technical assessment | 5
14 | P03 | Commercial assessment | 9
14 | P04 | Approval and close | 3
15 | P01 | Submission review | 5
15 | P02 | Technical assessment | 6
15 | P03 | Commercial assessment | 3
15 | P04 | Approval and close | 4
16 | P01 | Submission review | 3
16 | P02 | Technical assessment | 5
16 | P03 | Commercial assessment | 10
16 | P04 | Approval and close | 4
17 | P01 | Submission review | 3
17 | P02 | Technical assessment | 9
17 | P03 | Commercial assessment | 5
17 | P04 | Approval and close | 3
18 | P01 | Submission review | 4
18 | P02 | Technical assessment | 4
18 | P03 | Commercial assessment | 10
18 | P04 | Approval and close | 4
19 | P01 | Submission review | 5
19 | P02 | Technical assessment | 4
19 | P03 | Commercial assessment | 9
19 | P04 | Approval and close | 4
20 | P01 | Submission review | 6
20 | P02 | Technical assessment | 7
20 | P03 | Commercial assessment | 6
20 | P04 | Approval and close | 4
21 | P01 | Submission review | 6
21 | P02 | Technical assessment | 5
21 | P03 | Commercial assessment | 9
21 | P04 | Approval and close | 3
22 | P01 | Submission review | 4
22 | P02 | Technical assessment | 8
22 | P03 | Commercial assessment | 5
22 | P04 | Approval and close | 3
23 | P01 | Submission review | 5
23 | P02 | Technical assessment | 6
23 | P03 | Commercial assessment | 9
23 | P04 | Approval and close | 3
24 | P01 | Submission review | 6
24 | P02 | Technical assessment | 5
24 | P03 | Commercial assessment | 6
24 | P04 | Approval and close | 3
25 | P01 | Submission review | 4
25 | P02 | Technical assessment | 5
25 | P03 | Commercial assessment | 6
25 | P04 | Approval and close | 3
26 | P01 | Submission review | 4
26 | P02 | Technical assessment | 5
26 | P03 | Commercial assessment | 10
26 | P04 | Approval and close | 4
27 | P01 | Submission review | 3
27 | P02 | Technical assessment | 7
27 | P03 | Commercial assessment | 3
27 | P04 | Approval and close | 5
28 | P01 | Submission review | 4
28 | P02 | Technical assessment | 4
28 | P03 | Commercial assessment | 9
28 | P04 | Approval and close | 5
29 | P01 | Submission review | 7
29 | P02 | Technical assessment | 7
29 | P03 | Commercial assessment | 5
29 | P04 | Approval and close | 2
30 | P01 | Submission review | 5
30 | P02 | Technical assessment | 5
30 | P03 | Commercial assessment | 8
30 | P04 | Approval and close | 4
31 | P01 | Submission review | 4
31 | P02 | Technical assessment | 9
31 | P03 | Commercial assessment | 4
31 | P04 | Approval and close | 4
32 | P01 | Submission review | 3
32 | P02 | Technical assessment | 6
32 | P03 | Commercial assessment | 7
32 | P04 | Approval and close | 4
33 | P01 | Submission review | 6
33 | P02 | Technical assessment | 6
33 | P03 | Commercial assessment | 5
33 | P04 | Approval and close | 3
34 | P01 | Submission review | 6
34 | P02 | Technical assessment | 4
34 | P03 | Commercial assessment | 7
34 | P04 | Approval and close | 3
35 | P01 | Submission review | 5
35 | P02 | Technical assessment | 6
35 | P03 | Commercial assessment | 5
35 | P04 | Approval and close | 3
36 | P01 | Submission review | 4
36 | P02 | Technical assessment | 6
36 | P03 | Commercial assessment | 8
36 | P04 | Approval and close | 4
37 | P01 | Submission review | 6
37 | P02 | Technical assessment | 6
37 | P03 | Commercial assessment | 4
37 | P04 | Approval and close | 2
38 | P01 | Submission review | 6
38 | P02 | Technical assessment | 4
38 | P03 | Commercial assessment | 7
38 | P04 | Approval and close | 3
39 | P01 | Submission review | 5
39 | P02 | Technical assessment | 7
39 | P03 | Commercial assessment | 6
39 | P04 | Approval and close | 4
40 | P01 | Submission review | 5
40 | P02 | Technical assessment | 6
40 | P03 | Commercial assessment | 4
40 | P04 | Approval and close | 3
41 | P01 | Submission review | 4
41 | P02 | Technical assessment | 7
41 | P03 | Commercial assessment | 5
41 | P04 | Approval and close | 3
42 | P01 | Submission review | 5
42 | P02 | Technical assessment | 6
42 | P03 | Commercial assessment | 7
42 | P04 | Approval and close | 4
43 | P01 | Submission review | 4
43 | P02 | Technical assessment | 7
43 | P03 | Commercial assessment | 4
43 | P04 | Approval and close | 3
44 | P01 | Submission review | 5
44 | P02 | Technical assessment | 5
44 | P03 | Commercial assessment | 9
44 | P04 | Approval and close | 5
45 | P01 | Submission review | 6
45 | P02 | Technical assessment | 4
45 | P03 | Commercial assessment | 5
45 | P04 | Approval and close | 3
46 | P01 | Submission review | 3
46 | P02 | Technical assessment | 6
46 | P03 | Commercial assessment | 10
46 | P04 | Approval and close | 5
47 | P01 | Submission review | 4
47 | P02 | Technical assessment | 6
47 | P03 | Commercial assessment | 6
47 | P04 | Approval and close | 3
48 | P01 | Submission review | 3
48 | P02 | Technical assessment | 5
48 | P03 | Commercial assessment | 7
48 | P04 | Approval and close | 4
49 | P01 | Submission review | 5
49 | P02 | Technical assessment | 6
49 | P03 | Commercial assessment | 7
49 | P04 | Approval and close | 4
50 | P01 | Submission review | 4
50 | P02 | Technical assessment | 8
50 | P03 | Commercial assessment | 6
50 | P04 | Approval and close | 5
51 | P01 | Submission review | 3
51 | P02 | Technical assessment | 4
51 | P03 | Commercial assessment | 8
51 | P04 | Approval and close | 4
52 | P01 | Submission review | 3
52 | P02 | Technical assessment | 7
52 | P03 | Commercial assessment | 7
52 | P04 | Approval and close | 3
53 | P01 | Submission review | 5
53 | P02 | Technical assessment | 6
53 | P03 | Commercial assessment | 10
53 | P04 | Approval and close | 3
54 | P01 | Submission review | 6
54 | P02 | Technical assessment | 5
54 | P03 | Commercial assessment | 4
54 | P04 | Approval and close | 2
55 | P01 | Submission review | 5
55 | P02 | Technical assessment | 4
55 | P03 | Commercial assessment | 7
55 | P04 | Approval and close | 5
56 | P01 | Submission review | 3
56 | P02 | Technical assessment | 5
56 | P03 | Commercial assessment | 6
56 | P04 | Approval and close | 3
57 | P01 | Submission review | 5
57 | P02 | Technical assessment | 6
57 | P03 | Commercial assessment | 9
57 | P04 | Approval and close | 4
58 | P01 | Submission review | 5
58 | P02 | Technical assessment | 6
58 | P03 | Commercial assessment | 7
58 | P04 | Approval and close | 5
59 | P01 | Submission review | 4
59 | P02 | Technical assessment | 6
59 | P03 | Commercial assessment | 5
59 | P04 | Approval and close | 4
60 | P01 | Submission review | 4
60 | P02 | Technical assessment | 6
60 | P03 | Commercial assessment | 10
60 | P04 | Approval and close | 4
61 | P01 | Submission review | 5
61 | P02 | Technical assessment | 6
61 | P03 | Commercial assessment | 8
61 | P04 | Approval and close | 5
62 | P01 | Submission review | 4
62 | P02 | Technical assessment | 8
62 | P03 | Commercial assessment | 9
62 | P04 | Approval and close | 4
63 | P01 | Submission review | 5
63 | P02 | Technical assessment | 6
63 | P03 | Commercial assessment | 7
63 | P04 | Approval and close | 5
64 | P01 | Submission review | 5
64 | P02 | Technical assessment | 6
64 | P03 | Commercial assessment | 6
64 | P04 | Approval and close | 3
65 | P01 | Submission review | 4
65 | P02 | Technical assessment | 5
65 | P03 | Commercial assessment | 6
65 | P04 | Approval and close | 4
66 | P01 | Submission review | 4
66 | P02 | Technical assessment | 6
66 | P03 | Commercial assessment | 5
66 | P04 | Approval and close | 4
67 | P01 | Submission review | 5
67 | P02 | Technical assessment | 6
67 | P03 | Commercial assessment | 11
67 | P04 | Approval and close | 3
68 | P01 | Submission review | 6
68 | P02 | Technical assessment | 5
68 | P03 | Commercial assessment | 5
68 | P04 | Approval and close | 4
69 | P01 | Submission review | 5
69 | P02 | Technical assessment | 5
69 | P03 | Commercial assessment | 6
69 | P04 | Approval and close | 5
70 | P01 | Submission review | 4
70 | P02 | Technical assessment | 5
70 | P03 | Commercial assessment | 6
70 | P04 | Approval and close | 3
71 | P01 | Submission review | 6
71 | P02 | Technical assessment | 6
71 | P03 | Commercial assessment | 4
71 | P04 | Approval and close | 4
72 | P01 | Submission review | 6
72 | P02 | Technical assessment | 5
72 | P03 | Commercial assessment | 9
72 | P04 | Approval and close | 5
73 | P01 | Submission review | 6
73 | P02 | Technical assessment | 7
73 | P03 | Commercial assessment | 5
73 | P04 | Approval and close | 3
74 | P01 | Submission review | 3
74 | P02 | Technical assessment | 6
74 | P03 | Commercial assessment | 8
74 | P04 | Approval and close | 3
75 | P01 | Submission review | 5
75 | P02 | Technical assessment | 7
75 | P03 | Commercial assessment | 9
75 | P04 | Approval and close | 3
76 | P01 | Submission review | 3
76 | P02 | Technical assessment | 5
76 | P03 | Commercial assessment | 7
76 | P04 | Approval and close | 4
77 | P01 | Submission review | 3
77 | P02 | Technical assessment | 6
77 | P03 | Commercial assessment | 7
77 | P04 | Approval and close | 3
78 | P01 | Submission review | 5
78 | P02 | Technical assessment | 5
78 | P03 | Commercial assessment | 9
78 | P04 | Approval and close | 3
79 | P01 | Submission review | 4
79 | P02 | Technical assessment | 5
79 | P03 | Commercial assessment | 7
79 | P04 | Approval and close | 4
80 | P01 | Submission review | 4
80 | P02 | Technical assessment | 5
80 | P03 | Commercial assessment | 5
80 | P04 | Approval and close | 3
81 | P01 | Submission review | 6
81 | P02 | Technical assessment | 7
81 | P03 | Commercial assessment | 6
81 | P04 | Approval and close | 2
82 | P01 | Submission review | 5
82 | P02 | Technical assessment | 8
82 | P03 | Commercial assessment | 9
82 | P04 | Approval and close | 3
83 | P01 | Submission review | 3
83 | P02 | Technical assessment | 5
83 | P03 | Commercial assessment | 6
83 | P04 | Approval and close | 4
84 | P01 | Submission review | 5
84 | P02 | Technical assessment | 7
84 | P03 | Commercial assessment | 8
84 | P04 | Approval and close | 3
85 | P01 | Submission review | 5
85 | P02 | Technical assessment | 5
85 | P03 | Commercial assessment | 7
85 | P04 | Approval and close | 4
86 | P01 | Submission review | 5
86 | P02 | Technical assessment | 5
86 | P03 | Commercial assessment | 8
86 | P04 | Approval and close | 3
87 | P01 | Submission review | 4
87 | P02 | Technical assessment | 6
87 | P03 | Commercial assessment | 9
87 | P04 | Approval and close | 4
88 | P01 | Submission review | 5
88 | P02 | Technical assessment | 6
88 | P03 | Commercial assessment | 5
88 | P04 | Approval and close | 3
89 | P01 | Submission review | 5
89 | P02 | Technical assessment | 4
89 | P03 | Commercial assessment | 6
89 | P04 | Approval and close | 3
90 | P01 | Submission review | 6
90 | P02 | Technical assessment | 7
90 | P03 | Commercial assessment | 7
90 | P04 | Approval and close | 3
91 | P01 | Submission review | 3
91 | P02 | Technical assessment | 5
91 | P03 | Commercial assessment | 9
91 | P04 | Approval and close | 3
92 | P01 | Submission review | 5
92 | P02 | Technical assessment | 6
92 | P03 | Commercial assessment | 7
92 | P04 | Approval and close | 4
93 | P01 | Submission review | 6
93 | P02 | Technical assessment | 7
93 | P03 | Commercial assessment | 7
93 | P04 | Approval and close | 4
94 | P01 | Submission review | 4
94 | P02 | Technical assessment | 4
94 | P03 | Commercial assessment | 7
94 | P04 | Approval and close | 3
95 | P01 | Submission review | 4
95 | P02 | Technical assessment | 8
95 | P03 | Commercial assessment | 7
95 | P04 | Approval and close | 2
96 | P01 | Submission review | 4
96 | P02 | Technical assessment | 7
96 | P03 | Commercial assessment | 8
96 | P04 | Approval and close | 4
97 | P01 | Submission review | 5
97 | P02 | Technical assessment | 5
97 | P03 | Commercial assessment | 7
97 | P04 | Approval and close | 4
98 | P01 | Submission review | 3
98 | P02 | Technical assessment | 5
98 | P03 | Commercial assessment | 10
98 | P04 | Approval and close | 4
99 | P01 | Submission review | 5
99 | P02 | Technical assessment | 5
99 | P03 | Commercial assessment | 6
99 | P04 | Approval and close | 4
100 | P01 | Submission review | 6
100 | P02 | Technical assessment | 7
100 | P03 | Commercial assessment | 4
100 | P04 | Approval and close | 5
101 | P01 | Submission review | 6
101 | P02 | Technical assessment | 8
101 | P03 | Commercial assessment | 4
101 | P04 | Approval and close | 4
102 | P01 | Submission review | 6
102 | P02 | Technical assessment | 6
102 | P03 | Commercial assessment | 5
102 | P04 | Approval and close | 2
103 | P01 | Submission review | 5
103 | P02 | Technical assessment | 5
103 | P03 | Commercial assessment | 7
103 | P04 | Approval and close | 5
104 | P01 | Submission review | 5
104 | P02 | Technical assessment | 5
104 | P03 | Commercial assessment | 8
104 | P04 | Approval and close | 4
105 | P01 | Submission review | 5
105 | P02 | Technical assessment | 7
105 | P03 | Commercial assessment | 6
105 | P04 | Approval and close | 4
106 | P01 | Submission review | 5
106 | P02 | Technical assessment | 7
106 | P03 | Commercial assessment | 8
106 | P04 | Approval and close | 3
107 | P01 | Submission review | 4
107 | P02 | Technical assessment | 5
107 | P03 | Commercial assessment | 7
107 | P04 | Approval and close | 2
108 | P01 | Submission review | 4
108 | P02 | Technical assessment | 6
108 | P03 | Commercial assessment | 9
108 | P04 | Approval and close | 4
109 | P01 | Submission review | 4
109 | P02 | Technical assessment | 7
109 | P03 | Commercial assessment | 6
109 | P04 | Approval and close | 3
110 | P01 | Submission review | 6
110 | P02 | Technical assessment | 5
110 | P03 | Commercial assessment | 5
110 | P04 | Approval and close | 4
111 | P01 | Submission review | 6
111 | P02 | Technical assessment | 5
111 | P03 | Commercial assessment | 11
111 | P04 | Approval and close | 2
112 | P01 | Submission review | 3
112 | P02 | Technical assessment | 5
112 | P03 | Commercial assessment | 7
112 | P04 | Approval and close | 4
113 | P01 | Submission review | 5
113 | P02 | Technical assessment | 5
113 | P03 | Commercial assessment | 7
113 | P04 | Approval and close | 4
114 | P01 | Submission review | 5
114 | P02 | Technical assessment | 5
114 | P03 | Commercial assessment | 10
114 | P04 | Approval and close | 3
115 | P01 | Submission review | 5
115 | P02 | Technical assessment | 7
115 | P03 | Commercial assessment | 7
115 | P04 | Approval and close | 3
116 | P01 | Submission review | 3
116 | P02 | Technical assessment | 4
116 | P03 | Commercial assessment | 9
116 | P04 | Approval and close | 4
117 | P01 | Submission review | 6
117 | P02 | Technical assessment | 5
117 | P03 | Commercial assessment | 8
117 | P04 | Approval and close | 4
118 | P01 | Submission review | 5
118 | P02 | Technical assessment | 4
118 | P03 | Commercial assessment | 5
118 | P04 | Approval and close | 5
119 | P01 | Submission review | 5
119 | P02 | Technical assessment | 7
119 | P03 | Commercial assessment | 3
119 | P04 | Approval and close | 3
120 | P01 | Submission review | 3
120 | P02 | Technical assessment | 4
120 | P03 | Commercial assessment | 7
120 | P04 | Approval and close | 3
121 | P01 | Submission review | 4
121 | P02 | Technical assessment | 7
121 | P03 | Commercial assessment | 8
121 | P04 | Approval and close | 5
122 | P01 | Submission review | 5
122 | P02 | Technical assessment | 6
122 | P03 | Commercial assessment | 7
122 | P04 | Approval and close | 4
123 | P01 | Submission review | 6
123 | P02 | Technical assessment | 5
123 | P03 | Commercial assessment | 7
123 | P04 | Approval and close | 2
124 | P01 | Submission review | 6
124 | P02 | Technical assessment | 7
124 | P03 | Commercial assessment | 5
124 | P04 | Approval and close | 4
125 | P01 | Submission review | 5
125 | P02 | Technical assessment | 5
125 | P03 | Commercial assessment | 6
125 | P04 | Approval and close | 4
126 | P01 | Submission review | 5
126 | P02 | Technical assessment | 7
126 | P03 | Commercial assessment | 6
126 | P04 | Approval and close | 4
127 | P01 | Submission review | 4
127 | P02 | Technical assessment | 6
127 | P03 | Commercial assessment | 3
127 | P04 | Approval and close | 3
128 | P01 | Submission review | 5
128 | P02 | Technical assessment | 6
128 | P03 | Commercial assessment | 8
128 | P04 | Approval and close | 2
129 | P01 | Submission review | 4
129 | P02 | Technical assessment | 5
129 | P03 | Commercial assessment | 10
129 | P04 | Approval and close | 3
130 | P01 | Submission review | 4
130 | P02 | Technical assessment | 5
130 | P03 | Commercial assessment | 7
130 | P04 | Approval and close | 4
131 | P01 | Submission review | 6
131 | P02 | Technical assessment | 7
131 | P03 | Commercial assessment | 6
131 | P04 | Approval and close | 5
132 | P01 | Submission review | 5
132 | P02 | Technical assessment | 5
132 | P03 | Commercial assessment | 8
132 | P04 | Approval and close | 3
133 | P01 | Submission review | 6
133 | P02 | Technical assessment | 8
133 | P03 | Commercial assessment | 7
133 | P04 | Approval and close | 4
134 | P01 | Submission review | 4
134 | P02 | Technical assessment | 5
134 | P03 | Commercial assessment | 10
134 | P04 | Approval and close | 4
135 | P01 | Submission review | 3
135 | P02 | Technical assessment | 6
135 | P03 | Commercial assessment | 6
135 | P04 | Approval and close | 5
136 | P01 | Submission review | 6
136 | P02 | Technical assessment | 7
136 | P03 | Commercial assessment | 7
136 | P04 | Approval and close | 3
137 | P01 | Submission review | 5
137 | P02 | Technical assessment | 5
137 | P03 | Commercial assessment | 6
137 | P04 | Approval and close | 3
138 | P01 | Submission review | 4
138 | P02 | Technical assessment | 4
138 | P03 | Commercial assessment | 8
138 | P04 | Approval and close | 2
139 | P01 | Submission review | 5
139 | P02 | Technical assessment | 6
139 | P03 | Commercial assessment | 7
139 | P04 | Approval and close | 3
140 | P01 | Submission review | 4
140 | P02 | Technical assessment | 7
140 | P03 | Commercial assessment | 6
140 | P04 | Approval and close | 3
141 | P01 | Submission review | 3
141 | P02 | Technical assessment | 6
141 | P03 | Commercial assessment | 8
141 | P04 | Approval and close | 4
142 | P01 | Submission review | 5
142 | P02 | Technical assessment | 6
142 | P03 | Commercial assessment | 7
142 | P04 | Approval and close | 3
143 | P01 | Submission review | 6
143 | P02 | Technical assessment | 7
143 | P03 | Commercial assessment | 6
143 | P04 | Approval and close | 4
144 | P01 | Submission review | 7
144 | P02 | Technical assessment | 4
144 | P03 | Commercial assessment | 7
144 | P04 | Approval and close | 4
145 | P01 | Submission review | 3
145 | P02 | Technical assessment | 4
145 | P03 | Commercial assessment | 5
145 | P04 | Approval and close | 4
146 | P01 | Submission review | 4
146 | P02 | Technical assessment | 5
146 | P03 | Commercial assessment | 8
146 | P04 | Approval and close | 5
147 | P01 | Submission review | 4
147 | P02 | Technical assessment | 5
147 | P03 | Commercial assessment | 5
147 | P04 | Approval and close | 3
148 | P01 | Submission review | 6
148 | P02 | Technical assessment | 4
148 | P03 | Commercial assessment | 5
148 | P04 | Approval and close | 5
149 | P01 | Submission review | 4
149 | P02 | Technical assessment | 7
149 | P03 | Commercial assessment | 8
149 | P04 | Approval and close | 3
150 | P01 | Submission review | 6
150 | P02 | Technical assessment | 6
150 | P03 | Commercial assessment | 6
150 | P04 | Approval and close | 4
151 | P01 | Submission review | 7
151 | P02 | Technical assessment | 4
151 | P03 | Commercial assessment | 10
151 | P04 | Approval and close | 4
152 | P01 | Submission review | 6
152 | P02 | Technical assessment | 7
152 | P03 | Commercial assessment | 11
152 | P04 | Approval and close | 3
153 | P01 | Submission review | 3
153 | P02 | Technical assessment | 8
153 | P03 | Commercial assessment | 6
153 | P04 | Approval and close | 3
154 | P01 | Submission review | 5
154 | P02 | Technical assessment | 4
154 | P03 | Commercial assessment | 6
154 | P04 | Approval and close | 4
155 | P01 | Submission review | 5
155 | P02 | Technical assessment | 4
155 | P03 | Commercial assessment | 8
155 | P04 | Approval and close | 3
156 | P01 | Submission review | 5
156 | P02 | Technical assessment | 7
156 | P03 | Commercial assessment | 5
156 | P04 | Approval and close | 2
157 | P01 | Submission review | 5
157 | P02 | Technical assessment | 5
157 | P03 | Commercial assessment | 9
157 | P04 | Approval and close | 3
158 | P01 | Submission review | 4
158 | P02 | Technical assessment | 7
158 | P03 | Commercial assessment | 7
158 | P04 | Approval and close | 3
159 | P01 | Submission review | 4
159 | P02 | Technical assessment | 6
159 | P03 | Commercial assessment | 8
159 | P04 | Approval and close | 4
160 | P01 | Submission review | 4
160 | P02 | Technical assessment | 6
160 | P03 | Commercial assessment | 5
160 | P04 | Approval and close | 3
161 | P01 | Submission review | 4
161 | P02 | Technical assessment | 6
161 | P03 | Commercial assessment | 9
161 | P04 | Approval and close | 4
162 | P01 | Submission review | 4
162 | P02 | Technical assessment | 6
162 | P03 | Commercial assessment | 5
162 | P04 | Approval and close | 4
163 | P01 | Submission review | 5
163 | P02 | Technical assessment | 7
163 | P03 | Commercial assessment | 10
163 | P04 | Approval and close | 3
164 | P01 | Submission review | 4
164 | P02 | Technical assessment | 6
164 | P03 | Commercial assessment | 8
164 | P04 | Approval and close | 5
165 | P01 | Submission review | 4
165 | P02 | Technical assessment | 4
165 | P03 | Commercial assessment | 7
165 | P04 | Approval and close | 4
166 | P01 | Submission review | 4
166 | P02 | Technical assessment | 4
166 | P03 | Commercial assessment | 7
166 | P04 | Approval and close | 4
167 | P01 | Submission review | 3
167 | P02 | Technical assessment | 5
167 | P03 | Commercial assessment | 7
167 | P04 | Approval and close | 4
168 | P01 | Submission review | 4
168 | P02 | Technical assessment | 7
168 | P03 | Commercial assessment | 4
168 | P04 | Approval and close | 4
169 | P01 | Submission review | 5
169 | P02 | Technical assessment | 6
169 | P03 | Commercial assessment | 10
169 | P04 | Approval and close | 3
170 | P01 | Submission review | 4
170 | P02 | Technical assessment | 5
170 | P03 | Commercial assessment | 7
170 | P04 | Approval and close | 5
171 | P01 | Submission review | 5
171 | P02 | Technical assessment | 6
171 | P03 | Commercial assessment | 6
171 | P04 | Approval and close | 5
172 | P01 | Submission review | 5
172 | P02 | Technical assessment | 5
172 | P03 | Commercial assessment | 7
172 | P04 | Approval and close | 4
173 | P01 | Submission review | 5
173 | P02 | Technical assessment | 7
173 | P03 | Commercial assessment | 10
173 | P04 | Approval and close | 4
174 | P01 | Submission review | 4
174 | P02 | Technical assessment | 8
174 | P03 | Commercial assessment | 6
174 | P04 | Approval and close | 3
175 | P01 | Submission review | 6
175 | P02 | Technical assessment | 4
175 | P03 | Commercial assessment | 5
175 | P04 | Approval and close | 5
176 | P01 | Submission review | 5
176 | P02 | Technical assessment | 7
176 | P03 | Commercial assessment | 6
176 | P04 | Approval and close | 3
177 | P01 | Submission review | 4
177 | P02 | Technical assessment | 5
177 | P03 | Commercial assessment | 7
177 | P04 | Approval and close | 3
178 | P01 | Submission review | 3
178 | P02 | Technical assessment | 8
178 | P03 | Commercial assessment | 6
178 | P04 | Approval and close | 3
179 | P01 | Submission review | 5
179 | P02 | Technical assessment | 4
179 | P03 | Commercial assessment | 6
179 | P04 | Approval and close | 3
180 | P01 | Submission review | 4
180 | P02 | Technical assessment | 5
180 | P03 | Commercial assessment | 6
180 | P04 | Approval and close | 4
181 | P01 | Submission review | 4
181 | P02 | Technical assessment | 7
181 | P03 | Commercial assessment | 8
181 | P04 | Approval and close | 3
182 | P01 | Submission review | 4
182 | P02 | Technical assessment | 5
182 | P03 | Commercial assessment | 8
182 | P04 | Approval and close | 3
183 | P01 | Submission review | 5
183 | P02 | Technical assessment | 7
183 | P03 | Commercial assessment | 4
183 | P04 | Approval and close | 3
184 | P01 | Submission review | 5
184 | P02 | Technical assessment | 6
184 | P03 | Commercial assessment | 7
184 | P04 | Approval and close | 3
185 | P01 | Submission review | 4
185 | P02 | Technical assessment | 6
185 | P03 | Commercial assessment | 8
185 | P04 | Approval and close | 4
186 | P01 | Submission review | 6
186 | P02 | Technical assessment | 5
186 | P03 | Commercial assessment | 6
186 | P04 | Approval and close | 3
187 | P01 | Submission review | 4
187 | P02 | Technical assessment | 6
187 | P03 | Commercial assessment | 7
187 | P04 | Approval and close | 4
188 | P01 | Submission review | 5
188 | P02 | Technical assessment | 8
188 | P03 | Commercial assessment | 6
188 | P04 | Approval and close | 4
189 | P01 | Submission review | 5
189 | P02 | Technical assessment | 5
189 | P03 | Commercial assessment | 9
189 | P04 | Approval and close | 2
190 | P01 | Submission review | 6
190 | P02 | Technical assessment | 6
190 | P03 | Commercial assessment | 6
190 | P04 | Approval and close | 3
191 | P01 | Submission review | 5
191 | P02 | Technical assessment | 6
191 | P03 | Commercial assessment | 6
191 | P04 | Approval and close | 4
192 | P01 | Submission review | 4
192 | P02 | Technical assessment | 7
192 | P03 | Commercial assessment | 4
192 | P04 | Approval and close | 4
193 | P01 | Submission review | 5
193 | P02 | Technical assessment | 6
193 | P03 | Commercial assessment | 6
193 | P04 | Approval and close | 3
194 | P01 | Submission review | 7
194 | P02 | Technical assessment | 5
194 | P03 | Commercial assessment | 6
194 | P04 | Approval and close | 5
195 | P01 | Submission review | 5
195 | P02 | Technical assessment | 5
195 | P03 | Commercial assessment | 4
195 | P04 | Approval and close | 3
196 | P01 | Submission review | 4
196 | P02 | Technical assessment | 7
196 | P03 | Commercial assessment | 8
196 | P04 | Approval and close | 3
197 | P01 | Submission review | 3
197 | P02 | Technical assessment | 6
197 | P03 | Commercial assessment | 6
197 | P04 | Approval and close | 3
198 | P01 | Submission review | 4
198 | P02 | Technical assessment | 4
198 | P03 | Commercial assessment | 6
198 | P04 | Approval and close | 3
199 | P01 | Submission review | 4
199 | P02 | Technical assessment | 5
199 | P03 | Commercial assessment | 6
199 | P04 | Approval and close | 3
200 | P01 | Submission review | 5
200 | P02 | Technical assessment | 5
200 | P03 | Commercial assessment | 7
200 | P04 | Approval and close | 4
201 | P01 | Submission review | 5
201 | P02 | Technical assessment | 5
201 | P03 | Commercial assessment | 5
201 | P04 | Approval and close | 3
202 | P01 | Submission review | 5
202 | P02 | Technical assessment | 6
202 | P03 | Commercial assessment | 6
202 | P04 | Approval and close | 3
203 | P01 | Submission review | 5
203 | P02 | Technical assessment | 6
203 | P03 | Commercial assessment | 5
203 | P04 | Approval and close | 4
204 | P01 | Submission review | 5
204 | P02 | Technical assessment | 7
204 | P03 | Commercial assessment | 6
204 | P04 | Approval and close | 3
205 | P01 | Submission review | 5
205 | P02 | Technical assessment | 5
205 | P03 | Commercial assessment | 9
205 | P04 | Approval and close | 3
206 | P01 | Submission review | 5
206 | P02 | Technical assessment | 7
206 | P03 | Commercial assessment | 8
206 | P04 | Approval and close | 4
207 | P01 | Submission review | 4
207 | P02 | Technical assessment | 8
207 | P03 | Commercial assessment | 10
207 | P04 | Approval and close | 3
208 | P01 | Submission review | 5
208 | P02 | Technical assessment | 6
208 | P03 | Commercial assessment | 4
208 | P04 | Approval and close | 4
209 | P01 | Submission review | 4
209 | P02 | Technical assessment | 5
209 | P03 | Commercial assessment | 7
209 | P04 | Approval and close | 5
210 | P01 | Submission review | 3
210 | P02 | Technical assessment | 5
210 | P03 | Commercial assessment | 5
210 | P04 | Approval and close | 2
211 | P01 | Submission review | 5
211 | P02 | Technical assessment | 5
211 | P03 | Commercial assessment | 7
211 | P04 | Approval and close | 3
212 | P01 | Submission review | 5
212 | P02 | Technical assessment | 5
212 | P03 | Commercial assessment | 8
212 | P04 | Approval and close | 3
213 | P01 | Submission review | 4
213 | P02 | Technical assessment | 6
213 | P03 | Commercial assessment | 6
213 | P04 | Approval and close | 4
214 | P01 | Submission review | 3
214 | P02 | Technical assessment | 4
214 | P03 | Commercial assessment | 4
214 | P04 | Approval and close | 3
215 | P01 | Submission review | 4
215 | P02 | Technical assessment | 7
215 | P03 | Commercial assessment | 5
215 | P04 | Approval and close | 3
216 | P01 | Submission review | 4
216 | P02 | Technical assessment | 7
216 | P03 | Commercial assessment | 10
216 | P04 | Approval and close | 3
217 | P01 | Submission review | 3
217 | P02 | Technical assessment | 6
217 | P03 | Commercial assessment | 10
217 | P04 | Approval and close | 4
218 | P01 | Submission review | 5
218 | P02 | Technical assessment | 5
218 | P03 | Commercial assessment | 8
218 | P04 | Approval and close | 2
219 | P01 | Submission review | 4
219 | P02 | Technical assessment | 6
219 | P03 | Commercial assessment | 7
219 | P04 | Approval and close | 4
220 | P01 | Submission review | 4
220 | P02 | Technical assessment | 6
220 | P03 | Commercial assessment | 6
220 | P04 | Approval and close | 4
221 | P01 | Submission review | 4
221 | P02 | Technical assessment | 5
221 | P03 | Commercial assessment | 8
221 | P04 | Approval and close | 2
222 | P01 | Submission review | 5
222 | P02 | Technical assessment | 8
222 | P03 | Commercial assessment | 6
222 | P04 | Approval and close | 3
223 | P01 | Submission review | 4
223 | P02 | Technical assessment | 5
223 | P03 | Commercial assessment | 10
223 | P04 | Approval and close | 3
224 | P01 | Submission review | 5
224 | P02 | Technical assessment | 6
224 | P03 | Commercial assessment | 10
224 | P04 | Approval and close | 2
225 | P01 | Submission review | 3
225 | P02 | Technical assessment | 7
225 | P03 | Commercial assessment | 8
225 | P04 | Approval and close | 2
226 | P01 | Submission review | 5
226 | P02 | Technical assessment | 6
226 | P03 | Commercial assessment | 7
226 | P04 | Approval and close | 3
227 | P01 | Submission review | 5
227 | P02 | Technical assessment | 4
227 | P03 | Commercial assessment | 10
227 | P04 | Approval and close | 4
228 | P01 | Submission review | 6
228 | P02 | Technical assessment | 6
228 | P03 | Commercial assessment | 4
228 | P04 | Approval and close | 3
229 | P01 | Submission review | 5
229 | P02 | Technical assessment | 7
229 | P03 | Commercial assessment | 5
229 | P04 | Approval and close | 3
230 | P01 | Submission review | 4
230 | P02 | Technical assessment | 7
230 | P03 | Commercial assessment | 6
230 | P04 | Approval and close | 4
231 | P01 | Submission review | 5
231 | P02 | Technical assessment | 6
231 | P03 | Commercial assessment | 5
231 | P04 | Approval and close | 4
232 | P01 | Submission review | 4
232 | P02 | Technical assessment | 7
232 | P03 | Commercial assessment | 7
232 | P04 | Approval and close | 3
233 | P01 | Submission review | 3
233 | P02 | Technical assessment | 4
233 | P03 | Commercial assessment | 6
233 | P04 | Approval and close | 3
234 | P01 | Submission review | 5
234 | P02 | Technical assessment | 6
234 | P03 | Commercial assessment | 5
234 | P04 | Approval and close | 3
235 | P01 | Submission review | 4
235 | P02 | Technical assessment | 6
235 | P03 | Commercial assessment | 7
235 | P04 | Approval and close | 4
236 | P01 | Submission review | 5
236 | P02 | Technical assessment | 7
236 | P03 | Commercial assessment | 5
236 | P04 | Approval and close | 4
237 | P01 | Submission review | 6
237 | P02 | Technical assessment | 4
237 | P03 | Commercial assessment | 4
237 | P04 | Approval and close | 3
238 | P01 | Submission review | 6
238 | P02 | Technical assessment | 5
238 | P03 | Commercial assessment | 5
238 | P04 | Approval and close | 3
239 | P01 | Submission review | 5
239 | P02 | Technical assessment | 6
239 | P03 | Commercial assessment | 6
239 | P04 | Approval and close | 3
240 | P01 | Submission review | 5
240 | P02 | Technical assessment | 5
240 | P03 | Commercial assessment | 6
240 | P04 | Approval and close | 3
241 | P01 | Submission review | 5
241 | P02 | Technical assessment | 4
241 | P03 | Commercial assessment | 10
241 | P04 | Approval and close | 4
242 | P01 | Submission review | 6
242 | P02 | Technical assessment | 6
242 | P03 | Commercial assessment | 11
242 | P04 | Approval and close | 5
243 | P01 | Submission review | 4
243 | P02 | Technical assessment | 7
243 | P03 | Commercial assessment | 8
243 | P04 | Approval and close | 3
244 | P01 | Submission review | 4
244 | P02 | Technical assessment | 5
244 | P03 | Commercial assessment | 7
244 | P04 | Approval and close | 3
245 | P01 | Submission review | 5
245 | P02 | Technical assessment | 7
245 | P03 | Commercial assessment | 8
245 | P04 | Approval and close | 3
246 | P01 | Submission review | 6
246 | P02 | Technical assessment | 9
246 | P03 | Commercial assessment | 8
246 | P04 | Approval and close | 4
247 | P01 | Submission review | 6
247 | P02 | Technical assessment | 4
247 | P03 | Commercial assessment | 4
247 | P04 | Approval and close | 4
248 | P01 | Submission review | 4
248 | P02 | Technical assessment | 4
248 | P03 | Commercial assessment | 9
248 | P04 | Approval and close | 5
249 | P01 | Submission review | 6
249 | P02 | Technical assessment | 6
249 | P03 | Commercial assessment | 6
249 | P04 | Approval and close | 3
250 | P01 | Submission review | 6
250 | P02 | Technical assessment | 7
250 | P03 | Commercial assessment | 9
250 | P04 | Approval and close | 3
251 | P01 | Submission review | 3
251 | P02 | Technical assessment | 5
251 | P03 | Commercial assessment | 5
251 | P04 | Approval and close | 2
252 | P01 | Submission review | 6
252 | P02 | Technical assessment | 5
252 | P03 | Commercial assessment | 8
252 | P04 | Approval and close | 4
253 | P01 | Submission review | 4
253 | P02 | Technical assessment | 6
253 | P03 | Commercial assessment | 6
253 | P04 | Approval and close | 4
254 | P01 | Submission review | 3
254 | P02 | Technical assessment | 4
254 | P03 | Commercial assessment | 7
254 | P04 | Approval and close | 4
255 | P01 | Submission review | 5
255 | P02 | Technical assessment | 7
255 | P03 | Commercial assessment | 4
255 | P04 | Approval and close | 4
256 | P01 | Submission review | 3
256 | P02 | Technical assessment | 7
256 | P03 | Commercial assessment | 5
256 | P04 | Approval and close | 4
257 | P01 | Submission review | 4
257 | P02 | Technical assessment | 7
257 | P03 | Commercial assessment | 4
257 | P04 | Approval and close | 5
258 | P01 | Submission review | 5
258 | P02 | Technical assessment | 6
258 | P03 | Commercial assessment | 8
258 | P04 | Approval and close | 3
259 | P01 | Submission review | 4
259 | P02 | Technical assessment | 7
259 | P03 | Commercial assessment | 8
259 | P04 | Approval and close | 3
260 | P01 | Submission review | 4
260 | P02 | Technical assessment | 6
260 | P03 | Commercial assessment | 4
260 | P04 | Approval and close | 4
261 | P01 | Submission review | 5
261 | P02 | Technical assessment | 6
261 | P03 | Commercial assessment | 7
261 | P04 | Approval and close | 3
262 | P01 | Submission review | 4
262 | P02 | Technical assessment | 4
262 | P03 | Commercial assessment | 4
262 | P04 | Approval and close | 3
263 | P01 | Submission review | 4
263 | P02 | Technical assessment | 6
263 | P03 | Commercial assessment | 5
263 | P04 | Approval and close | 4
264 | P01 | Submission review | 5
264 | P02 | Technical assessment | 5
264 | P03 | Commercial assessment | 11
264 | P04 | Approval and close | 3
265 | P01 | Submission review | 6
265 | P02 | Technical assessment | 6
265 | P03 | Commercial assessment | 8
265 | P04 | Approval and close | 5
266 | P01 | Submission review | 5
266 | P02 | Technical assessment | 6
266 | P03 | Commercial assessment | 6
266 | P04 | Approval and close | 3
267 | P01 | Submission review | 7
267 | P02 | Technical assessment | 5
267 | P03 | Commercial assessment | 9
267 | P04 | Approval and close | 4
268 | P01 | Submission review | 5
268 | P02 | Technical assessment | 4
268 | P03 | Commercial assessment | 7
268 | P04 | Approval and close | 4
269 | P01 | Submission review | 4
269 | P02 | Technical assessment | 5
269 | P03 | Commercial assessment | 9
269 | P04 | Approval and close | 3
270 | P01 | Submission review | 4
270 | P02 | Technical assessment | 6
270 | P03 | Commercial assessment | 5
270 | P04 | Approval and close | 3
271 | P01 | Submission review | 4
271 | P02 | Technical assessment | 6
271 | P03 | Commercial assessment | 9
271 | P04 | Approval and close | 4
272 | P01 | Submission review | 4
272 | P02 | Technical assessment | 5
272 | P03 | Commercial assessment | 4
272 | P04 | Approval and close | 3
273 | P01 | Submission review | 3
273 | P02 | Technical assessment | 6
273 | P03 | Commercial assessment | 6
273 | P04 | Approval and close | 3
274 | P01 | Submission review | 5
274 | P02 | Technical assessment | 6
274 | P03 | Commercial assessment | 7
274 | P04 | Approval and close | 4
275 | P01 | Submission review | 3
275 | P02 | Technical assessment | 5
275 | P03 | Commercial assessment | 6
275 | P04 | Approval and close | 3
276 | P01 | Submission review | 4
276 | P02 | Technical assessment | 5
276 | P03 | Commercial assessment | 3
276 | P04 | Approval and close | 5
277 | P01 | Submission review | 5
277 | P02 | Technical assessment | 6
277 | P03 | Commercial assessment | 8
277 | P04 | Approval and close | 2
278 | P01 | Submission review | 5
278 | P02 | Technical assessment | 7
278 | P03 | Commercial assessment | 8
278 | P04 | Approval and close | 4
279 | P01 | Submission review | 4
279 | P02 | Technical assessment | 7
279 | P03 | Commercial assessment | 10
279 | P04 | Approval and close | 2
280 | P01 | Submission review | 3
280 | P02 | Technical assessment | 4
280 | P03 | Commercial assessment | 6
280 | P04 | Approval and close | 3
281 | P01 | Submission review | 4
281 | P02 | Technical assessment | 8
281 | P03 | Commercial assessment | 7
281 | P04 | Approval and close | 4
282 | P01 | Submission review | 4
282 | P02 | Technical assessment | 4
282 | P03 | Commercial assessment | 9
282 | P04 | Approval and close | 3
283 | P01 | Submission review | 4
283 | P02 | Technical assessment | 7
283 | P03 | Commercial assessment | 6
283 | P04 | Approval and close | 5
284 | P01 | Submission review | 4
284 | P02 | Technical assessment | 6
284 | P03 | Commercial assessment | 8
284 | P04 | Approval and close | 5
285 | P01 | Submission review | 5
285 | P02 | Technical assessment | 4
285 | P03 | Commercial assessment | 7
285 | P04 | Approval and close | 3
286 | P01 | Submission review | 4
286 | P02 | Technical assessment | 8
286 | P03 | Commercial assessment | 9
286 | P04 | Approval and close | 4
287 | P01 | Submission review | 4
287 | P02 | Technical assessment | 4
287 | P03 | Commercial assessment | 8
287 | P04 | Approval and close | 3
288 | P01 | Submission review | 4
288 | P02 | Technical assessment | 9
288 | P03 | Commercial assessment | 8
288 | P04 | Approval and close | 3
289 | P01 | Submission review | 6
289 | P02 | Technical assessment | 8
289 | P03 | Commercial assessment | 6
289 | P04 | Approval and close | 5
290 | P01 | Submission review | 6
290 | P02 | Technical assessment | 8
290 | P03 | Commercial assessment | 5
290 | P04 | Approval and close | 4
291 | P01 | Submission review | 6
291 | P02 | Technical assessment | 8
291 | P03 | Commercial assessment | 7
291 | P04 | Approval and close | 3
292 | P01 | Submission review | 4
292 | P02 | Technical assessment | 4
292 | P03 | Commercial assessment | 7
292 | P04 | Approval and close | 5
293 | P01 | Submission review | 5
293 | P02 | Technical assessment | 5
293 | P03 | Commercial assessment | 9
293 | P04 | Approval and close | 5
294 | P01 | Submission review | 3
294 | P02 | Technical assessment | 6
294 | P03 | Commercial assessment | 6
294 | P04 | Approval and close | 2
295 | P01 | Submission review | 5
295 | P02 | Technical assessment | 7
295 | P03 | Commercial assessment | 9
295 | P04 | Approval and close | 4
296 | P01 | Submission review | 5
296 | P02 | Technical assessment | 8
296 | P03 | Commercial assessment | 10
296 | P04 | Approval and close | 4
297 | P01 | Submission review | 4
297 | P02 | Technical assessment | 5
297 | P03 | Commercial assessment | 9
297 | P04 | Approval and close | 4
298 | P01 | Submission review | 6
298 | P02 | Technical assessment | 5
298 | P03 | Commercial assessment | 6
298 | P04 | Approval and close | 4
299 | P01 | Submission review | 5
299 | P02 | Technical assessment | 5
299 | P03 | Commercial assessment | 7
299 | P04 | Approval and close | 5
300 | P01 | Submission review | 4
300 | P02 | Technical assessment | 7
300 | P03 | Commercial assessment | 8
300 | P04 | Approval and close | 2
301 | P01 | Submission review | 3
301 | P02 | Technical assessment | 6
301 | P03 | Commercial assessment | 10
301 | P04 | Approval and close | 3
302 | P01 | Submission review | 7
302 | P02 | Technical assessment | 6
302 | P03 | Commercial assessment | 6
302 | P04 | Approval and close | 2
303 | P01 | Submission review | 4
303 | P02 | Technical assessment | 4
303 | P03 | Commercial assessment | 4
303 | P04 | Approval and close | 3
304 | P01 | Submission review | 7
304 | P02 | Technical assessment | 6
304 | P03 | Commercial assessment | 7
304 | P04 | Approval and close | 3
305 | P01 | Submission review | 4
305 | P02 | Technical assessment | 5
305 | P03 | Commercial assessment | 8
305 | P04 | Approval and close | 3
306 | P01 | Submission review | 6
306 | P02 | Technical assessment | 5
306 | P03 | Commercial assessment | 8
306 | P04 | Approval and close | 4
307 | P01 | Submission review | 5
307 | P02 | Technical assessment | 5
307 | P03 | Commercial assessment | 4
307 | P04 | Approval and close | 4
308 | P01 | Submission review | 5
308 | P02 | Technical assessment | 7
308 | P03 | Commercial assessment | 4
308 | P04 | Approval and close | 4
309 | P01 | Submission review | 4
309 | P02 | Technical assessment | 5
309 | P03 | Commercial assessment | 11
309 | P04 | Approval and close | 4
310 | P01 | Submission review | 4
310 | P02 | Technical assessment | 6
310 | P03 | Commercial assessment | 7
310 | P04 | Approval and close | 3
311 | P01 | Submission review | 4
311 | P02 | Technical assessment | 4
311 | P03 | Commercial assessment | 4
311 | P04 | Approval and close | 3
312 | P01 | Submission review | 4
312 | P02 | Technical assessment | 4
312 | P03 | Commercial assessment | 8
312 | P04 | Approval and close | 4
313 | P01 | Submission review | 4
313 | P02 | Technical assessment | 4
313 | P03 | Commercial assessment | 7
313 | P04 | Approval and close | 4
314 | P01 | Submission review | 4
314 | P02 | Technical assessment | 6
314 | P03 | Commercial assessment | 7
314 | P04 | Approval and close | 2
315 | P01 | Submission review | 5
315 | P02 | Technical assessment | 8
315 | P03 | Commercial assessment | 7
315 | P04 | Approval and close | 3
316 | P01 | Submission review | 5
316 | P02 | Technical assessment | 7
316 | P03 | Commercial assessment | 5
316 | P04 | Approval and close | 4
317 | P01 | Submission review | 6
317 | P02 | Technical assessment | 6
317 | P03 | Commercial assessment | 7
317 | P04 | Approval and close | 5
318 | P01 | Submission review | 7
318 | P02 | Technical assessment | 5
318 | P03 | Commercial assessment | 10
318 | P04 | Approval and close | 4
319 | P01 | Submission review | 6
319 | P02 | Technical assessment | 7
319 | P03 | Commercial assessment | 6
319 | P04 | Approval and close | 3
320 | P01 | Submission review | 5
320 | P02 | Technical assessment | 6
320 | P03 | Commercial assessment | 6
320 | P04 | Approval and close | 5
321 | P01 | Submission review | 3
321 | P02 | Technical assessment | 7
321 | P03 | Commercial assessment | 8
321 | P04 | Approval and close | 4
322 | P01 | Submission review | 4
322 | P02 | Technical assessment | 4
322 | P03 | Commercial assessment | 4
322 | P04 | Approval and close | 4
323 | P01 | Submission review | 5
323 | P02 | Technical assessment | 6
323 | P03 | Commercial assessment | 5
323 | P04 | Approval and close | 2
324 | P01 | Submission review | 5
324 | P02 | Technical assessment | 4
324 | P03 | Commercial assessment | 9
324 | P04 | Approval and close | 4
325 | P01 | Submission review | 5
325 | P02 | Technical assessment | 4
325 | P03 | Commercial assessment | 5
325 | P04 | Approval and close | 3
326 | P01 | Submission review | 5
326 | P02 | Technical assessment | 6
326 | P03 | Commercial assessment | 5
326 | P04 | Approval and close | 4
327 | P01 | Submission review | 6
327 | P02 | Technical assessment | 6
327 | P03 | Commercial assessment | 5
327 | P04 | Approval and close | 3
328 | P01 | Submission review | 4
328 | P02 | Technical assessment | 6
328 | P03 | Commercial assessment | 5
328 | P04 | Approval and close | 5
329 | P01 | Submission review | 5
329 | P02 | Technical assessment | 6
329 | P03 | Commercial assessment | 5
329 | P04 | Approval and close | 3
330 | P01 | Submission review | 4
330 | P02 | Technical assessment | 4
330 | P03 | Commercial assessment | 5
330 | P04 | Approval and close | 4
331 | P01 | Submission review | 5
331 | P02 | Technical assessment | 5
331 | P03 | Commercial assessment | 9
331 | P04 | Approval and close | 3
332 | P01 | Submission review | 6
332 | P02 | Technical assessment | 5
332 | P03 | Commercial assessment | 10
332 | P04 | Approval and close | 2
333 | P01 | Submission review | 6
333 | P02 | Technical assessment | 4
333 | P03 | Commercial assessment | 6
333 | P04 | Approval and close | 2
334 | P01 | Submission review | 3
334 | P02 | Technical assessment | 6
334 | P03 | Commercial assessment | 8
334 | P04 | Approval and close | 4
335 | P01 | Submission review | 4
335 | P02 | Technical assessment | 6
335 | P03 | Commercial assessment | 5
335 | P04 | Approval and close | 5
336 | P01 | Submission review | 5
336 | P02 | Technical assessment | 5
336 | P03 | Commercial assessment | 7
336 | P04 | Approval and close | 4
337 | P01 | Submission review | 6
337 | P02 | Technical assessment | 7
337 | P03 | Commercial assessment | 6
337 | P04 | Approval and close | 4
338 | P01 | Submission review | 6
338 | P02 | Technical assessment | 4
338 | P03 | Commercial assessment | 4
338 | P04 | Approval and close | 2
339 | P01 | Submission review | 5
339 | P02 | Technical assessment | 7
339 | P03 | Commercial assessment | 4
339 | P04 | Approval and close | 4
340 | P01 | Submission review | 4
340 | P02 | Technical assessment | 7
340 | P03 | Commercial assessment | 6
340 | P04 | Approval and close | 3
341 | P01 | Submission review | 6
341 | P02 | Technical assessment | 4
341 | P03 | Commercial assessment | 5
341 | P04 | Approval and close | 4
342 | P01 | Submission review | 4
342 | P02 | Technical assessment | 6
342 | P03 | Commercial assessment | 4
342 | P04 | Approval and close | 3
343 | P01 | Submission review | 4
343 | P02 | Technical assessment | 6
343 | P03 | Commercial assessment | 10
343 | P04 | Approval and close | 4
344 | P01 | Submission review | 5
344 | P02 | Technical assessment | 6
344 | P03 | Commercial assessment | 3
344 | P04 | Approval and close | 4
345 | P01 | Submission review | 5
345 | P02 | Technical assessment | 4
345 | P03 | Commercial assessment | 5
345 | P04 | Approval and close | 3
346 | P01 | Submission review | 4
346 | P02 | Technical assessment | 8
346 | P03 | Commercial assessment | 6
346 | P04 | Approval and close | 4
347 | P01 | Submission review | 3
347 | P02 | Technical assessment | 4
347 | P03 | Commercial assessment | 10
347 | P04 | Approval and close | 5
348 | P01 | Submission review | 5
348 | P02 | Technical assessment | 6
348 | P03 | Commercial assessment | 4
348 | P04 | Approval and close | 3
349 | P01 | Submission review | 3
349 | P02 | Technical assessment | 8
349 | P03 | Commercial assessment | 7
349 | P04 | Approval and close | 2
350 | P01 | Submission review | 5
350 | P02 | Technical assessment | 5
350 | P03 | Commercial assessment | 10
350 | P04 | Approval and close | 3
351 | P01 | Submission review | 5
351 | P02 | Technical assessment | 6
351 | P03 | Commercial assessment | 4
351 | P04 | Approval and close | 4
352 | P01 | Submission review | 3
352 | P02 | Technical assessment | 5
352 | P03 | Commercial assessment | 9
352 | P04 | Approval and close | 3
353 | P01 | Submission review | 4
353 | P02 | Technical assessment | 4
353 | P03 | Commercial assessment | 9
353 | P04 | Approval and close | 3
354 | P01 | Submission review | 5
354 | P02 | Technical assessment | 5
354 | P03 | Commercial assessment | 10
354 | P04 | Approval and close | 4
355 | P01 | Submission review | 4
355 | P02 | Technical assessment | 4
355 | P03 | Commercial assessment | 6
355 | P04 | Approval and close | 3
356 | P01 | Submission review | 5
356 | P02 | Technical assessment | 6
356 | P03 | Commercial assessment | 8
356 | P04 | Approval and close | 4
357 | P01 | Submission review | 5
357 | P02 | Technical assessment | 6
357 | P03 | Commercial assessment | 5
357 | P04 | Approval and close | 2
358 | P01 | Submission review | 5
358 | P02 | Technical assessment | 7
358 | P03 | Commercial assessment | 10
358 | P04 | Approval and close | 4
359 | P01 | Submission review | 5
359 | P02 | Technical assessment | 4
359 | P03 | Commercial assessment | 6
359 | P04 | Approval and close | 3
360 | P01 | Submission review | 5
360 | P02 | Technical assessment | 7
360 | P03 | Commercial assessment | 7
360 | P04 | Approval and close | 3
361 | P01 | Submission review | 4
361 | P02 | Technical assessment | 6
361 | P03 | Commercial assessment | 8
361 | P04 | Approval and close | 4
362 | P01 | Submission review | 6
362 | P02 | Technical assessment | 6
362 | P03 | Commercial assessment | 12
362 | P04 | Approval and close | 4
363 | P01 | Submission review | 5
363 | P02 | Technical assessment | 4
363 | P03 | Commercial assessment | 7
363 | P04 | Approval and close | 3
364 | P01 | Submission review | 3
364 | P02 | Technical assessment | 7
364 | P03 | Commercial assessment | 8
364 | P04 | Approval and close | 5
365 | P01 | Submission review | 3
365 | P02 | Technical assessment | 5
365 | P03 | Commercial assessment | 6
365 | P04 | Approval and close | 2
366 | P01 | Submission review | 7
366 | P02 | Technical assessment | 8
366 | P03 | Commercial assessment | 4
366 | P04 | Approval and close | 4
367 | P01 | Submission review | 4
367 | P02 | Technical assessment | 6
367 | P03 | Commercial assessment | 5
367 | P04 | Approval and close | 4
368 | P01 | Submission review | 5
368 | P02 | Technical assessment | 6
368 | P03 | Commercial assessment | 7
368 | P04 | Approval and close | 4
369 | P01 | Submission review | 4
369 | P02 | Technical assessment | 7
369 | P03 | Commercial assessment | 9
369 | P04 | Approval and close | 2
370 | P01 | Submission review | 4
370 | P02 | Technical assessment | 8
370 | P03 | Commercial assessment | 7
370 | P04 | Approval and close | 3
371 | P01 | Submission review | 5
371 | P02 | Technical assessment | 7
371 | P03 | Commercial assessment | 7
371 | P04 | Approval and close | 4
372 | P01 | Submission review | 4
372 | P02 | Technical assessment | 6
372 | P03 | Commercial assessment | 8
372 | P04 | Approval and close | 3
373 | P01 | Submission review | 4
373 | P02 | Technical assessment | 4
373 | P03 | Commercial assessment | 9
373 | P04 | Approval and close | 4
374 | P01 | Submission review | 4
374 | P02 | Technical assessment | 5
374 | P03 | Commercial assessment | 8
374 | P04 | Approval and close | 4
375 | P01 | Submission review | 3
375 | P02 | Technical assessment | 6
375 | P03 | Commercial assessment | 4
375 | P04 | Approval and close | 4
376 | P01 | Submission review | 6
376 | P02 | Technical assessment | 6
376 | P03 | Commercial assessment | 8
376 | P04 | Approval and close | 4
377 | P01 | Submission review | 6
377 | P02 | Technical assessment | 5
377 | P03 | Commercial assessment | 6
377 | P04 | Approval and close | 3
378 | P01 | Submission review | 6
378 | P02 | Technical assessment | 5
378 | P03 | Commercial assessment | 8
378 | P04 | Approval and close | 3
379 | P01 | Submission review | 4
379 | P02 | Technical assessment | 5
379 | P03 | Commercial assessment | 3
379 | P04 | Approval and close | 3
380 | P01 | Submission review | 5
380 | P02 | Technical assessment | 5
380 | P03 | Commercial assessment | 6
380 | P04 | Approval and close | 4
381 | P01 | Submission review | 5
381 | P02 | Technical assessment | 5
381 | P03 | Commercial assessment | 4
381 | P04 | Approval and close | 3
382 | P01 | Submission review | 4
382 | P02 | Technical assessment | 8
382 | P03 | Commercial assessment | 8
382 | P04 | Approval and close | 3
383 | P01 | Submission review | 4
383 | P02 | Technical assessment | 6
383 | P03 | Commercial assessment | 6
383 | P04 | Approval and close | 4
384 | P01 | Submission review | 5
384 | P02 | Technical assessment | 5
384 | P03 | Commercial assessment | 6
384 | P04 | Approval and close | 5
385 | P01 | Submission review | 4
385 | P02 | Technical assessment | 5
385 | P03 | Commercial assessment | 9
385 | P04 | Approval and close | 3
386 | P01 | Submission review | 4
386 | P02 | Technical assessment | 5
386 | P03 | Commercial assessment | 8
386 | P04 | Approval and close | 3
387 | P01 | Submission review | 5
387 | P02 | Technical assessment | 6
387 | P03 | Commercial assessment | 7
387 | P04 | Approval and close | 5
388 | P01 | Submission review | 6
388 | P02 | Technical assessment | 4
388 | P03 | Commercial assessment | 8
388 | P04 | Approval and close | 3
389 | P01 | Submission review | 4
389 | P02 | Technical assessment | 5
389 | P03 | Commercial assessment | 6
389 | P04 | Approval and close | 3
390 | P01 | Submission review | 3
390 | P02 | Technical assessment | 5
390 | P03 | Commercial assessment | 4
390 | P04 | Approval and close | 3
391 | P01 | Submission review | 4
391 | P02 | Technical assessment | 5
391 | P03 | Commercial assessment | 8
391 | P04 | Approval and close | 4
392 | P01 | Submission review | 4
392 | P02 | Technical assessment | 8
392 | P03 | Commercial assessment | 8
392 | P04 | Approval and close | 4
393 | P01 | Submission review | 4
393 | P02 | Technical assessment | 6
393 | P03 | Commercial assessment | 9
393 | P04 | Approval and close | 3
394 | P01 | Submission review | 5
394 | P02 | Technical assessment | 5
394 | P03 | Commercial assessment | 8
394 | P04 | Approval and close | 4
395 | P01 | Submission review | 4
395 | P02 | Technical assessment | 7
395 | P03 | Commercial assessment | 6
395 | P04 | Approval and close | 5
396 | P01 | Submission review | 6
396 | P02 | Technical assessment | 7
396 | P03 | Commercial assessment | 8
396 | P04 | Approval and close | 3
397 | P01 | Submission review | 4
397 | P02 | Technical assessment | 6
397 | P03 | Commercial assessment | 5
397 | P04 | Approval and close | 4
398 | P01 | Submission review | 6
398 | P02 | Technical assessment | 6
398 | P03 | Commercial assessment | 10
398 | P04 | Approval and close | 4
399 | P01 | Submission review | 5
399 | P02 | Technical assessment | 7
399 | P03 | Commercial assessment | 4
399 | P04 | Approval and close | 3
400 | P01 | Submission review | 6
400 | P02 | Technical assessment | 5
400 | P03 | Commercial assessment | 5
400 | P04 | Approval and close | 3
401 | P01 | Submission review | 5
401 | P02 | Technical assessment | 5
401 | P03 | Commercial assessment | 7
401 | P04 | Approval and close | 3
402 | P01 | Submission review | 5
402 | P02 | Technical assessment | 4
402 | P03 | Commercial assessment | 8
402 | P04 | Approval and close | 4
403 | P01 | Submission review | 5
403 | P02 | Technical assessment | 7
403 | P03 | Commercial assessment | 5
403 | P04 | Approval and close | 3
404 | P01 | Submission review | 5
404 | P02 | Technical assessment | 8
404 | P03 | Commercial assessment | 7
404 | P04 | Approval and close | 3
405 | P01 | Submission review | 6
405 | P02 | Technical assessment | 6
405 | P03 | Commercial assessment | 8
405 | P04 | Approval and close | 3
406 | P01 | Submission review | 4
406 | P02 | Technical assessment | 5
406 | P03 | Commercial assessment | 10
406 | P04 | Approval and close | 3
407 | P01 | Submission review | 5
407 | P02 | Technical assessment | 5
407 | P03 | Commercial assessment | 5
407 | P04 | Approval and close | 4
408 | P01 | Submission review | 6
408 | P02 | Technical assessment | 5
408 | P03 | Commercial assessment | 9
408 | P04 | Approval and close | 4
409 | P01 | Submission review | 5
409 | P02 | Technical assessment | 7
409 | P03 | Commercial assessment | 8
409 | P04 | Approval and close | 4
410 | P01 | Submission review | 3
410 | P02 | Technical assessment | 7
410 | P03 | Commercial assessment | 9
410 | P04 | Approval and close | 3
411 | P01 | Submission review | 5
411 | P02 | Technical assessment | 6
411 | P03 | Commercial assessment | 7
411 | P04 | Approval and close | 5
412 | P01 | Submission review | 5
412 | P02 | Technical assessment | 5
412 | P03 | Commercial assessment | 9
412 | P04 | Approval and close | 3
413 | P01 | Submission review | 4
413 | P02 | Technical assessment | 6
413 | P03 | Commercial assessment | 7
413 | P04 | Approval and close | 3
414 | P01 | Submission review | 5
414 | P02 | Technical assessment | 8
414 | P03 | Commercial assessment | 8
414 | P04 | Approval and close | 4
415 | P01 | Submission review | 4
415 | P02 | Technical assessment | 6
415 | P03 | Commercial assessment | 4
415 | P04 | Approval and close | 4
416 | P01 | Submission review | 5
416 | P02 | Technical assessment | 7
416 | P03 | Commercial assessment | 7
416 | P04 | Approval and close | 3
417 | P01 | Submission review | 4
417 | P02 | Technical assessment | 5
417 | P03 | Commercial assessment | 6
417 | P04 | Approval and close | 4
418 | P01 | Submission review | 6
418 | P02 | Technical assessment | 7
418 | P03 | Commercial assessment | 6
418 | P04 | Approval and close | 3
419 | P01 | Submission review | 4
419 | P02 | Technical assessment | 5
419 | P03 | Commercial assessment | 4
419 | P04 | Approval and close | 5
420 | P01 | Submission review | 5
420 | P02 | Technical assessment | 6
420 | P03 | Commercial assessment | 4
420 | P04 | Approval and close | 4
421 | P01 | Submission review | 5
421 | P02 | Technical assessment | 7
421 | P03 | Commercial assessment | 5
421 | P04 | Approval and close | 3
422 | P01 | Submission review | 5
422 | P02 | Technical assessment | 7
422 | P03 | Commercial assessment | 9
422 | P04 | Approval and close | 3
423 | P01 | Submission review | 4
423 | P02 | Technical assessment | 7
423 | P03 | Commercial assessment | 6
423 | P04 | Approval and close | 5
424 | P01 | Submission review | 4
424 | P02 | Technical assessment | 7
424 | P03 | Commercial assessment | 4
424 | P04 | Approval and close | 4
425 | P01 | Submission review | 4
425 | P02 | Technical assessment | 5
425 | P03 | Commercial assessment | 8
425 | P04 | Approval and close | 4
426 | P01 | Submission review | 5
426 | P02 | Technical assessment | 7
426 | P03 | Commercial assessment | 6
426 | P04 | Approval and close | 3
427 | P01 | Submission review | 5
427 | P02 | Technical assessment | 6
427 | P03 | Commercial assessment | 6
427 | P04 | Approval and close | 3
428 | P01 | Submission review | 4
428 | P02 | Technical assessment | 6
428 | P03 | Commercial assessment | 8
428 | P04 | Approval and close | 5
429 | P01 | Submission review | 4
429 | P02 | Technical assessment | 7
429 | P03 | Commercial assessment | 7
429 | P04 | Approval and close | 4
430 | P01 | Submission review | 4
430 | P02 | Technical assessment | 4
430 | P03 | Commercial assessment | 8
430 | P04 | Approval and close | 4
431 | P01 | Submission review | 5
431 | P02 | Technical assessment | 8
431 | P03 | Commercial assessment | 9
431 | P04 | Approval and close | 5
432 | P01 | Submission review | 4
432 | P02 | Technical assessment | 5
432 | P03 | Commercial assessment | 10
432 | P04 | Approval and close | 3
433 | P01 | Submission review | 4
433 | P02 | Technical assessment | 5
433 | P03 | Commercial assessment | 7
433 | P04 | Approval and close | 3
434 | P01 | Submission review | 4
434 | P02 | Technical assessment | 5
434 | P03 | Commercial assessment | 9
434 | P04 | Approval and close | 3
435 | P01 | Submission review | 5
435 | P02 | Technical assessment | 5
435 | P03 | Commercial assessment | 7
435 | P04 | Approval and close | 5
436 | P01 | Submission review | 4
436 | P02 | Technical assessment | 7
436 | P03 | Commercial assessment | 6
436 | P04 | Approval and close | 3
437 | P01 | Submission review | 5
437 | P02 | Technical assessment | 4
437 | P03 | Commercial assessment | 6
437 | P04 | Approval and close | 3
438 | P01 | Submission review | 5
438 | P02 | Technical assessment | 6
438 | P03 | Commercial assessment | 4
438 | P04 | Approval and close | 4
439 | P01 | Submission review | 4
439 | P02 | Technical assessment | 6
439 | P03 | Commercial assessment | 10
439 | P04 | Approval and close | 4
440 | P01 | Submission review | 3
440 | P02 | Technical assessment | 7
440 | P03 | Commercial assessment | 8
440 | P04 | Approval and close | 4
441 | P01 | Submission review | 5
441 | P02 | Technical assessment | 6
441 | P03 | Commercial assessment | 7
441 | P04 | Approval and close | 4
442 | P01 | Submission review | 3
442 | P02 | Technical assessment | 6
442 | P03 | Commercial assessment | 9
442 | P04 | Approval and close | 3
443 | P01 | Submission review | 4
443 | P02 | Technical assessment | 6
443 | P03 | Commercial assessment | 6
443 | P04 | Approval and close | 4
444 | P01 | Submission review | 4
444 | P02 | Technical assessment | 6
444 | P03 | Commercial assessment | 5
444 | P04 | Approval and close | 4
445 | P01 | Submission review | 3
445 | P02 | Technical assessment | 5
445 | P03 | Commercial assessment | 5
445 | P04 | Approval and close | 3
446 | P01 | Submission review | 4
446 | P02 | Technical assessment | 5
446 | P03 | Commercial assessment | 6
446 | P04 | Approval and close | 4
447 | P01 | Submission review | 6
447 | P02 | Technical assessment | 4
447 | P03 | Commercial assessment | 7
447 | P04 | Approval and close | 4
448 | P01 | Submission review | 6
448 | P02 | Technical assessment | 7
448 | P03 | Commercial assessment | 6
448 | P04 | Approval and close | 3
449 | P01 | Submission review | 5
449 | P02 | Technical assessment | 7
449 | P03 | Commercial assessment | 7
449 | P04 | Approval and close | 3
450 | P01 | Submission review | 5
450 | P02 | Technical assessment | 6
450 | P03 | Commercial assessment | 8
450 | P04 | Approval and close | 3
451 | P01 | Submission review | 4
451 | P02 | Technical assessment | 7
451 | P03 | Commercial assessment | 5
451 | P04 | Approval and close | 4
452 | P01 | Submission review | 5
452 | P02 | Technical assessment | 8
452 | P03 | Commercial assessment | 7
452 | P04 | Approval and close | 3
453 | P01 | Submission review | 6
453 | P02 | Technical assessment | 4
453 | P03 | Commercial assessment | 8
453 | P04 | Approval and close | 3
454 | P01 | Submission review | 4
454 | P02 | Technical assessment | 4
454 | P03 | Commercial assessment | 5
454 | P04 | Approval and close | 3
455 | P01 | Submission review | 5
455 | P02 | Technical assessment | 8
455 | P03 | Commercial assessment | 7
455 | P04 | Approval and close | 4
456 | P01 | Submission review | 6
456 | P02 | Technical assessment | 7
456 | P03 | Commercial assessment | 8
456 | P04 | Approval and close | 4
457 | P01 | Submission review | 4
457 | P02 | Technical assessment | 7
457 | P03 | Commercial assessment | 8
457 | P04 | Approval and close | 4
458 | P01 | Submission review | 3
458 | P02 | Technical assessment | 7
458 | P03 | Commercial assessment | 7
458 | P04 | Approval and close | 2
459 | P01 | Submission review | 4
459 | P02 | Technical assessment | 5
459 | P03 | Commercial assessment | 6
459 | P04 | Approval and close | 3
460 | P01 | Submission review | 4
460 | P02 | Technical assessment | 5
460 | P03 | Commercial assessment | 4
460 | P04 | Approval and close | 2
461 | P01 | Submission review | 4
461 | P02 | Technical assessment | 6
461 | P03 | Commercial assessment | 6
461 | P04 | Approval and close | 4
462 | P01 | Submission review | 4
462 | P02 | Technical assessment | 6
462 | P03 | Commercial assessment | 8
462 | P04 | Approval and close | 3
463 | P01 | Submission review | 5
463 | P02 | Technical assessment | 8
463 | P03 | Commercial assessment | 10
463 | P04 | Approval and close | 5
464 | P01 | Submission review | 4
464 | P02 | Technical assessment | 9
464 | P03 | Commercial assessment | 4
464 | P04 | Approval and close | 2
465 | P01 | Submission review | 5
465 | P02 | Technical assessment | 7
465 | P03 | Commercial assessment | 11
465 | P04 | Approval and close | 4
466 | P01 | Submission review | 6
466 | P02 | Technical assessment | 7
466 | P03 | Commercial assessment | 9
466 | P04 | Approval and close | 3
467 | P01 | Submission review | 4
467 | P02 | Technical assessment | 6
467 | P03 | Commercial assessment | 8
467 | P04 | Approval and close | 4
468 | P01 | Submission review | 3
468 | P02 | Technical assessment | 4
468 | P03 | Commercial assessment | 5
468 | P04 | Approval and close | 2
469 | P01 | Submission review | 5
469 | P02 | Technical assessment | 7
469 | P03 | Commercial assessment | 9
469 | P04 | Approval and close | 3
470 | P01 | Submission review | 5
470 | P02 | Technical assessment | 5
470 | P03 | Commercial assessment | 10
470 | P04 | Approval and close | 4
471 | P01 | Submission review | 6
471 | P02 | Technical assessment | 7
471 | P03 | Commercial assessment | 8
471 | P04 | Approval and close | 4
472 | P01 | Submission review | 7
472 | P02 | Technical assessment | 5
472 | P03 | Commercial assessment | 11
472 | P04 | Approval and close | 4
473 | P01 | Submission review | 4
473 | P02 | Technical assessment | 6
473 | P03 | Commercial assessment | 7
473 | P04 | Approval and close | 3
474 | P01 | Submission review | 3
474 | P02 | Technical assessment | 5
474 | P03 | Commercial assessment | 7
474 | P04 | Approval and close | 5
475 | P01 | Submission review | 5
475 | P02 | Technical assessment | 5
475 | P03 | Commercial assessment | 7
475 | P04 | Approval and close | 3
476 | P01 | Submission review | 5
476 | P02 | Technical assessment | 5
476 | P03 | Commercial assessment | 6
476 | P04 | Approval and close | 3
477 | P01 | Submission review | 3
477 | P02 | Technical assessment | 7
477 | P03 | Commercial assessment | 7
477 | P04 | Approval and close | 4
478 | P01 | Submission review | 4
478 | P02 | Technical assessment | 5
478 | P03 | Commercial assessment | 6
478 | P04 | Approval and close | 3
479 | P01 | Submission review | 5
479 | P02 | Technical assessment | 7
479 | P03 | Commercial assessment | 6
479 | P04 | Approval and close | 3
480 | P01 | Submission review | 3
480 | P02 | Technical assessment | 4
480 | P03 | Commercial assessment | 7
480 | P04 | Approval and close | 2
481 | P01 | Submission review | 5
481 | P02 | Technical assessment | 4
481 | P03 | Commercial assessment | 7
481 | P04 | Approval and close | 3
482 | P01 | Submission review | 4
482 | P02 | Technical assessment | 4
482 | P03 | Commercial assessment | 5
482 | P04 | Approval and close | 4
483 | P01 | Submission review | 5
483 | P02 | Technical assessment | 7
483 | P03 | Commercial assessment | 9
483 | P04 | Approval and close | 3
484 | P01 | Submission review | 5
484 | P02 | Technical assessment | 5
484 | P03 | Commercial assessment | 6
484 | P04 | Approval and close | 2
485 | P01 | Submission review | 5
485 | P02 | Technical assessment | 5
485 | P03 | Commercial assessment | 9
485 | P04 | Approval and close | 4
486 | P01 | Submission review | 6
486 | P02 | Technical assessment | 5
486 | P03 | Commercial assessment | 9
486 | P04 | Approval and close | 3
487 | P01 | Submission review | 7
487 | P02 | Technical assessment | 4
487 | P03 | Commercial assessment | 7
487 | P04 | Approval and close | 5
488 | P01 | Submission review | 4
488 | P02 | Technical assessment | 5
488 | P03 | Commercial assessment | 9
488 | P04 | Approval and close | 3
489 | P01 | Submission review | 5
489 | P02 | Technical assessment | 7
489 | P03 | Commercial assessment | 8
489 | P04 | Approval and close | 4
490 | P01 | Submission review | 5
490 | P02 | Technical assessment | 6
490 | P03 | Commercial assessment | 6
490 | P04 | Approval and close | 2
491 | P01 | Submission review | 4
491 | P02 | Technical assessment | 5
491 | P03 | Commercial assessment | 7
491 | P04 | Approval and close | 2
492 | P01 | Submission review | 6
492 | P02 | Technical assessment | 8
492 | P03 | Commercial assessment | 6
492 | P04 | Approval and close | 4
493 | P01 | Submission review | 4
493 | P02 | Technical assessment | 4
493 | P03 | Commercial assessment | 8
493 | P04 | Approval and close | 3
494 | P01 | Submission review | 7
494 | P02 | Technical assessment | 7
494 | P03 | Commercial assessment | 9
494 | P04 | Approval and close | 3
495 | P01 | Submission review | 5
495 | P02 | Technical assessment | 4
495 | P03 | Commercial assessment | 8
495 | P04 | Approval and close | 2
496 | P01 | Submission review | 4
496 | P02 | Technical assessment | 7
496 | P03 | Commercial assessment | 6
496 | P04 | Approval and close | 3
497 | P01 | Submission review | 5
497 | P02 | Technical assessment | 5
497 | P03 | Commercial assessment | 8
497 | P04 | Approval and close | 3
498 | P01 | Submission review | 5
498 | P02 | Technical assessment | 5
498 | P03 | Commercial assessment | 7
498 | P04 | Approval and close | 4
499 | P01 | Submission review | 4
499 | P02 | Technical assessment | 6
499 | P03 | Commercial assessment | 8
499 | P04 | Approval and close | 3
500 | P01 | Submission review | 4
500 | P02 | Technical assessment | 7
500 | P03 | Commercial assessment | 5
500 | P04 | Approval and close | 5
501 | P01 | Submission review | 4
501 | P02 | Technical assessment | 7
501 | P03 | Commercial assessment | 9
501 | P04 | Approval and close | 4
502 | P01 | Submission review | 3
502 | P02 | Technical assessment | 5
502 | P03 | Commercial assessment | 7
502 | P04 | Approval and close | 2
503 | P01 | Submission review | 6
503 | P02 | Technical assessment | 5
503 | P03 | Commercial assessment | 11
503 | P04 | Approval and close | 3
504 | P01 | Submission review | 3
504 | P02 | Technical assessment | 5
504 | P03 | Commercial assessment | 8
504 | P04 | Approval and close | 3
505 | P01 | Submission review | 4
505 | P02 | Technical assessment | 5
505 | P03 | Commercial assessment | 8
505 | P04 | Approval and close | 4
506 | P01 | Submission review | 4
506 | P02 | Technical assessment | 7
506 | P03 | Commercial assessment | 8
506 | P04 | Approval and close | 3
507 | P01 | Submission review | 6
507 | P02 | Technical assessment | 6
507 | P03 | Commercial assessment | 4
507 | P04 | Approval and close | 4
508 | P01 | Submission review | 4
508 | P02 | Technical assessment | 6
508 | P03 | Commercial assessment | 10
508 | P04 | Approval and close | 3
509 | P01 | Submission review | 6
509 | P02 | Technical assessment | 5
509 | P03 | Commercial assessment | 7
509 | P04 | Approval and close | 4
510 | P01 | Submission review | 6
510 | P02 | Technical assessment | 5
510 | P03 | Commercial assessment | 9
510 | P04 | Approval and close | 4
511 | P01 | Submission review | 3
511 | P02 | Technical assessment | 5
511 | P03 | Commercial assessment | 4
511 | P04 | Approval and close | 3
512 | P01 | Submission review | 4
512 | P02 | Technical assessment | 5
512 | P03 | Commercial assessment | 10
512 | P04 | Approval and close | 4
513 | P01 | Submission review | 3
513 | P02 | Technical assessment | 6
513 | P03 | Commercial assessment | 8
513 | P04 | Approval and close | 3
514 | P01 | Submission review | 4
514 | P02 | Technical assessment | 6
514 | P03 | Commercial assessment | 5
514 | P04 | Approval and close | 5
515 | P01 | Submission review | 5
515 | P02 | Technical assessment | 8
515 | P03 | Commercial assessment | 6
515 | P04 | Approval and close | 3
516 | P01 | Submission review | 4
516 | P02 | Technical assessment | 5
516 | P03 | Commercial assessment | 9
516 | P04 | Approval and close | 4
517 | P01 | Submission review | 4
517 | P02 | Technical assessment | 4
517 | P03 | Commercial assessment | 5
517 | P04 | Approval and close | 3
518 | P01 | Submission review | 4
518 | P02 | Technical assessment | 5
518 | P03 | Commercial assessment | 7
518 | P04 | Approval and close | 3
519 | P01 | Submission review | 5
519 | P02 | Technical assessment | 6
519 | P03 | Commercial assessment | 7
519 | P04 | Approval and close | 4
520 | P01 | Submission review | 6
520 | P02 | Technical assessment | 6
520 | P03 | Commercial assessment | 6
520 | P04 | Approval and close | 3
521 | P01 | Submission review | 4
521 | P02 | Technical assessment | 5
521 | P03 | Commercial assessment | 11
521 | P04 | Approval and close | 2
522 | P01 | Submission review | 4
522 | P02 | Technical assessment | 6
522 | P03 | Commercial assessment | 7
522 | P04 | Approval and close | 2
523 | P01 | Submission review | 6
523 | P02 | Technical assessment | 8
523 | P03 | Commercial assessment | 7
523 | P04 | Approval and close | 4
524 | P01 | Submission review | 5
524 | P02 | Technical assessment | 4
524 | P03 | Commercial assessment | 8
524 | P04 | Approval and close | 2
525 | P01 | Submission review | 5
525 | P02 | Technical assessment | 6
525 | P03 | Commercial assessment | 6
525 | P04 | Approval and close | 4
526 | P01 | Submission review | 4
526 | P02 | Technical assessment | 6
526 | P03 | Commercial assessment | 9
526 | P04 | Approval and close | 3
527 | P01 | Submission review | 5
527 | P02 | Technical assessment | 5
527 | P03 | Commercial assessment | 10
527 | P04 | Approval and close | 4
528 | P01 | Submission review | 4
528 | P02 | Technical assessment | 5
528 | P03 | Commercial assessment | 8
528 | P04 | Approval and close | 4
529 | P01 | Submission review | 6
529 | P02 | Technical assessment | 6
529 | P03 | Commercial assessment | 10
529 | P04 | Approval and close | 3
530 | P01 | Submission review | 5
530 | P02 | Technical assessment | 5
530 | P03 | Commercial assessment | 4
530 | P04 | Approval and close | 4
531 | P01 | Submission review | 5
531 | P02 | Technical assessment | 4
531 | P03 | Commercial assessment | 6
531 | P04 | Approval and close | 3
532 | P01 | Submission review | 4
532 | P02 | Technical assessment | 5
532 | P03 | Commercial assessment | 5
532 | P04 | Approval and close | 4
533 | P01 | Submission review | 5
533 | P02 | Technical assessment | 6
533 | P03 | Commercial assessment | 3
533 | P04 | Approval and close | 3
534 | P01 | Submission review | 4
534 | P02 | Technical assessment | 5
534 | P03 | Commercial assessment | 4
534 | P04 | Approval and close | 3
535 | P01 | Submission review | 6
535 | P02 | Technical assessment | 7
535 | P03 | Commercial assessment | 6
535 | P04 | Approval and close | 2
536 | P01 | Submission review | 5
536 | P02 | Technical assessment | 5
536 | P03 | Commercial assessment | 5
536 | P04 | Approval and close | 4
537 | P01 | Submission review | 7
537 | P02 | Technical assessment | 6
537 | P03 | Commercial assessment | 7
537 | P04 | Approval and close | 4
538 | P01 | Submission review | 4
538 | P02 | Technical assessment | 6
538 | P03 | Commercial assessment | 8
538 | P04 | Approval and close | 4
539 | P01 | Submission review | 4
539 | P02 | Technical assessment | 6
539 | P03 | Commercial assessment | 5
539 | P04 | Approval and close | 3
540 | P01 | Submission review | 6
540 | P02 | Technical assessment | 7
540 | P03 | Commercial assessment | 8
540 | P04 | Approval and close | 2
541 | P01 | Submission review | 5
541 | P02 | Technical assessment | 6
541 | P03 | Commercial assessment | 7
541 | P04 | Approval and close | 4
542 | P01 | Submission review | 3
542 | P02 | Technical assessment | 5
542 | P03 | Commercial assessment | 6
542 | P04 | Approval and close | 4
543 | P01 | Submission review | 3
543 | P02 | Technical assessment | 4
543 | P03 | Commercial assessment | 7
543 | P04 | Approval and close | 3
544 | P01 | Submission review | 5
544 | P02 | Technical assessment | 6
544 | P03 | Commercial assessment | 8
544 | P04 | Approval and close | 3
545 | P01 | Submission review | 4
545 | P02 | Technical assessment | 6
545 | P03 | Commercial assessment | 6
545 | P04 | Approval and close | 4
546 | P01 | Submission review | 5
546 | P02 | Technical assessment | 7
546 | P03 | Commercial assessment | 5
546 | P04 | Approval and close | 4
547 | P01 | Submission review | 4
547 | P02 | Technical assessment | 6
547 | P03 | Commercial assessment | 4
547 | P04 | Approval and close | 4
548 | P01 | Submission review | 3
548 | P02 | Technical assessment | 6
548 | P03 | Commercial assessment | 5
548 | P04 | Approval and close | 4
549 | P01 | Submission review | 4
549 | P02 | Technical assessment | 6
549 | P03 | Commercial assessment | 7
549 | P04 | Approval and close | 3
550 | P01 | Submission review | 3
550 | P02 | Technical assessment | 6
550 | P03 | Commercial assessment | 5
550 | P04 | Approval and close | 4
551 | P01 | Submission review | 4
551 | P02 | Technical assessment | 6
551 | P03 | Commercial assessment | 9
551 | P04 | Approval and close | 5
552 | P01 | Submission review | 5
552 | P02 | Technical assessment | 9
552 | P03 | Commercial assessment | 6
552 | P04 | Approval and close | 3
553 | P01 | Submission review | 5
553 | P02 | Technical assessment | 5
553 | P03 | Commercial assessment | 4
553 | P04 | Approval and close | 4
554 | P01 | Submission review | 4
554 | P02 | Technical assessment | 6
554 | P03 | Commercial assessment | 5
554 | P04 | Approval and close | 3
555 | P01 | Submission review | 4
555 | P02 | Technical assessment | 6
555 | P03 | Commercial assessment | 11
555 | P04 | Approval and close | 4
556 | P01 | Submission review | 5
556 | P02 | Technical assessment | 8
556 | P03 | Commercial assessment | 7
556 | P04 | Approval and close | 4
557 | P01 | Submission review | 4
557 | P02 | Technical assessment | 6
557 | P03 | Commercial assessment | 7
557 | P04 | Approval and close | 4
558 | P01 | Submission review | 5
558 | P02 | Technical assessment | 6
558 | P03 | Commercial assessment | 7
558 | P04 | Approval and close | 2
559 | P01 | Submission review | 4
559 | P02 | Technical assessment | 5
559 | P03 | Commercial assessment | 7
559 | P04 | Approval and close | 2
560 | P01 | Submission review | 4
560 | P02 | Technical assessment | 7
560 | P03 | Commercial assessment | 9
560 | P04 | Approval and close | 4
561 | P01 | Submission review | 6
561 | P02 | Technical assessment | 7
561 | P03 | Commercial assessment | 10
561 | P04 | Approval and close | 3
562 | P01 | Submission review | 5
562 | P02 | Technical assessment | 6
562 | P03 | Commercial assessment | 6
562 | P04 | Approval and close | 4
563 | P01 | Submission review | 4
563 | P02 | Technical assessment | 6
563 | P03 | Commercial assessment | 6
563 | P04 | Approval and close | 3
564 | P01 | Submission review | 6
564 | P02 | Technical assessment | 5
564 | P03 | Commercial assessment | 9
564 | P04 | Approval and close | 2
565 | P01 | Submission review | 4
565 | P02 | Technical assessment | 5
565 | P03 | Commercial assessment | 9
565 | P04 | Approval and close | 2
566 | P01 | Submission review | 6
566 | P02 | Technical assessment | 6
566 | P03 | Commercial assessment | 7
566 | P04 | Approval and close | 3
567 | P01 | Submission review | 5
567 | P02 | Technical assessment | 5
567 | P03 | Commercial assessment | 5
567 | P04 | Approval and close | 4
568 | P01 | Submission review | 3
568 | P02 | Technical assessment | 5
568 | P03 | Commercial assessment | 8
568 | P04 | Approval and close | 3
569 | P01 | Submission review | 5
569 | P02 | Technical assessment | 5
569 | P03 | Commercial assessment | 7
569 | P04 | Approval and close | 3
570 | P01 | Submission review | 4
570 | P02 | Technical assessment | 8
570 | P03 | Commercial assessment | 6
570 | P04 | Approval and close | 4
571 | P01 | Submission review | 4
571 | P02 | Technical assessment | 7
571 | P03 | Commercial assessment | 11
571 | P04 | Approval and close | 4
572 | P01 | Submission review | 4
572 | P02 | Technical assessment | 6
572 | P03 | Commercial assessment | 6
572 | P04 | Approval and close | 2
573 | P01 | Submission review | 6
573 | P02 | Technical assessment | 8
573 | P03 | Commercial assessment | 5
573 | P04 | Approval and close | 4
574 | P01 | Submission review | 4
574 | P02 | Technical assessment | 6
574 | P03 | Commercial assessment | 7
574 | P04 | Approval and close | 5
575 | P01 | Submission review | 5
575 | P02 | Technical assessment | 7
575 | P03 | Commercial assessment | 9
575 | P04 | Approval and close | 4
576 | P01 | Submission review | 6
576 | P02 | Technical assessment | 5
576 | P03 | Commercial assessment | 7
576 | P04 | Approval and close | 2
577 | P01 | Submission review | 5
577 | P02 | Technical assessment | 5
577 | P03 | Commercial assessment | 3
577 | P04 | Approval and close | 3
578 | P01 | Submission review | 4
578 | P02 | Technical assessment | 6
578 | P03 | Commercial assessment | 6
578 | P04 | Approval and close | 3
579 | P01 | Submission review | 4
579 | P02 | Technical assessment | 7
579 | P03 | Commercial assessment | 6
579 | P04 | Approval and close | 5
580 | P01 | Submission review | 4
580 | P02 | Technical assessment | 6
580 | P03 | Commercial assessment | 10
580 | P04 | Approval and close | 4
581 | P01 | Submission review | 5
581 | P02 | Technical assessment | 6
581 | P03 | Commercial assessment | 8
581 | P04 | Approval and close | 3
582 | P01 | Submission review | 4
582 | P02 | Technical assessment | 5
582 | P03 | Commercial assessment | 8
582 | P04 | Approval and close | 3
583 | P01 | Submission review | 6
583 | P02 | Technical assessment | 6
583 | P03 | Commercial assessment | 7
583 | P04 | Approval and close | 3
584 | P01 | Submission review | 4
584 | P02 | Technical assessment | 7
584 | P03 | Commercial assessment | 4
584 | P04 | Approval and close | 4
585 | P01 | Submission review | 7
585 | P02 | Technical assessment | 7
585 | P03 | Commercial assessment | 7
585 | P04 | Approval and close | 3
586 | P01 | Submission review | 6
586 | P02 | Technical assessment | 7
586 | P03 | Commercial assessment | 6
586 | P04 | Approval and close | 4
587 | P01 | Submission review | 5
587 | P02 | Technical assessment | 6
587 | P03 | Commercial assessment | 5
587 | P04 | Approval and close | 3
588 | P01 | Submission review | 6
588 | P02 | Technical assessment | 6
588 | P03 | Commercial assessment | 6
588 | P04 | Approval and close | 2
589 | P01 | Submission review | 4
589 | P02 | Technical assessment | 4
589 | P03 | Commercial assessment | 6
589 | P04 | Approval and close | 2
590 | P01 | Submission review | 4
590 | P02 | Technical assessment | 5
590 | P03 | Commercial assessment | 6
590 | P04 | Approval and close | 3
591 | P01 | Submission review | 4
591 | P02 | Technical assessment | 4
591 | P03 | Commercial assessment | 3
591 | P04 | Approval and close | 3
592 | P01 | Submission review | 5
592 | P02 | Technical assessment | 5
592 | P03 | Commercial assessment | 6
592 | P04 | Approval and close | 4
593 | P01 | Submission review | 5
593 | P02 | Technical assessment | 5
593 | P03 | Commercial assessment | 9
593 | P04 | Approval and close | 3
594 | P01 | Submission review | 5
594 | P02 | Technical assessment | 8
594 | P03 | Commercial assessment | 10
594 | P04 | Approval and close | 4
595 | P01 | Submission review | 6
595 | P02 | Technical assessment | 6
595 | P03 | Commercial assessment | 4
595 | P04 | Approval and close | 3
596 | P01 | Submission review | 3
596 | P02 | Technical assessment | 5
596 | P03 | Commercial assessment | 8
596 | P04 | Approval and close | 4
597 | P01 | Submission review | 5
597 | P02 | Technical assessment | 6
597 | P03 | Commercial assessment | 6
597 | P04 | Approval and close | 4
598 | P01 | Submission review | 6
598 | P02 | Technical assessment | 5
598 | P03 | Commercial assessment | 7
598 | P04 | Approval and close | 4
599 | P01 | Submission review | 5
599 | P02 | Technical assessment | 5
599 | P03 | Commercial assessment | 5
599 | P04 | Approval and close | 5
600 | P01 | Submission review | 7
600 | P02 | Technical assessment | 7
600 | P03 | Commercial assessment | 8
600 | P04 | Approval and close | 3
601 | P01 | Submission review | 5
601 | P02 | Technical assessment | 7
601 | P03 | Commercial assessment | 6
601 | P04 | Approval and close | 3
602 | P01 | Submission review | 4
602 | P02 | Technical assessment | 4
602 | P03 | Commercial assessment | 4
602 | P04 | Approval and close | 5
603 | P01 | Submission review | 6
603 | P02 | Technical assessment | 6
603 | P03 | Commercial assessment | 5
603 | P04 | Approval and close | 4
604 | P01 | Submission review | 5
604 | P02 | Technical assessment | 4
604 | P03 | Commercial assessment | 7
604 | P04 | Approval and close | 4
605 | P01 | Submission review | 6
605 | P02 | Technical assessment | 5
605 | P03 | Commercial assessment | 9
605 | P04 | Approval and close | 3
606 | P01 | Submission review | 5
606 | P02 | Technical assessment | 6
606 | P03 | Commercial assessment | 6
606 | P04 | Approval and close | 2
607 | P01 | Submission review | 4
607 | P02 | Technical assessment | 7
607 | P03 | Commercial assessment | 7
607 | P04 | Approval and close | 5
608 | P01 | Submission review | 6
608 | P02 | Technical assessment | 5
608 | P03 | Commercial assessment | 9
608 | P04 | Approval and close | 4
609 | P01 | Submission review | 5
609 | P02 | Technical assessment | 4
609 | P03 | Commercial assessment | 8
609 | P04 | Approval and close | 3
610 | P01 | Submission review | 4
610 | P02 | Technical assessment | 7
610 | P03 | Commercial assessment | 6
610 | P04 | Approval and close | 4
611 | P01 | Submission review | 6
611 | P02 | Technical assessment | 5
611 | P03 | Commercial assessment | 7
611 | P04 | Approval and close | 4
612 | P01 | Submission review | 4
612 | P02 | Technical assessment | 6
612 | P03 | Commercial assessment | 4
612 | P04 | Approval and close | 3
613 | P01 | Submission review | 3
613 | P02 | Technical assessment | 5
613 | P03 | Commercial assessment | 9
613 | P04 | Approval and close | 4
614 | P01 | Submission review | 4
614 | P02 | Technical assessment | 5
614 | P03 | Commercial assessment | 4
614 | P04 | Approval and close | 4
615 | P01 | Submission review | 5
615 | P02 | Technical assessment | 6
615 | P03 | Commercial assessment | 9
615 | P04 | Approval and close | 3
616 | P01 | Submission review | 4
616 | P02 | Technical assessment | 5
616 | P03 | Commercial assessment | 8
616 | P04 | Approval and close | 4
617 | P01 | Submission review | 5
617 | P02 | Technical assessment | 5
617 | P03 | Commercial assessment | 6
617 | P04 | Approval and close | 3
618 | P01 | Submission review | 5
618 | P02 | Technical assessment | 8
618 | P03 | Commercial assessment | 8
618 | P04 | Approval and close | 3
619 | P01 | Submission review | 5
619 | P02 | Technical assessment | 5
619 | P03 | Commercial assessment | 5
619 | P04 | Approval and close | 3
620 | P01 | Submission review | 5
620 | P02 | Technical assessment | 6
620 | P03 | Commercial assessment | 7
620 | P04 | Approval and close | 4
621 | P01 | Submission review | 3
621 | P02 | Technical assessment | 5
621 | P03 | Commercial assessment | 7
621 | P04 | Approval and close | 3
622 | P01 | Submission review | 4
622 | P02 | Technical assessment | 5
622 | P03 | Commercial assessment | 10
622 | P04 | Approval and close | 2
623 | P01 | Submission review | 6
623 | P02 | Technical assessment | 8
623 | P03 | Commercial assessment | 9
623 | P04 | Approval and close | 3
624 | P01 | Submission review | 4
624 | P02 | Technical assessment | 5
624 | P03 | Commercial assessment | 8
624 | P04 | Approval and close | 3
625 | P01 | Submission review | 5
625 | P02 | Technical assessment | 5
625 | P03 | Commercial assessment | 6
625 | P04 | Approval and close | 3
626 | P01 | Submission review | 6
626 | P02 | Technical assessment | 6
626 | P03 | Commercial assessment | 7
626 | P04 | Approval and close | 4
627 | P01 | Submission review | 5
627 | P02 | Technical assessment | 5
627 | P03 | Commercial assessment | 6
627 | P04 | Approval and close | 5
628 | P01 | Submission review | 4
628 | P02 | Technical assessment | 6
628 | P03 | Commercial assessment | 7
628 | P04 | Approval and close | 4
629 | P01 | Submission review | 5
629 | P02 | Technical assessment | 7
629 | P03 | Commercial assessment | 9
629 | P04 | Approval and close | 3
630 | P01 | Submission review | 3
630 | P02 | Technical assessment | 4
630 | P03 | Commercial assessment | 7
630 | P04 | Approval and close | 5
631 | P01 | Submission review | 4
631 | P02 | Technical assessment | 8
631 | P03 | Commercial assessment | 8
631 | P04 | Approval and close | 3
632 | P01 | Submission review | 4
632 | P02 | Technical assessment | 7
632 | P03 | Commercial assessment | 6
632 | P04 | Approval and close | 4
633 | P01 | Submission review | 4
633 | P02 | Technical assessment | 6
633 | P03 | Commercial assessment | 6
633 | P04 | Approval and close | 4
634 | P01 | Submission review | 3
634 | P02 | Technical assessment | 8
634 | P03 | Commercial assessment | 7
634 | P04 | Approval and close | 4
635 | P01 | Submission review | 4
635 | P02 | Technical assessment | 6
635 | P03 | Commercial assessment | 8
635 | P04 | Approval and close | 3
636 | P01 | Submission review | 6
636 | P02 | Technical assessment | 7
636 | P03 | Commercial assessment | 8
636 | P04 | Approval and close | 2
637 | P01 | Submission review | 5
637 | P02 | Technical assessment | 5
637 | P03 | Commercial assessment | 10
637 | P04 | Approval and close | 3
638 | P01 | Submission review | 4
638 | P02 | Technical assessment | 6
638 | P03 | Commercial assessment | 6
638 | P04 | Approval and close | 4
639 | P01 | Submission review | 3
639 | P02 | Technical assessment | 6
639 | P03 | Commercial assessment | 5
639 | P04 | Approval and close | 4
640 | P01 | Submission review | 5
640 | P02 | Technical assessment | 5
640 | P03 | Commercial assessment | 8
640 | P04 | Approval and close | 4
641 | P01 | Submission review | 4
641 | P02 | Technical assessment | 6
641 | P03 | Commercial assessment | 5
641 | P04 | Approval and close | 5
642 | P01 | Submission review | 4
642 | P02 | Technical assessment | 6
642 | P03 | Commercial assessment | 8
642 | P04 | Approval and close | 3
643 | P01 | Submission review | 3
643 | P02 | Technical assessment | 5
643 | P03 | Commercial assessment | 4
643 | P04 | Approval and close | 2
644 | P01 | Submission review | 6
644 | P02 | Technical assessment | 5
644 | P03 | Commercial assessment | 6
644 | P04 | Approval and close | 3
645 | P01 | Submission review | 4
645 | P02 | Technical assessment | 6
645 | P03 | Commercial assessment | 8
645 | P04 | Approval and close | 3
646 | P01 | Submission review | 5
646 | P02 | Technical assessment | 6
646 | P03 | Commercial assessment | 4
646 | P04 | Approval and close | 4
647 | P01 | Submission review | 5
647 | P02 | Technical assessment | 4
647 | P03 | Commercial assessment | 9
647 | P04 | Approval and close | 2
648 | P01 | Submission review | 4
648 | P02 | Technical assessment | 6
648 | P03 | Commercial assessment | 7
648 | P04 | Approval and close | 3
649 | P01 | Submission review | 4
649 | P02 | Technical assessment | 6
649 | P03 | Commercial assessment | 6
649 | P04 | Approval and close | 3
650 | P01 | Submission review | 6
650 | P02 | Technical assessment | 8
650 | P03 | Commercial assessment | 9
650 | P04 | Approval and close | 3
651 | P01 | Submission review | 5
651 | P02 | Technical assessment | 5
651 | P03 | Commercial assessment | 6
651 | P04 | Approval and close | 4
652 | P01 | Submission review | 4
652 | P02 | Technical assessment | 7
652 | P03 | Commercial assessment | 5
652 | P04 | Approval and close | 4
653 | P01 | Submission review | 4
653 | P02 | Technical assessment | 7
653 | P03 | Commercial assessment | 6
653 | P04 | Approval and close | 4
654 | P01 | Submission review | 4
654 | P02 | Technical assessment | 6
654 | P03 | Commercial assessment | 5
654 | P04 | Approval and close | 4
655 | P01 | Submission review | 6
655 | P02 | Technical assessment | 5
655 | P03 | Commercial assessment | 12
655 | P04 | Approval and close | 3
656 | P01 | Submission review | 5
656 | P02 | Technical assessment | 5
656 | P03 | Commercial assessment | 8
656 | P04 | Approval and close | 4
657 | P01 | Submission review | 6
657 | P02 | Technical assessment | 5
657 | P03 | Commercial assessment | 4
657 | P04 | Approval and close | 3
658 | P01 | Submission review | 4
658 | P02 | Technical assessment | 5
658 | P03 | Commercial assessment | 4
658 | P04 | Approval and close | 5
659 | P01 | Submission review | 4
659 | P02 | Technical assessment | 6
659 | P03 | Commercial assessment | 5
659 | P04 | Approval and close | 3
660 | P01 | Submission review | 4
660 | P02 | Technical assessment | 6
660 | P03 | Commercial assessment | 8
660 | P04 | Approval and close | 4
661 | P01 | Submission review | 5
661 | P02 | Technical assessment | 6
661 | P03 | Commercial assessment | 10
661 | P04 | Approval and close | 3
662 | P01 | Submission review | 3
662 | P02 | Technical assessment | 4
662 | P03 | Commercial assessment | 11
662 | P04 | Approval and close | 5
663 | P01 | Submission review | 3
663 | P02 | Technical assessment | 4
663 | P03 | Commercial assessment | 5
663 | P04 | Approval and close | 4
664 | P01 | Submission review | 3
664 | P02 | Technical assessment | 5
664 | P03 | Commercial assessment | 8
664 | P04 | Approval and close | 4
665 | P01 | Submission review | 3
665 | P02 | Technical assessment | 9
665 | P03 | Commercial assessment | 4
665 | P04 | Approval and close | 2
666 | P01 | Submission review | 5
666 | P02 | Technical assessment | 6
666 | P03 | Commercial assessment | 4
666 | P04 | Approval and close | 5
667 | P01 | Submission review | 5
667 | P02 | Technical assessment | 5
667 | P03 | Commercial assessment | 6
667 | P04 | Approval and close | 4
668 | P01 | Submission review | 5
668 | P02 | Technical assessment | 7
668 | P03 | Commercial assessment | 6
668 | P04 | Approval and close | 3
669 | P01 | Submission review | 5
669 | P02 | Technical assessment | 7
669 | P03 | Commercial assessment | 6
669 | P04 | Approval and close | 3
670 | P01 | Submission review | 5
670 | P02 | Technical assessment | 7
670 | P03 | Commercial assessment | 6
670 | P04 | Approval and close | 3
671 | P01 | Submission review | 5
671 | P02 | Technical assessment | 8
671 | P03 | Commercial assessment | 9
671 | P04 | Approval and close | 3
672 | P01 | Submission review | 5
672 | P02 | Technical assessment | 6
672 | P03 | Commercial assessment | 6
672 | P04 | Approval and close | 3
673 | P01 | Submission review | 4
673 | P02 | Technical assessment | 4
673 | P03 | Commercial assessment | 9
673 | P04 | Approval and close | 3
674 | P01 | Submission review | 5
674 | P02 | Technical assessment | 6
674 | P03 | Commercial assessment | 6
674 | P04 | Approval and close | 5
675 | P01 | Submission review | 4
675 | P02 | Technical assessment | 4
675 | P03 | Commercial assessment | 5
675 | P04 | Approval and close | 3
676 | P01 | Submission review | 3
676 | P02 | Technical assessment | 5
676 | P03 | Commercial assessment | 10
676 | P04 | Approval and close | 4
677 | P01 | Submission review | 4
677 | P02 | Technical assessment | 9
677 | P03 | Commercial assessment | 6
677 | P04 | Approval and close | 3
678 | P01 | Submission review | 3
678 | P02 | Technical assessment | 4
678 | P03 | Commercial assessment | 6
678 | P04 | Approval and close | 3
679 | P01 | Submission review | 5
679 | P02 | Technical assessment | 6
679 | P03 | Commercial assessment | 4
679 | P04 | Approval and close | 3
680 | P01 | Submission review | 6
680 | P02 | Technical assessment | 6
680 | P03 | Commercial assessment | 6
680 | P04 | Approval and close | 4
681 | P01 | Submission review | 5
681 | P02 | Technical assessment | 6
681 | P03 | Commercial assessment | 4
681 | P04 | Approval and close | 4
682 | P01 | Submission review | 5
682 | P02 | Technical assessment | 7
682 | P03 | Commercial assessment | 10
682 | P04 | Approval and close | 3
683 | P01 | Submission review | 4
683 | P02 | Technical assessment | 7
683 | P03 | Commercial assessment | 11
683 | P04 | Approval and close | 3
684 | P01 | Submission review | 6
684 | P02 | Technical assessment | 6
684 | P03 | Commercial assessment | 6
684 | P04 | Approval and close | 5
685 | P01 | Submission review | 6
685 | P02 | Technical assessment | 7
685 | P03 | Commercial assessment | 7
685 | P04 | Approval and close | 3
686 | P01 | Submission review | 4
686 | P02 | Technical assessment | 7
686 | P03 | Commercial assessment | 5
686 | P04 | Approval and close | 3
687 | P01 | Submission review | 4
687 | P02 | Technical assessment | 6
687 | P03 | Commercial assessment | 6
687 | P04 | Approval and close | 4
688 | P01 | Submission review | 4
688 | P02 | Technical assessment | 5
688 | P03 | Commercial assessment | 5
688 | P04 | Approval and close | 2
689 | P01 | Submission review | 4
689 | P02 | Technical assessment | 7
689 | P03 | Commercial assessment | 5
689 | P04 | Approval and close | 4
690 | P01 | Submission review | 5
690 | P02 | Technical assessment | 5
690 | P03 | Commercial assessment | 4
690 | P04 | Approval and close | 4
691 | P01 | Submission review | 6
691 | P02 | Technical assessment | 5
691 | P03 | Commercial assessment | 9
691 | P04 | Approval and close | 4
692 | P01 | Submission review | 6
692 | P02 | Technical assessment | 6
692 | P03 | Commercial assessment | 7
692 | P04 | Approval and close | 4
693 | P01 | Submission review | 5
693 | P02 | Technical assessment | 5
693 | P03 | Commercial assessment | 11
693 | P04 | Approval and close | 3
694 | P01 | Submission review | 4
694 | P02 | Technical assessment | 6
694 | P03 | Commercial assessment | 6
694 | P04 | Approval and close | 3
695 | P01 | Submission review | 7
695 | P02 | Technical assessment | 6
695 | P03 | Commercial assessment | 9
695 | P04 | Approval and close | 3
696 | P01 | Submission review | 5
696 | P02 | Technical assessment | 4
696 | P03 | Commercial assessment | 10
696 | P04 | Approval and close | 2
697 | P01 | Submission review | 4
697 | P02 | Technical assessment | 5
697 | P03 | Commercial assessment | 7
697 | P04 | Approval and close | 3
698 | P01 | Submission review | 4
698 | P02 | Technical assessment | 4
698 | P03 | Commercial assessment | 9
698 | P04 | Approval and close | 3
699 | P01 | Submission review | 3
699 | P02 | Technical assessment | 5
699 | P03 | Commercial assessment | 7
699 | P04 | Approval and close | 3
700 | P01 | Submission review | 5
700 | P02 | Technical assessment | 6
700 | P03 | Commercial assessment | 7
700 | P04 | Approval and close | 3
701 | P01 | Submission review | 5
701 | P02 | Technical assessment | 6
701 | P03 | Commercial assessment | 6
701 | P04 | Approval and close | 4
702 | P01 | Submission review | 6
702 | P02 | Technical assessment | 8
702 | P03 | Commercial assessment | 9
702 | P04 | Approval and close | 3
703 | P01 | Submission review | 6
703 | P02 | Technical assessment | 6
703 | P03 | Commercial assessment | 6
703 | P04 | Approval and close | 4
704 | P01 | Submission review | 4
704 | P02 | Technical assessment | 5
704 | P03 | Commercial assessment | 3
704 | P04 | Approval and close | 3
705 | P01 | Submission review | 4
705 | P02 | Technical assessment | 5
705 | P03 | Commercial assessment | 5
705 | P04 | Approval and close | 4
706 | P01 | Submission review | 4
706 | P02 | Technical assessment | 7
706 | P03 | Commercial assessment | 5
706 | P04 | Approval and close | 4
707 | P01 | Submission review | 4
707 | P02 | Technical assessment | 6
707 | P03 | Commercial assessment | 9
707 | P04 | Approval and close | 4
708 | P01 | Submission review | 4
708 | P02 | Technical assessment | 5
708 | P03 | Commercial assessment | 4
708 | P04 | Approval and close | 4
709 | P01 | Submission review | 4
709 | P02 | Technical assessment | 5
709 | P03 | Commercial assessment | 5
709 | P04 | Approval and close | 5
710 | P01 | Submission review | 5
710 | P02 | Technical assessment | 7
710 | P03 | Commercial assessment | 8
710 | P04 | Approval and close | 3
711 | P01 | Submission review | 4
711 | P02 | Technical assessment | 4
711 | P03 | Commercial assessment | 5
711 | P04 | Approval and close | 3
712 | P01 | Submission review | 6
712 | P02 | Technical assessment | 5
712 | P03 | Commercial assessment | 6
712 | P04 | Approval and close | 4
713 | P01 | Submission review | 4
713 | P02 | Technical assessment | 6
713 | P03 | Commercial assessment | 8
713 | P04 | Approval and close | 4
714 | P01 | Submission review | 5
714 | P02 | Technical assessment | 6
714 | P03 | Commercial assessment | 6
714 | P04 | Approval and close | 4
715 | P01 | Submission review | 3
715 | P02 | Technical assessment | 5
715 | P03 | Commercial assessment | 7
715 | P04 | Approval and close | 2
716 | P01 | Submission review | 5
716 | P02 | Technical assessment | 6
716 | P03 | Commercial assessment | 7
716 | P04 | Approval and close | 2
717 | P01 | Submission review | 6
717 | P02 | Technical assessment | 5
717 | P03 | Commercial assessment | 3
717 | P04 | Approval and close | 2
718 | P01 | Submission review | 6
718 | P02 | Technical assessment | 5
718 | P03 | Commercial assessment | 7
718 | P04 | Approval and close | 4
719 | P01 | Submission review | 4
719 | P02 | Technical assessment | 7
719 | P03 | Commercial assessment | 6
719 | P04 | Approval and close | 3
720 | P01 | Submission review | 4
720 | P02 | Technical assessment | 5
720 | P03 | Commercial assessment | 3
720 | P04 | Approval and close | 5
721 | P01 | Submission review | 4
721 | P02 | Technical assessment | 6
721 | P03 | Commercial assessment | 6
721 | P04 | Approval and close | 4
722 | P01 | Submission review | 4
722 | P02 | Technical assessment | 6
722 | P03 | Commercial assessment | 8
722 | P04 | Approval and close | 4
723 | P01 | Submission review | 6
723 | P02 | Technical assessment | 7
723 | P03 | Commercial assessment | 4
723 | P04 | Approval and close | 3
724 | P01 | Submission review | 4
724 | P02 | Technical assessment | 4
724 | P03 | Commercial assessment | 5
724 | P04 | Approval and close | 4
725 | P01 | Submission review | 3
725 | P02 | Technical assessment | 7
725 | P03 | Commercial assessment | 6
725 | P04 | Approval and close | 4
726 | P01 | Submission review | 4
726 | P02 | Technical assessment | 7
726 | P03 | Commercial assessment | 7
726 | P04 | Approval and close | 3
727 | P01 | Submission review | 6
727 | P02 | Technical assessment | 7
727 | P03 | Commercial assessment | 6
727 | P04 | Approval and close | 4
728 | P01 | Submission review | 4
728 | P02 | Technical assessment | 7
728 | P03 | Commercial assessment | 5
728 | P04 | Approval and close | 3
729 | P01 | Submission review | 5
729 | P02 | Technical assessment | 5
729 | P03 | Commercial assessment | 5
729 | P04 | Approval and close | 4
730 | P01 | Submission review | 5
730 | P02 | Technical assessment | 8
730 | P03 | Commercial assessment | 5
730 | P04 | Approval and close | 5
731 | P01 | Submission review | 5
731 | P02 | Technical assessment | 4
731 | P03 | Commercial assessment | 4
731 | P04 | Approval and close | 3
732 | P01 | Submission review | 6
732 | P02 | Technical assessment | 6
732 | P03 | Commercial assessment | 10
732 | P04 | Approval and close | 4
733 | P01 | Submission review | 4
733 | P02 | Technical assessment | 5
733 | P03 | Commercial assessment | 5
733 | P04 | Approval and close | 2
734 | P01 | Submission review | 4
734 | P02 | Technical assessment | 5
734 | P03 | Commercial assessment | 10
734 | P04 | Approval and close | 3
735 | P01 | Submission review | 5
735 | P02 | Technical assessment | 7
735 | P03 | Commercial assessment | 9
735 | P04 | Approval and close | 2
736 | P01 | Submission review | 4
736 | P02 | Technical assessment | 6
736 | P03 | Commercial assessment | 4
736 | P04 | Approval and close | 3
737 | P01 | Submission review | 6
737 | P02 | Technical assessment | 7
737 | P03 | Commercial assessment | 5
737 | P04 | Approval and close | 4
738 | P01 | Submission review | 5
738 | P02 | Technical assessment | 5
738 | P03 | Commercial assessment | 5
738 | P04 | Approval and close | 3
739 | P01 | Submission review | 3
739 | P02 | Technical assessment | 5
739 | P03 | Commercial assessment | 9
739 | P04 | Approval and close | 4
740 | P01 | Submission review | 7
740 | P02 | Technical assessment | 6
740 | P03 | Commercial assessment | 4
740 | P04 | Approval and close | 4
741 | P01 | Submission review | 4
741 | P02 | Technical assessment | 4
741 | P03 | Commercial assessment | 8
741 | P04 | Approval and close | 5
742 | P01 | Submission review | 4
742 | P02 | Technical assessment | 7
742 | P03 | Commercial assessment | 6
742 | P04 | Approval and close | 4
743 | P01 | Submission review | 4
743 | P02 | Technical assessment | 6
743 | P03 | Commercial assessment | 7
743 | P04 | Approval and close | 2
744 | P01 | Submission review | 3
744 | P02 | Technical assessment | 5
744 | P03 | Commercial assessment | 9
744 | P04 | Approval and close | 4
745 | P01 | Submission review | 5
745 | P02 | Technical assessment | 7
745 | P03 | Commercial assessment | 7
745 | P04 | Approval and close | 4
746 | P01 | Submission review | 4
746 | P02 | Technical assessment | 5
746 | P03 | Commercial assessment | 5
746 | P04 | Approval and close | 2
747 | P01 | Submission review | 4
747 | P02 | Technical assessment | 7
747 | P03 | Commercial assessment | 9
747 | P04 | Approval and close | 4
748 | P01 | Submission review | 5
748 | P02 | Technical assessment | 4
748 | P03 | Commercial assessment | 6
748 | P04 | Approval and close | 3
749 | P01 | Submission review | 4
749 | P02 | Technical assessment | 6
749 | P03 | Commercial assessment | 5
749 | P04 | Approval and close | 3
750 | P01 | Submission review | 4
750 | P02 | Technical assessment | 5
750 | P03 | Commercial assessment | 6
750 | P04 | Approval and close | 2
751 | P01 | Submission review | 3
751 | P02 | Technical assessment | 5
751 | P03 | Commercial assessment | 6
751 | P04 | Approval and close | 4
752 | P01 | Submission review | 5
752 | P02 | Technical assessment | 5
752 | P03 | Commercial assessment | 4
752 | P04 | Approval and close | 5
753 | P01 | Submission review | 5
753 | P02 | Technical assessment | 7
753 | P03 | Commercial assessment | 6
753 | P04 | Approval and close | 3
754 | P01 | Submission review | 4
754 | P02 | Technical assessment | 6
754 | P03 | Commercial assessment | 5
754 | P04 | Approval and close | 4
755 | P01 | Submission review | 6
755 | P02 | Technical assessment | 5
755 | P03 | Commercial assessment | 9
755 | P04 | Approval and close | 3
756 | P01 | Submission review | 4
756 | P02 | Technical assessment | 4
756 | P03 | Commercial assessment | 4
756 | P04 | Approval and close | 3
757 | P01 | Submission review | 3
757 | P02 | Technical assessment | 4
757 | P03 | Commercial assessment | 5
757 | P04 | Approval and close | 3
758 | P01 | Submission review | 5
758 | P02 | Technical assessment | 5
758 | P03 | Commercial assessment | 4
758 | P04 | Approval and close | 3
759 | P01 | Submission review | 6
759 | P02 | Technical assessment | 7
759 | P03 | Commercial assessment | 7
759 | P04 | Approval and close | 4
760 | P01 | Submission review | 4
760 | P02 | Technical assessment | 5
760 | P03 | Commercial assessment | 4
760 | P04 | Approval and close | 3
761 | P01 | Submission review | 5
761 | P02 | Technical assessment | 6
761 | P03 | Commercial assessment | 5
761 | P04 | Approval and close | 2
762 | P01 | Submission review | 3
762 | P02 | Technical assessment | 8
762 | P03 | Commercial assessment | 10
762 | P04 | Approval and close | 2
763 | P01 | Submission review | 4
763 | P02 | Technical assessment | 7
763 | P03 | Commercial assessment | 8
763 | P04 | Approval and close | 2
764 | P01 | Submission review | 4
764 | P02 | Technical assessment | 6
764 | P03 | Commercial assessment | 7
764 | P04 | Approval and close | 2
765 | P01 | Submission review | 4
765 | P02 | Technical assessment | 7
765 | P03 | Commercial assessment | 7
765 | P04 | Approval and close | 4
766 | P01 | Submission review | 5
766 | P02 | Technical assessment | 7
766 | P03 | Commercial assessment | 6
766 | P04 | Approval and close | 4
767 | P01 | Submission review | 5
767 | P02 | Technical assessment | 4
767 | P03 | Commercial assessment | 8
767 | P04 | Approval and close | 4
768 | P01 | Submission review | 5
768 | P02 | Technical assessment | 7
768 | P03 | Commercial assessment | 9
768 | P04 | Approval and close | 3
769 | P01 | Submission review | 5
769 | P02 | Technical assessment | 4
769 | P03 | Commercial assessment | 6
769 | P04 | Approval and close | 3
770 | P01 | Submission review | 3
770 | P02 | Technical assessment | 5
770 | P03 | Commercial assessment | 8
770 | P04 | Approval and close | 3
771 | P01 | Submission review | 5
771 | P02 | Technical assessment | 6
771 | P03 | Commercial assessment | 5
771 | P04 | Approval and close | 2
772 | P01 | Submission review | 4
772 | P02 | Technical assessment | 6
772 | P03 | Commercial assessment | 7
772 | P04 | Approval and close | 3
773 | P01 | Submission review | 4
773 | P02 | Technical assessment | 5
773 | P03 | Commercial assessment | 6
773 | P04 | Approval and close | 3
774 | P01 | Submission review | 4
774 | P02 | Technical assessment | 6
774 | P03 | Commercial assessment | 5
774 | P04 | Approval and close | 4
775 | P01 | Submission review | 5
775 | P02 | Technical assessment | 7
775 | P03 | Commercial assessment | 11
775 | P04 | Approval and close | 3
776 | P01 | Submission review | 4
776 | P02 | Technical assessment | 6
776 | P03 | Commercial assessment | 8
776 | P04 | Approval and close | 3
777 | P01 | Submission review | 6
777 | P02 | Technical assessment | 5
777 | P03 | Commercial assessment | 7
777 | P04 | Approval and close | 4
778 | P01 | Submission review | 5
778 | P02 | Technical assessment | 5
778 | P03 | Commercial assessment | 10
778 | P04 | Approval and close | 3
779 | P01 | Submission review | 4
779 | P02 | Technical assessment | 5
779 | P03 | Commercial assessment | 6
779 | P04 | Approval and close | 5
780 | P01 | Submission review | 4
780 | P02 | Technical assessment | 5
780 | P03 | Commercial assessment | 6
780 | P04 | Approval and close | 4
781 | P01 | Submission review | 4
781 | P02 | Technical assessment | 4
781 | P03 | Commercial assessment | 9
781 | P04 | Approval and close | 2
782 | P01 | Submission review | 3
782 | P02 | Technical assessment | 4
782 | P03 | Commercial assessment | 11
782 | P04 | Approval and close | 4
783 | P01 | Submission review | 3
783 | P02 | Technical assessment | 4
783 | P03 | Commercial assessment | 7
783 | P04 | Approval and close | 3
784 | P01 | Submission review | 5
784 | P02 | Technical assessment | 7
784 | P03 | Commercial assessment | 8
784 | P04 | Approval and close | 5
785 | P01 | Submission review | 6
785 | P02 | Technical assessment | 5
785 | P03 | Commercial assessment | 6
785 | P04 | Approval and close | 5
786 | P01 | Submission review | 3
786 | P02 | Technical assessment | 7
786 | P03 | Commercial assessment | 8
786 | P04 | Approval and close | 4
787 | P01 | Submission review | 4
787 | P02 | Technical assessment | 6
787 | P03 | Commercial assessment | 6
787 | P04 | Approval and close | 4
788 | P01 | Submission review | 3
788 | P02 | Technical assessment | 4
788 | P03 | Commercial assessment | 4
788 | P04 | Approval and close | 4
789 | P01 | Submission review | 3
789 | P02 | Technical assessment | 5
789 | P03 | Commercial assessment | 6
789 | P04 | Approval and close | 3
790 | P01 | Submission review | 6
790 | P02 | Technical assessment | 6
790 | P03 | Commercial assessment | 7
790 | P04 | Approval and close | 4
791 | P01 | Submission review | 5
791 | P02 | Technical assessment | 8
791 | P03 | Commercial assessment | 6
791 | P04 | Approval and close | 3
792 | P01 | Submission review | 3
792 | P02 | Technical assessment | 5
792 | P03 | Commercial assessment | 8
792 | P04 | Approval and close | 4
793 | P01 | Submission review | 5
793 | P02 | Technical assessment | 4
793 | P03 | Commercial assessment | 7
793 | P04 | Approval and close | 4
794 | P01 | Submission review | 4
794 | P02 | Technical assessment | 6
794 | P03 | Commercial assessment | 5
794 | P04 | Approval and close | 4
795 | P01 | Submission review | 5
795 | P02 | Technical assessment | 5
795 | P03 | Commercial assessment | 4
795 | P04 | Approval and close | 2
796 | P01 | Submission review | 4
796 | P02 | Technical assessment | 6
796 | P03 | Commercial assessment | 5
796 | P04 | Approval and close | 4
797 | P01 | Submission review | 6
797 | P02 | Technical assessment | 6
797 | P03 | Commercial assessment | 5
797 | P04 | Approval and close | 3
798 | P01 | Submission review | 4
798 | P02 | Technical assessment | 8
798 | P03 | Commercial assessment | 5
798 | P04 | Approval and close | 4
799 | P01 | Submission review | 3
799 | P02 | Technical assessment | 4
799 | P03 | Commercial assessment | 3
799 | P04 | Approval and close | 4
800 | P01 | Submission review | 5
800 | P02 | Technical assessment | 4
800 | P03 | Commercial assessment | 6
800 | P04 | Approval and close | 4
801 | P01 | Submission review | 4
801 | P02 | Technical assessment | 6
801 | P03 | Commercial assessment | 10
801 | P04 | Approval and close | 3
802 | P01 | Submission review | 4
802 | P02 | Technical assessment | 7
802 | P03 | Commercial assessment | 6
802 | P04 | Approval and close | 4
803 | P01 | Submission review | 5
803 | P02 | Technical assessment | 4
803 | P03 | Commercial assessment | 7
803 | P04 | Approval and close | 4
804 | P01 | Submission review | 4
804 | P02 | Technical assessment | 5
804 | P03 | Commercial assessment | 7
804 | P04 | Approval and close | 4
805 | P01 | Submission review | 5
805 | P02 | Technical assessment | 5
805 | P03 | Commercial assessment | 4
805 | P04 | Approval and close | 3
806 | P01 | Submission review | 7
806 | P02 | Technical assessment | 7
806 | P03 | Commercial assessment | 6
806 | P04 | Approval and close | 4
807 | P01 | Submission review | 6
807 | P02 | Technical assessment | 7
807 | P03 | Commercial assessment | 9
807 | P04 | Approval and close | 3
808 | P01 | Submission review | 4
808 | P02 | Technical assessment | 4
808 | P03 | Commercial assessment | 7
808 | P04 | Approval and close | 4
809 | P01 | Submission review | 5
809 | P02 | Technical assessment | 6
809 | P03 | Commercial assessment | 5
809 | P04 | Approval and close | 3
810 | P01 | Submission review | 5
810 | P02 | Technical assessment | 6
810 | P03 | Commercial assessment | 6
810 | P04 | Approval and close | 5
811 | P01 | Submission review | 4
811 | P02 | Technical assessment | 7
811 | P03 | Commercial assessment | 7
811 | P04 | Approval and close | 4
812 | P01 | Submission review | 5
812 | P02 | Technical assessment | 5
812 | P03 | Commercial assessment | 5
812 | P04 | Approval and close | 4
813 | P01 | Submission review | 6
813 | P02 | Technical assessment | 6
813 | P03 | Commercial assessment | 9
813 | P04 | Approval and close | 4
814 | P01 | Submission review | 5
814 | P02 | Technical assessment | 6
814 | P03 | Commercial assessment | 7
814 | P04 | Approval and close | 3
815 | P01 | Submission review | 4
815 | P02 | Technical assessment | 4
815 | P03 | Commercial assessment | 9
815 | P04 | Approval and close | 4
816 | P01 | Submission review | 4
816 | P02 | Technical assessment | 8
816 | P03 | Commercial assessment | 8
816 | P04 | Approval and close | 2
817 | P01 | Submission review | 5
817 | P02 | Technical assessment | 4
817 | P03 | Commercial assessment | 10
817 | P04 | Approval and close | 4
818 | P01 | Submission review | 5
818 | P02 | Technical assessment | 5
818 | P03 | Commercial assessment | 7
818 | P04 | Approval and close | 3
819 | P01 | Submission review | 6
819 | P02 | Technical assessment | 6
819 | P03 | Commercial assessment | 6
819 | P04 | Approval and close | 5
820 | P01 | Submission review | 5
820 | P02 | Technical assessment | 7
820 | P03 | Commercial assessment | 5
820 | P04 | Approval and close | 3
821 | P01 | Submission review | 3
821 | P02 | Technical assessment | 5
821 | P03 | Commercial assessment | 9
821 | P04 | Approval and close | 3
822 | P01 | Submission review | 3
822 | P02 | Technical assessment | 4
822 | P03 | Commercial assessment | 8
822 | P04 | Approval and close | 3
823 | P01 | Submission review | 5
823 | P02 | Technical assessment | 7
823 | P03 | Commercial assessment | 9
823 | P04 | Approval and close | 4
824 | P01 | Submission review | 5
824 | P02 | Technical assessment | 6
824 | P03 | Commercial assessment | 8
824 | P04 | Approval and close | 4
825 | P01 | Submission review | 5
825 | P02 | Technical assessment | 4
825 | P03 | Commercial assessment | 6
825 | P04 | Approval and close | 3
826 | P01 | Submission review | 6
826 | P02 | Technical assessment | 8
826 | P03 | Commercial assessment | 7
826 | P04 | Approval and close | 3
827 | P01 | Submission review | 4
827 | P02 | Technical assessment | 6
827 | P03 | Commercial assessment | 6
827 | P04 | Approval and close | 2
828 | P01 | Submission review | 5
828 | P02 | Technical assessment | 5
828 | P03 | Commercial assessment | 7
828 | P04 | Approval and close | 3
829 | P01 | Submission review | 3
829 | P02 | Technical assessment | 6
829 | P03 | Commercial assessment | 4
829 | P04 | Approval and close | 4
830 | P01 | Submission review | 5
830 | P02 | Technical assessment | 6
830 | P03 | Commercial assessment | 5
830 | P04 | Approval and close | 4
831 | P01 | Submission review | 5
831 | P02 | Technical assessment | 5
831 | P03 | Commercial assessment | 6
831 | P04 | Approval and close | 3
832 | P01 | Submission review | 4
832 | P02 | Technical assessment | 7
832 | P03 | Commercial assessment | 7
832 | P04 | Approval and close | 3
833 | P01 | Submission review | 3
833 | P02 | Technical assessment | 8
833 | P03 | Commercial assessment | 8
833 | P04 | Approval and close | 5
834 | P01 | Submission review | 5
834 | P02 | Technical assessment | 8
834 | P03 | Commercial assessment | 7
834 | P04 | Approval and close | 4
835 | P01 | Submission review | 4
835 | P02 | Technical assessment | 7
835 | P03 | Commercial assessment | 6
835 | P04 | Approval and close | 2
836 | P01 | Submission review | 5
836 | P02 | Technical assessment | 6
836 | P03 | Commercial assessment | 7
836 | P04 | Approval and close | 4
837 | P01 | Submission review | 3
837 | P02 | Technical assessment | 6
837 | P03 | Commercial assessment | 8
837 | P04 | Approval and close | 4
838 | P01 | Submission review | 5
838 | P02 | Technical assessment | 4
838 | P03 | Commercial assessment | 4
838 | P04 | Approval and close | 4
839 | P01 | Submission review | 4
839 | P02 | Technical assessment | 5
839 | P03 | Commercial assessment | 9
839 | P04 | Approval and close | 3
840 | P01 | Submission review | 5
840 | P02 | Technical assessment | 5
840 | P03 | Commercial assessment | 9
840 | P04 | Approval and close | 3
841 | P01 | Submission review | 4
841 | P02 | Technical assessment | 5
841 | P03 | Commercial assessment | 8
841 | P04 | Approval and close | 4
842 | P01 | Submission review | 4
842 | P02 | Technical assessment | 4
842 | P03 | Commercial assessment | 10
842 | P04 | Approval and close | 3
843 | P01 | Submission review | 6
843 | P02 | Technical assessment | 5
843 | P03 | Commercial assessment | 7
843 | P04 | Approval and close | 4
844 | P01 | Submission review | 4
844 | P02 | Technical assessment | 6
844 | P03 | Commercial assessment | 7
844 | P04 | Approval and close | 2
845 | P01 | Submission review | 3
845 | P02 | Technical assessment | 6
845 | P03 | Commercial assessment | 4
845 | P04 | Approval and close | 4
846 | P01 | Submission review | 4
846 | P02 | Technical assessment | 5
846 | P03 | Commercial assessment | 6
846 | P04 | Approval and close | 5
847 | P01 | Submission review | 5
847 | P02 | Technical assessment | 5
847 | P03 | Commercial assessment | 7
847 | P04 | Approval and close | 5
848 | P01 | Submission review | 4
848 | P02 | Technical assessment | 5
848 | P03 | Commercial assessment | 7
848 | P04 | Approval and close | 3
849 | P01 | Submission review | 6
849 | P02 | Technical assessment | 4
849 | P03 | Commercial assessment | 5
849 | P04 | Approval and close | 3
850 | P01 | Submission review | 4
850 | P02 | Technical assessment | 5
850 | P03 | Commercial assessment | 4
850 | P04 | Approval and close | 3
851 | P01 | Submission review | 5
851 | P02 | Technical assessment | 9
851 | P03 | Commercial assessment | 6
851 | P04 | Approval and close | 3
852 | P01 | Submission review | 6
852 | P02 | Technical assessment | 8
852 | P03 | Commercial assessment | 6
852 | P04 | Approval and close | 3
853 | P01 | Submission review | 3
853 | P02 | Technical assessment | 7
853 | P03 | Commercial assessment | 7
853 | P04 | Approval and close | 2
854 | P01 | Submission review | 5
854 | P02 | Technical assessment | 6
854 | P03 | Commercial assessment | 5
854 | P04 | Approval and close | 3
855 | P01 | Submission review | 3
855 | P02 | Technical assessment | 5
855 | P03 | Commercial assessment | 5
855 | P04 | Approval and close | 4
856 | P01 | Submission review | 6
856 | P02 | Technical assessment | 7
856 | P03 | Commercial assessment | 9
856 | P04 | Approval and close | 4
857 | P01 | Submission review | 4
857 | P02 | Technical assessment | 6
857 | P03 | Commercial assessment | 7
857 | P04 | Approval and close | 4
858 | P01 | Submission review | 6
858 | P02 | Technical assessment | 7
858 | P03 | Commercial assessment | 5
858 | P04 | Approval and close | 3
859 | P01 | Submission review | 5
859 | P02 | Technical assessment | 5
859 | P03 | Commercial assessment | 9
859 | P04 | Approval and close | 3
860 | P01 | Submission review | 4
860 | P02 | Technical assessment | 5
860 | P03 | Commercial assessment | 4
860 | P04 | Approval and close | 4
861 | P01 | Submission review | 6
861 | P02 | Technical assessment | 5
861 | P03 | Commercial assessment | 8
861 | P04 | Approval and close | 3
862 | P01 | Submission review | 4
862 | P02 | Technical assessment | 4
862 | P03 | Commercial assessment | 5
862 | P04 | Approval and close | 3
863 | P01 | Submission review | 6
863 | P02 | Technical assessment | 6
863 | P03 | Commercial assessment | 5
863 | P04 | Approval and close | 4
864 | P01 | Submission review | 5
864 | P02 | Technical assessment | 5
864 | P03 | Commercial assessment | 9
864 | P04 | Approval and close | 4
865 | P01 | Submission review | 6
865 | P02 | Technical assessment | 7
865 | P03 | Commercial assessment | 4
865 | P04 | Approval and close | 5
866 | P01 | Submission review | 6
866 | P02 | Technical assessment | 7
866 | P03 | Commercial assessment | 9
866 | P04 | Approval and close | 3
867 | P01 | Submission review | 5
867 | P02 | Technical assessment | 6
867 | P03 | Commercial assessment | 7
867 | P04 | Approval and close | 3
868 | P01 | Submission review | 4
868 | P02 | Technical assessment | 4
868 | P03 | Commercial assessment | 4
868 | P04 | Approval and close | 4
869 | P01 | Submission review | 3
869 | P02 | Technical assessment | 6
869 | P03 | Commercial assessment | 6
869 | P04 | Approval and close | 3
870 | P01 | Submission review | 3
870 | P02 | Technical assessment | 5
870 | P03 | Commercial assessment | 8
870 | P04 | Approval and close | 3
871 | P01 | Submission review | 6
871 | P02 | Technical assessment | 5
871 | P03 | Commercial assessment | 5
871 | P04 | Approval and close | 5
872 | P01 | Submission review | 3
872 | P02 | Technical assessment | 6
872 | P03 | Commercial assessment | 5
872 | P04 | Approval and close | 3
873 | P01 | Submission review | 4
873 | P02 | Technical assessment | 8
873 | P03 | Commercial assessment | 4
873 | P04 | Approval and close | 4
874 | P01 | Submission review | 5
874 | P02 | Technical assessment | 7
874 | P03 | Commercial assessment | 10
874 | P04 | Approval and close | 4
875 | P01 | Submission review | 3
875 | P02 | Technical assessment | 6
875 | P03 | Commercial assessment | 8
875 | P04 | Approval and close | 3
876 | P01 | Submission review | 5
876 | P02 | Technical assessment | 6
876 | P03 | Commercial assessment | 10
876 | P04 | Approval and close | 5
877 | P01 | Submission review | 4
877 | P02 | Technical assessment | 7
877 | P03 | Commercial assessment | 5
877 | P04 | Approval and close | 3
878 | P01 | Submission review | 6
878 | P02 | Technical assessment | 4
878 | P03 | Commercial assessment | 8
878 | P04 | Approval and close | 3
879 | P01 | Submission review | 4
879 | P02 | Technical assessment | 7
879 | P03 | Commercial assessment | 8
879 | P04 | Approval and close | 2
880 | P01 | Submission review | 5
880 | P02 | Technical assessment | 6
880 | P03 | Commercial assessment | 6
880 | P04 | Approval and close | 4
881 | P01 | Submission review | 6
881 | P02 | Technical assessment | 5
881 | P03 | Commercial assessment | 6
881 | P04 | Approval and close | 3
882 | P01 | Submission review | 3
882 | P02 | Technical assessment | 7
882 | P03 | Commercial assessment | 5
882 | P04 | Approval and close | 3
883 | P01 | Submission review | 5
883 | P02 | Technical assessment | 8
883 | P03 | Commercial assessment | 6
883 | P04 | Approval and close | 3
884 | P01 | Submission review | 4
884 | P02 | Technical assessment | 6
884 | P03 | Commercial assessment | 8
884 | P04 | Approval and close | 4
885 | P01 | Submission review | 7
885 | P02 | Technical assessment | 8
885 | P03 | Commercial assessment | 6
885 | P04 | Approval and close | 4
886 | P01 | Submission review | 4
886 | P02 | Technical assessment | 5
886 | P03 | Commercial assessment | 5
886 | P04 | Approval and close | 3
887 | P01 | Submission review | 4
887 | P02 | Technical assessment | 8
887 | P03 | Commercial assessment | 5
887 | P04 | Approval and close | 3
888 | P01 | Submission review | 4
888 | P02 | Technical assessment | 5
888 | P03 | Commercial assessment | 4
888 | P04 | Approval and close | 3
889 | P01 | Submission review | 6
889 | P02 | Technical assessment | 6
889 | P03 | Commercial assessment | 5
889 | P04 | Approval and close | 3
890 | P01 | Submission review | 6
890 | P02 | Technical assessment | 7
890 | P03 | Commercial assessment | 6
890 | P04 | Approval and close | 4
891 | P01 | Submission review | 5
891 | P02 | Technical assessment | 5
891 | P03 | Commercial assessment | 7
891 | P04 | Approval and close | 5
892 | P01 | Submission review | 4
892 | P02 | Technical assessment | 6
892 | P03 | Commercial assessment | 6
892 | P04 | Approval and close | 2
893 | P01 | Submission review | 7
893 | P02 | Technical assessment | 6
893 | P03 | Commercial assessment | 7
893 | P04 | Approval and close | 3
894 | P01 | Submission review | 4
894 | P02 | Technical assessment | 6
894 | P03 | Commercial assessment | 6
894 | P04 | Approval and close | 3
895 | P01 | Submission review | 5
895 | P02 | Technical assessment | 4
895 | P03 | Commercial assessment | 9
895 | P04 | Approval and close | 3
896 | P01 | Submission review | 3
896 | P02 | Technical assessment | 7
896 | P03 | Commercial assessment | 5
896 | P04 | Approval and close | 3
897 | P01 | Submission review | 6
897 | P02 | Technical assessment | 6
897 | P03 | Commercial assessment | 7
897 | P04 | Approval and close | 4
898 | P01 | Submission review | 4
898 | P02 | Technical assessment | 6
898 | P03 | Commercial assessment | 6
898 | P04 | Approval and close | 4
899 | P01 | Submission review | 3
899 | P02 | Technical assessment | 5
899 | P03 | Commercial assessment | 6
899 | P04 | Approval and close | 3
900 | P01 | Submission review | 6
900 | P02 | Technical assessment | 6
900 | P03 | Commercial assessment | 7
900 | P04 | Approval and close | 3
901 | P01 | Submission review | 4
901 | P02 | Technical assessment | 5
901 | P03 | Commercial assessment | 8
901 | P04 | Approval and close | 5
902 | P01 | Submission review | 6
902 | P02 | Technical assessment | 6
902 | P03 | Commercial assessment | 8
902 | P04 | Approval and close | 3
903 | P01 | Submission review | 5
903 | P02 | Technical assessment | 7
903 | P03 | Commercial assessment | 6
903 | P04 | Approval and close | 3
904 | P01 | Submission review | 4
904 | P02 | Technical assessment | 5
904 | P03 | Commercial assessment | 7
904 | P04 | Approval and close | 4
905 | P01 | Submission review | 4
905 | P02 | Technical assessment | 6
905 | P03 | Commercial assessment | 5
905 | P04 | Approval and close | 4
906 | P01 | Submission review | 4
906 | P02 | Technical assessment | 9
906 | P03 | Commercial assessment | 10
906 | P04 | Approval and close | 4
907 | P01 | Submission review | 6
907 | P02 | Technical assessment | 8
907 | P03 | Commercial assessment | 7
907 | P04 | Approval and close | 2
908 | P01 | Submission review | 4
908 | P02 | Technical assessment | 5
908 | P03 | Commercial assessment | 4
908 | P04 | Approval and close | 5
909 | P01 | Submission review | 4
909 | P02 | Technical assessment | 5
909 | P03 | Commercial assessment | 10
909 | P04 | Approval and close | 2
910 | P01 | Submission review | 6
910 | P02 | Technical assessment | 7
910 | P03 | Commercial assessment | 5
910 | P04 | Approval and close | 3
911 | P01 | Submission review | 6
911 | P02 | Technical assessment | 7
911 | P03 | Commercial assessment | 8
911 | P04 | Approval and close | 3
912 | P01 | Submission review | 4
912 | P02 | Technical assessment | 5
912 | P03 | Commercial assessment | 5
912 | P04 | Approval and close | 3
913 | P01 | Submission review | 5
913 | P02 | Technical assessment | 4
913 | P03 | Commercial assessment | 8
913 | P04 | Approval and close | 4
914 | P01 | Submission review | 3
914 | P02 | Technical assessment | 5
914 | P03 | Commercial assessment | 6
914 | P04 | Approval and close | 3
915 | P01 | Submission review | 3
915 | P02 | Technical assessment | 7
915 | P03 | Commercial assessment | 6
915 | P04 | Approval and close | 3
916 | P01 | Submission review | 5
916 | P02 | Technical assessment | 7
916 | P03 | Commercial assessment | 4
916 | P04 | Approval and close | 4
917 | P01 | Submission review | 7
917 | P02 | Technical assessment | 6
917 | P03 | Commercial assessment | 8
917 | P04 | Approval and close | 3
918 | P01 | Submission review | 5
918 | P02 | Technical assessment | 5
918 | P03 | Commercial assessment | 5
918 | P04 | Approval and close | 2
919 | P01 | Submission review | 4
919 | P02 | Technical assessment | 6
919 | P03 | Commercial assessment | 7
919 | P04 | Approval and close | 3
920 | P01 | Submission review | 3
920 | P02 | Technical assessment | 4
920 | P03 | Commercial assessment | 7
920 | P04 | Approval and close | 3
921 | P01 | Submission review | 5
921 | P02 | Technical assessment | 5
921 | P03 | Commercial assessment | 8
921 | P04 | Approval and close | 2
922 | P01 | Submission review | 4
922 | P02 | Technical assessment | 6
922 | P03 | Commercial assessment | 8
922 | P04 | Approval and close | 3
923 | P01 | Submission review | 6
923 | P02 | Technical assessment | 4
923 | P03 | Commercial assessment | 6
923 | P04 | Approval and close | 4
924 | P01 | Submission review | 5
924 | P02 | Technical assessment | 5
924 | P03 | Commercial assessment | 7
924 | P04 | Approval and close | 4
925 | P01 | Submission review | 6
925 | P02 | Technical assessment | 5
925 | P03 | Commercial assessment | 4
925 | P04 | Approval and close | 4
926 | P01 | Submission review | 4
926 | P02 | Technical assessment | 5
926 | P03 | Commercial assessment | 10
926 | P04 | Approval and close | 4
927 | P01 | Submission review | 3
927 | P02 | Technical assessment | 6
927 | P03 | Commercial assessment | 8
927 | P04 | Approval and close | 4
928 | P01 | Submission review | 4
928 | P02 | Technical assessment | 7
928 | P03 | Commercial assessment | 6
928 | P04 | Approval and close | 4
929 | P01 | Submission review | 6
929 | P02 | Technical assessment | 7
929 | P03 | Commercial assessment | 5
929 | P04 | Approval and close | 4
930 | P01 | Submission review | 6
930 | P02 | Technical assessment | 7
930 | P03 | Commercial assessment | 6
930 | P04 | Approval and close | 4
931 | P01 | Submission review | 6
931 | P02 | Technical assessment | 6
931 | P03 | Commercial assessment | 7
931 | P04 | Approval and close | 3
932 | P01 | Submission review | 5
932 | P02 | Technical assessment | 6
932 | P03 | Commercial assessment | 5
932 | P04 | Approval and close | 3
933 | P01 | Submission review | 3
933 | P02 | Technical assessment | 8
933 | P03 | Commercial assessment | 4
933 | P04 | Approval and close | 5
934 | P01 | Submission review | 6
934 | P02 | Technical assessment | 6
934 | P03 | Commercial assessment | 6
934 | P04 | Approval and close | 2
935 | P01 | Submission review | 7
935 | P02 | Technical assessment | 5
935 | P03 | Commercial assessment | 9
935 | P04 | Approval and close | 4
936 | P01 | Submission review | 6
936 | P02 | Technical assessment | 5
936 | P03 | Commercial assessment | 9
936 | P04 | Approval and close | 3
937 | P01 | Submission review | 3
937 | P02 | Technical assessment | 5
937 | P03 | Commercial assessment | 4
937 | P04 | Approval and close | 4
938 | P01 | Submission review | 5
938 | P02 | Technical assessment | 7
938 | P03 | Commercial assessment | 9
938 | P04 | Approval and close | 4
939 | P01 | Submission review | 6
939 | P02 | Technical assessment | 7
939 | P03 | Commercial assessment | 9
939 | P04 | Approval and close | 4
940 | P01 | Submission review | 5
940 | P02 | Technical assessment | 9
940 | P03 | Commercial assessment | 8
940 | P04 | Approval and close | 4
941 | P01 | Submission review | 6
941 | P02 | Technical assessment | 5
941 | P03 | Commercial assessment | 4
941 | P04 | Approval and close | 3
942 | P01 | Submission review | 3
942 | P02 | Technical assessment | 5
942 | P03 | Commercial assessment | 8
942 | P04 | Approval and close | 4
943 | P01 | Submission review | 4
943 | P02 | Technical assessment | 6
943 | P03 | Commercial assessment | 5
943 | P04 | Approval and close | 3
944 | P01 | Submission review | 5
944 | P02 | Technical assessment | 7
944 | P03 | Commercial assessment | 9
944 | P04 | Approval and close | 2
945 | P01 | Submission review | 5
945 | P02 | Technical assessment | 4
945 | P03 | Commercial assessment | 10
945 | P04 | Approval and close | 3
946 | P01 | Submission review | 5
946 | P02 | Technical assessment | 8
946 | P03 | Commercial assessment | 6
946 | P04 | Approval and close | 4
947 | P01 | Submission review | 5
947 | P02 | Technical assessment | 6
947 | P03 | Commercial assessment | 5
947 | P04 | Approval and close | 5
948 | P01 | Submission review | 5
948 | P02 | Technical assessment | 5
948 | P03 | Commercial assessment | 6
948 | P04 | Approval and close | 3
949 | P01 | Submission review | 4
949 | P02 | Technical assessment | 4
949 | P03 | Commercial assessment | 6
949 | P04 | Approval and close | 3
950 | P01 | Submission review | 4
950 | P02 | Technical assessment | 6
950 | P03 | Commercial assessment | 4
950 | P04 | Approval and close | 4
951 | P01 | Submission review | 7
951 | P02 | Technical assessment | 6
951 | P03 | Commercial assessment | 7
951 | P04 | Approval and close | 5
952 | P01 | Submission review | 4
952 | P02 | Technical assessment | 4
952 | P03 | Commercial assessment | 6
952 | P04 | Approval and close | 3
953 | P01 | Submission review | 4
953 | P02 | Technical assessment | 6
953 | P03 | Commercial assessment | 6
953 | P04 | Approval and close | 4
954 | P01 | Submission review | 5
954 | P02 | Technical assessment | 8
954 | P03 | Commercial assessment | 8
954 | P04 | Approval and close | 4
955 | P01 | Submission review | 3
955 | P02 | Technical assessment | 6
955 | P03 | Commercial assessment | 7
955 | P04 | Approval and close | 3
956 | P01 | Submission review | 4
956 | P02 | Technical assessment | 7
956 | P03 | Commercial assessment | 5
956 | P04 | Approval and close | 3
957 | P01 | Submission review | 6
957 | P02 | Technical assessment | 6
957 | P03 | Commercial assessment | 8
957 | P04 | Approval and close | 4
958 | P01 | Submission review | 5
958 | P02 | Technical assessment | 6
958 | P03 | Commercial assessment | 5
958 | P04 | Approval and close | 3
959 | P01 | Submission review | 6
959 | P02 | Technical assessment | 5
959 | P03 | Commercial assessment | 6
959 | P04 | Approval and close | 4
960 | P01 | Submission review | 6
960 | P02 | Technical assessment | 8
960 | P03 | Commercial assessment | 8
960 | P04 | Approval and close | 3
961 | P01 | Submission review | 3
961 | P02 | Technical assessment | 7
961 | P03 | Commercial assessment | 9
961 | P04 | Approval and close | 4
962 | P01 | Submission review | 5
962 | P02 | Technical assessment | 7
962 | P03 | Commercial assessment | 10
962 | P04 | Approval and close | 4
963 | P01 | Submission review | 6
963 | P02 | Technical assessment | 7
963 | P03 | Commercial assessment | 5
963 | P04 | Approval and close | 3
964 | P01 | Submission review | 5
964 | P02 | Technical assessment | 6
964 | P03 | Commercial assessment | 9
964 | P04 | Approval and close | 4
965 | P01 | Submission review | 5
965 | P02 | Technical assessment | 5
965 | P03 | Commercial assessment | 5
965 | P04 | Approval and close | 2
966 | P01 | Submission review | 5
966 | P02 | Technical assessment | 7
966 | P03 | Commercial assessment | 10
966 | P04 | Approval and close | 5
967 | P01 | Submission review | 5
967 | P02 | Technical assessment | 6
967 | P03 | Commercial assessment | 5
967 | P04 | Approval and close | 3
968 | P01 | Submission review | 5
968 | P02 | Technical assessment | 6
968 | P03 | Commercial assessment | 7
968 | P04 | Approval and close | 3
969 | P01 | Submission review | 4
969 | P02 | Technical assessment | 5
969 | P03 | Commercial assessment | 5
969 | P04 | Approval and close | 3
970 | P01 | Submission review | 4
970 | P02 | Technical assessment | 5
970 | P03 | Commercial assessment | 9
970 | P04 | Approval and close | 2
971 | P01 | Submission review | 6
971 | P02 | Technical assessment | 5
971 | P03 | Commercial assessment | 5
971 | P04 | Approval and close | 4
972 | P01 | Submission review | 4
972 | P02 | Technical assessment | 6
972 | P03 | Commercial assessment | 6
972 | P04 | Approval and close | 3
973 | P01 | Submission review | 6
973 | P02 | Technical assessment | 8
973 | P03 | Commercial assessment | 5
973 | P04 | Approval and close | 4
974 | P01 | Submission review | 4
974 | P02 | Technical assessment | 6
974 | P03 | Commercial assessment | 7
974 | P04 | Approval and close | 3
975 | P01 | Submission review | 6
975 | P02 | Technical assessment | 5
975 | P03 | Commercial assessment | 7
975 | P04 | Approval and close | 4
976 | P01 | Submission review | 6
976 | P02 | Technical assessment | 6
976 | P03 | Commercial assessment | 7
976 | P04 | Approval and close | 4
977 | P01 | Submission review | 5
977 | P02 | Technical assessment | 4
977 | P03 | Commercial assessment | 10
977 | P04 | Approval and close | 4
978 | P01 | Submission review | 3
978 | P02 | Technical assessment | 7
978 | P03 | Commercial assessment | 6
978 | P04 | Approval and close | 4
979 | P01 | Submission review | 5
979 | P02 | Technical assessment | 5
979 | P03 | Commercial assessment | 5
979 | P04 | Approval and close | 4
980 | P01 | Submission review | 6
980 | P02 | Technical assessment | 4
980 | P03 | Commercial assessment | 6
980 | P04 | Approval and close | 3
981 | P01 | Submission review | 3
981 | P02 | Technical assessment | 9
981 | P03 | Commercial assessment | 10
981 | P04 | Approval and close | 4
982 | P01 | Submission review | 6
982 | P02 | Technical assessment | 6
982 | P03 | Commercial assessment | 5
982 | P04 | Approval and close | 4
983 | P01 | Submission review | 3
983 | P02 | Technical assessment | 6
983 | P03 | Commercial assessment | 8
983 | P04 | Approval and close | 3
984 | P01 | Submission review | 4
984 | P02 | Technical assessment | 4
984 | P03 | Commercial assessment | 9
984 | P04 | Approval and close | 4
985 | P01 | Submission review | 4
985 | P02 | Technical assessment | 7
985 | P03 | Commercial assessment | 9
985 | P04 | Approval and close | 4
986 | P01 | Submission review | 5
986 | P02 | Technical assessment | 6
986 | P03 | Commercial assessment | 6
986 | P04 | Approval and close | 5
987 | P01 | Submission review | 5
987 | P02 | Technical assessment | 5
987 | P03 | Commercial assessment | 8
987 | P04 | Approval and close | 4
988 | P01 | Submission review | 5
988 | P02 | Technical assessment | 4
988 | P03 | Commercial assessment | 7
988 | P04 | Approval and close | 4
989 | P01 | Submission review | 5
989 | P02 | Technical assessment | 5
989 | P03 | Commercial assessment | 6
989 | P04 | Approval and close | 2
990 | P01 | Submission review | 6
990 | P02 | Technical assessment | 8
990 | P03 | Commercial assessment | 8
990 | P04 | Approval and close | 3
991 | P01 | Submission review | 3
991 | P02 | Technical assessment | 6
991 | P03 | Commercial assessment | 6
991 | P04 | Approval and close | 3
992 | P01 | Submission review | 5
992 | P02 | Technical assessment | 6
992 | P03 | Commercial assessment | 10
992 | P04 | Approval and close | 4
993 | P01 | Submission review | 4
993 | P02 | Technical assessment | 6
993 | P03 | Commercial assessment | 7
993 | P04 | Approval and close | 4
994 | P01 | Submission review | 4
994 | P02 | Technical assessment | 4
994 | P03 | Commercial assessment | 5
994 | P04 | Approval and close | 4
995 | P01 | Submission review | 4
995 | P02 | Technical assessment | 8
995 | P03 | Commercial assessment | 9
995 | P04 | Approval and close | 2
996 | P01 | Submission review | 5
996 | P02 | Technical assessment | 4
996 | P03 | Commercial assessment | 8
996 | P04 | Approval and close | 2
997 | P01 | Submission review | 5
997 | P02 | Technical assessment | 4
997 | P03 | Commercial assessment | 7
997 | P04 | Approval and close | 3
998 | P01 | Submission review | 4
998 | P02 | Technical assessment | 8
998 | P03 | Commercial assessment | 7
998 | P04 | Approval and close | 4
999 | P01 | Submission review | 4
999 | P02 | Technical assessment | 4
999 | P03 | Commercial assessment | 8
999 | P04 | Approval and close | 3
1000 | P01 | Submission review | 4
1000 | P02 | Technical assessment | 5
1000 | P03 | Commercial assessment | 11
1000 | P04 | Approval and close | 4

## Convergence
Checkpoint | Metric | Value | Relative Change | Stable
100 | PERT Total | 21.04 | 0 | FALSE
200 | PERT Total | 20.935 | 0.0049905 | TRUE
300 | PERT Total | 20.91 | 0.0011942 | TRUE
400 | PERT Total | 20.8225 | 0.0041846 | TRUE
500 | PERT Total | 20.882 | 0.0028575 | TRUE
600 | PERT Total | 20.8617 | 0.00097373 | TRUE
700 | PERT Total | 20.84 | 0.0010386 | TRUE
800 | PERT Total | 20.725 | 0.0055182 | TRUE
900 | PERT Total | 20.7144 | 0.00050932 | TRUE
1000 | PERT Total | 20.75 | 0.0017165 | TRUE